## Project Overview
Senior SQL Practice Project: Global Logistics Data Warehouse
Project Type | Self-directed portfolio and interview practice project
Target Role | Senior Azure Data Engineer, approximately 6-year capability level
Business Scenario | Build a SQL data warehouse for global logistics orders, shipments, customer history, revenue, delay analysis, incremental loading, performance tuning, and reconciliation.
Practice Commitment | 2 to 3 hours per working day
Database Recommendation | SQL Server Developer Edition or Azure SQL Database
Delivery Method | Complete phases sequentially; record evidence, test results, and design decisions.
Important Resume Note | Describe this as a personal or portfolio project unless implemented for a real client. Do not present synthetic volumes or outcomes as production facts.
Business Outcomes
• Design a defensible star schema with explicit fact-table grain.
• Implement dimensions and facts with auditability and unknown-member handling.
• Implement SCD Type 2 customer history.
• Produce revenue, growth, ranking, delivery-delay, and trend analytics.
• Build restartable incremental loading using a watermark and batch-control pattern.
• Investigate and optimize large-table query performance.
• Reconcile revenue and document root-cause evidence.
• Package scripts, tests, diagrams, runbooks, and portfolio evidence.
Workbook Guide
Requirements | Detailed business, functional, non-functional, data, and acceptance requirements.
Task Plan | Small implementation tasks with planned hours, dependencies, deliverables, status, and completion.
Daily Plan | A formula-driven 2 to 3 hour working-day schedule.
Test Cases | Functional, data-quality, reconciliation, failure-recovery, and performance tests.
Data Dictionary | Source and warehouse object/column definitions.
Dashboard | Overall progress, planned hours, test progress, and phase charts.
Risks & Decisions | Architecture risks, mitigations, assumptions, and decision log.
Resume Notes | Honest portfolio wording and interview discussion points.

## Requirements
Detailed Requirements Register
Requirement ID | Phase | Category | Requirement | Detailed Description | Priority | Acceptance Criteria | Deliverable
REQ-001 | 1 - Warehouse Modeling | Business | Confirm analytical scope | Define revenue, customer, product, location, order, shipment and calendar analysis required by stakeholders. | Must | Scope explicitly lists included metrics and excluded scenarios. | Scope document
REQ-002 | 1 - Warehouse Modeling | Modeling | Declare FactOrders grain | Define one row per order line, represented by OrderID plus OrderLineNumber. ProductID alone is insufficient if the same product can appear more than once in an order. | Must | Grain statement is written before table design and every fact column conforms to it. | Grain statement
REQ-003 | 1 - Warehouse Modeling | Modeling | Declare FactShipment grain | Define one row per shipment event or shipment record. Document treatment of split shipments and multiple delivery attempts. | Must | Grain and business key are unambiguous. | Shipment grain statement
REQ-004 | 1 - Warehouse Modeling | Modeling | Design star schema | Create FactOrders, FactShipment, DimCustomer, DimProduct, DimDate and DimLocation relationships. | Must | Diagram shows PK/FK relationships and no unresolved many-to-many relationship. | ERD/star schema
REQ-005 | 1 - Warehouse Modeling | Keys | Use surrogate keys | Use integer/bigint surrogate keys for warehouse dimensions while retaining source business keys. | Must | Facts reference surrogate keys; source keys remain available for traceability. | DDL design
REQ-006 | 1 - Warehouse Modeling | Keys | Create unknown members | Insert key 0 or -1 rows for unknown customer, product, date or location where applicable. | Must | Unmatched source rows load without null dimension foreign keys and are reportable. | Unknown-member script
REQ-007 | 1 - Warehouse Modeling | Data | Define additive measures | Store Quantity, GrossAmount, DiscountAmount, NetAmount, CostAmount and FreightAllocatedAmount at the declared grain where available. | Should | Each measure has a definition and aggregation behavior. | Measure catalogue
REQ-008 | 1 - Warehouse Modeling | Audit | Add audit columns | Include BatchID, SourceSystem, SourceModifiedDate, InsertedDateTime and UpdatedDateTime where applicable. | Must | Every loaded row can be traced to a batch and source. | Audit-column standard
REQ-009 | 1 - Warehouse Modeling | Modeling | Role-playing date dimensions | Represent OrderDate, ShipmentDate and DeliveryDate through separate foreign keys to DimDate. | Must | Date roles are clear and joins return correct calendar attributes. | Date-key design
REQ-010 | 1 - Warehouse Modeling | Data Quality | Enforce key integrity | Define PK, unique business-key constraints where practical, and FK strategy. | Should | Duplicate dimension business keys and orphan fact keys are detected. | Constraint script
REQ-011 | 2 - SCD Type 2 | History | Track customer changes | Track City, Country and CustomerType changes while preserving prior values. | Must | A changed tracked attribute expires the old row and creates one new current row. | SCD procedure
REQ-012 | 2 - SCD Type 2 | History | Ignore non-changing records | Do not create a new dimension version when tracked values are unchanged. | Must | Reprocessing identical source produces no extra versions. | Idempotency evidence
REQ-013 | 2 - SCD Type 2 | History | Handle new customers | Insert first version with EffectiveFrom, open-ended EffectiveTo and IsCurrent=1. | Must | New business key has exactly one current row. | Insert logic
REQ-014 | 2 - SCD Type 2 | History | Close prior version | Expire old row immediately before the new version starts using the selected timestamp convention. | Must | No overlap exists in effective date ranges. | Expiry logic
REQ-015 | 2 - SCD Type 2 | History | Maintain current-row uniqueness | Ensure no CustomerID has more than one IsCurrent=1 row. | Must | Uniqueness test returns zero violations. | Uniqueness test
REQ-016 | 2 - SCD Type 2 | History | Null-safe comparison | Treat null-to-value, value-to-null and value-to-different-value as changes. | Must | All null transition tests pass. | Comparison logic
REQ-017 | 2 - SCD Type 2 | Late Data | Define late-arriving customer handling | Document what happens when a fact arrives before its customer dimension record. | Should | Fact initially uses unknown key and has a documented correction process. | Late-arriving runbook
REQ-018 | 2 - SCD Type 2 | Audit | Capture change metadata | Store source modified timestamp and load batch identifier for every version. | Must | Version history is traceable to source and batch. | Audit query
REQ-019 | 3 - Revenue Analytics | Metric | Define revenue | Document whether revenue means gross, net, invoiced, recognized, local-currency or reporting-currency revenue. | Must | One approved SQL expression defines the metric. | Metric definition
REQ-020 | 3 - Revenue Analytics | Analytics | Monthly customer revenue | Aggregate revenue by customer and calendar month. | Must | Result reconciles to the fact table for the same filters. | Revenue view
REQ-021 | 3 - Revenue Analytics | Analytics | Previous month comparison | Use LAG to retrieve prior calendar-month revenue for each customer. | Must | January-to-December boundary works correctly. | Growth query
REQ-022 | 3 - Revenue Analytics | Analytics | Growth percentage | Calculate growth with divide-by-zero and absent-prior-month handling. | Must | No divide-by-zero error; documented null/zero rules are applied. | Growth calculation
REQ-023 | 3 - Revenue Analytics | Analytics | Zero-activity month handling | Choose whether missing months are absent or generated with a date scaffold. | Should | Output follows the documented reporting behavior. | Calendar scaffold logic
REQ-024 | 3 - Revenue Analytics | Analytics | Revenue trend | Produce month, quarter and year trend outputs. | Should | Totals remain consistent across hierarchy levels. | Trend view
REQ-025 | 3 - Revenue Analytics | Currency | Reporting currency rule | If multiple currencies exist, define exchange-rate date and conversion logic rather than summing currencies directly. | Must | Cross-currency totals only appear after conversion. | Currency design note
REQ-026 | 4 - Deduplication | Quality | Identify duplicate order events | Profile duplicate frequency by OrderID and OrderLineNumber. | Must | Duplicate counts and affected keys are reported. | Profiling query
REQ-027 | 4 - Deduplication | Quality | Define survivor rule | Keep the record with greatest SourceModifiedDate, then IngestionDateTime, then deterministic tie-breaker. | Must | Exactly one survivor exists per business key. | Survivorship rule
REQ-028 | 4 - Deduplication | Quality | Implement ROW_NUMBER | Use partitioned ROW_NUMBER to select the survivor. | Must | Dedup output has no duplicate natural keys. | Dedup view/procedure
REQ-029 | 4 - Deduplication | Quality | Quarantine rejected rows | Persist discarded duplicates with rejection reason and batch details. | Should | Rejected rows can be audited and replayed. | Reject table
REQ-030 | 4 - Deduplication | Quality | Ensure idempotency | Rerunning the same batch must not create additional target rows. | Must | Row counts remain unchanged after rerun. | Rerun evidence
REQ-031 | 4 - Deduplication | Quality | Handle exact ties | Use a deterministic final tie-breaker when timestamps are equal. | Must | Repeated execution selects the same row. | Tie-break test
REQ-032 | 5 - Delivery Delay | Metric | Define delivery duration | Calculate delivery days from ShipmentDate to DeliveryDate using an agreed calendar-day or business-day rule. | Must | Rule and SQL expression are documented. | Delay definition
REQ-033 | 5 - Delivery Delay | Metric | Identify late delivery | Flag delivery duration greater than 7 days as late. | Must | Boundary checks for day 7 and day 8 pass. | Late flag
REQ-034 | 5 - Delivery Delay | Analytics | Create non-overlapping buckets | Use 0-3, 4-7, 8-15 and 16+ days, avoiding overlap in the original 15+ wording. | Must | Every non-negative duration maps to exactly one bucket. | Bucket expression
REQ-035 | 5 - Delivery Delay | Quality | Handle undelivered shipments | Classify null DeliveryDate separately as In Transit or Undelivered. | Must | Null date does not appear as zero delay. | Null-handling logic
REQ-036 | 5 - Delivery Delay | Quality | Handle invalid chronology | Reject or flag DeliveryDate earlier than ShipmentDate. | Must | Negative duration is visible as a data-quality exception. | DQ rule
REQ-037 | 5 - Delivery Delay | Analytics | Delay KPI output | Report delayed shipment count, percentage, average days and bucket distribution. | Should | KPI denominators are documented and reconcilable. | Delay view
REQ-038 | 6 - Top Customers | Analytics | Rank within country | Rank customers by revenue separately within each country. | Must | Each country begins at rank 1. | Ranking query
REQ-039 | 6 - Top Customers | Analytics | Top 10 per country | Return customers whose rank is 10 or lower. | Must | No country returns rank above 10. | Top-customer view
REQ-040 | 6 - Top Customers | Analytics | Define tie behavior | Select RANK or DENSE_RANK and document whether ties can return more than 10 rows. | Must | Tie test matches documented behavior. | Tie decision
REQ-041 | 6 - Top Customers | History | Use transaction-time geography | Attribute the sale to the customer/location version valid on the order date. | Should | Historical country does not change when the customer later moves. | Temporal join
REQ-042 | 6 - Top Customers | Metric | Parameterize period | Allow ranking for a selected date range. | Should | Date filters are sargable and totals reconcile. | Parameterized procedure/view
REQ-043 | 7 - Incremental Load | Control | Create watermark table | Store PipelineName, SourceObject, LastSuccessfulWatermark, LastBatchID, Status and update timestamp. | Must | Each load has a recoverable control state. | Watermark table
REQ-044 | 7 - Incremental Load | Extraction | Read bounded source window | Capture high watermark at run start and extract greater than previous watermark and less than or equal to high watermark. | Must | Concurrent source changes are deferred safely to the next run. | Extraction query
REQ-045 | 7 - Incremental Load | Control | Advance only on success | Update the successful watermark only after target transaction and validations succeed. | Must | Failed run leaves previous successful watermark unchanged. | Commit logic
REQ-046 | 7 - Incremental Load | Recovery | Support restart | Reuse or safely regenerate batch state after failure without duplication. | Must | Injected failure can be rerun to a correct final state. | Restart procedure
REQ-047 | 7 - Incremental Load | Quality | Persist batch metrics | Record extracted, inserted, updated, rejected and target counts. | Must | Batch-control totals reconcile. | Batch audit table
REQ-048 | 7 - Incremental Load | Deletion | Define source-delete strategy | Choose soft delete, tombstone, CDC or periodic reconciliation. | Should | Deleted-source behavior is documented and tested. | Delete strategy
REQ-049 | 7 - Incremental Load | Late Data | Apply lookback window | Optionally reread a configurable historical period to catch late updates, while preserving idempotency. | Should | Late update is captured without duplicates. | Lookback logic
REQ-050 | 7 - Incremental Load | Concurrency | Prevent overlapping runs | Use an application lock or run-status check so the same pipeline cannot overlap unsafely. | Should | Second concurrent run is blocked or exits safely. | Concurrency control
REQ-051 | 7 - Incremental Load | Operations | Create operational logging | Capture start/end time, status, error message and executed procedure. | Must | Failed batch has actionable diagnostics. | Operational log
REQ-052 | 8 - Performance Tuning | Baseline | Capture baseline | Record elapsed time, CPU, logical reads, row count and execution plan for target queries. | Must | Before metrics and plan are saved. | Baseline report
REQ-053 | 8 - Performance Tuning | Indexing | Design clustered strategy | Choose a clustered key based on access pattern, uniqueness, width and load behavior. | Must | Decision is justified against measured workload. | Index decision
REQ-054 | 8 - Performance Tuning | Indexing | Design covering indexes | Create selective nonclustered indexes with INCLUDE columns for critical filters and joins. | Must | Plan and measured reads demonstrate benefit. | Index scripts
REQ-055 | 8 - Performance Tuning | Partitioning | Evaluate date partitioning | Partition very large facts by a date key only when pruning, maintenance and lifecycle benefits justify complexity. | Should | Partition elimination is demonstrated for date-filtered query. | Partition evidence
REQ-056 | 8 - Performance Tuning | SQL | Remove non-sargable predicates | Avoid functions on filtered columns and implicit datatype conversions. | Must | Seek-capable predicate is visible where appropriate. | Query rewrite
REQ-057 | 8 - Performance Tuning | Statistics | Maintain statistics | Define statistics update approach after significant loads. | Should | Estimated and actual row counts improve. | Maintenance script
REQ-058 | 8 - Performance Tuning | Aggregation | Create summary table | Build daily/monthly aggregate for high-frequency dashboard queries where justified. | Should | Aggregate reconciles and improves measured performance. | Aggregate table
REQ-059 | 8 - Performance Tuning | Analysis | Detect skew and parameter issues | Investigate skew, spills, memory grants and parameter-sensitive plans. | Should | Findings are tied to plan evidence. | Tuning notes
REQ-060 | 8 - Performance Tuning | Regression | Compare before and after | Document improvement without changing row-level results. | Must | Output checksum/count matches baseline and metrics are captured. | Performance report
REQ-061 | 9 - Reconciliation & RCA | Reconciliation | Build source-to-target control totals | Compare row count, quantity, gross, adjustments and net revenue by business date and batch. | Must | Differences are zero or explained. | Reconciliation report
REQ-062 | 9 - Reconciliation & RCA | RCA | Investigate revenue restatement | Assess late data, duplicate removal, SCD joins, failed batches, currency rates, deletes and filter changes. | Must | Evidence identifies or narrows the variance without guessing. | RCA worksheet
REQ-063 | 9 - Reconciliation & RCA | Reconciliation | Classify variances | Categorize timing, logic, reference-data, source-correction and processing variances. | Should | Every unresolved difference has an owner/status. | Variance table
REQ-064 | 9 - Reconciliation & RCA | Audit | Create lineage evidence | Trace dashboard total to aggregate, fact, batch and source keys. | Must | Sample metric can be traced end to end. | Lineage query
REQ-065 | 9 - Reconciliation & RCA | Quality | Set reconciliation thresholds | Define zero tolerance for counts where appropriate and approved tolerances for currency rounding. | Must | Threshold breaches fail or warn according to rule. | Threshold rules
REQ-066 | 9 - Reconciliation & RCA | Operations | Create support runbook | Document symptoms, diagnostic SQL, common causes, recovery and escalation evidence. | Should | Another engineer can follow the runbook. | Support runbook
REQ-067 | 10 - Packaging & Portfolio | Delivery | Organize source control | Store DDL, DML, procedures, views, tests and documentation in a clear repository structure. | Must | Fresh checkout contains all required assets. | Repository
REQ-068 | 10 - Packaging & Portfolio | Delivery | Create deployment order | Provide numbered scripts or automated deployment with dependency order. | Must | Empty database can be deployed successfully. | Deployment guide
REQ-069 | 10 - Packaging & Portfolio | Documentation | Create architecture document | Include assumptions, diagram, grain, keys, loading patterns and security considerations. | Must | Document is consistent with implementation. | Architecture document
REQ-070 | 10 - Packaging & Portfolio | Evidence | Capture test evidence | Record expected, actual, status and evidence query/file for all tests. | Must | All critical tests pass before completion. | Test report
REQ-071 | 10 - Packaging & Portfolio | Evidence | Capture performance evidence | Store baseline and optimized plans/metrics. | Should | Claims are supported by measurements. | Tuning report
REQ-072 | 10 - Packaging & Portfolio | Portfolio | Prepare honest resume wording | State that this is a self-directed portfolio project and quantify only measured results from your environment. | Must | Resume wording has no unverified client or production claims. | Resume bullets
REQ-073 | 10 - Packaging & Portfolio | Interview | Prepare design defense | Explain trade-offs, failure recovery, data quality, performance, and alternative approaches. | Must | A concise walkthrough and deep-dive answers are prepared. | Interview notes

## Task Plan
Granular Task Plan and Effort Estimate
Task ID | Req ID | Phase | Category | Small Task | Implementation Notes | Priority | Planned Hours | Dependency | Deliverable / Evidence | Status | Completion % | Actual Hours | Comments
TSK-001 | REQ-001 | 1 - Warehouse Modeling | Business | Analyze and document - Confirm analytical scope | Define revenue, customer, product, location, order, shipment and calendar analysis required by stakeholders. | Must | 1 |  | Analyze and document: Confirm analytical scope | Not Started | 0%
TSK-002 | REQ-001 | 1 - Warehouse Modeling | Business | Design approach - Confirm analytical scope | Define revenue, customer, product, location, order, shipment and calendar analysis required by stakeholders. | Must | 0.5 | TSK-001 | Design approach: Confirm analytical scope | Not Started | 0%
TSK-003 | REQ-001 | 1 - Warehouse Modeling | Business | Implement SQL or artifact - Confirm analytical scope | Define revenue, customer, product, location, order, shipment and calendar analysis required by stakeholders. | Must | 1 | TSK-002 | Scope document | Not Started | 0%
TSK-004 | REQ-001 | 1 - Warehouse Modeling | Business | Create and execute tests - Confirm analytical scope | Define revenue, customer, product, location, order, shipment and calendar analysis required by stakeholders. | Must | 1 | TSK-003 | Create and execute tests: Confirm analytical scope | Not Started | 0%
TSK-005 | REQ-001 | 1 - Warehouse Modeling | Business | Record evidence and decisions - Confirm analytical scope | Define revenue, customer, product, location, order, shipment and calendar analysis required by stakeholders. | Must | 0.5 | TSK-004 | Record evidence and decisions: Confirm analytical scope | Not Started | 0%
TSK-006 | REQ-002 | 1 - Warehouse Modeling | Modeling | Analyze and document - Declare FactOrders grain | Define one row per order line, represented by OrderID plus OrderLineNumber. ProductID alone is insufficient if the same product can appear more than once in an order. | Must | 0.5 | TSK-005 | Analyze and document: Declare FactOrders grain | Not Started | 0%
TSK-007 | REQ-002 | 1 - Warehouse Modeling | Modeling | Design approach - Declare FactOrders grain | Define one row per order line, represented by OrderID plus OrderLineNumber. ProductID alone is insufficient if the same product can appear more than once in an order. | Must | 0.5 | TSK-006 | Design approach: Declare FactOrders grain | Not Started | 0%
TSK-008 | REQ-002 | 1 - Warehouse Modeling | Modeling | Implement SQL or artifact - Declare FactOrders grain | Define one row per order line, represented by OrderID plus OrderLineNumber. ProductID alone is insufficient if the same product can appear more than once in an order. | Must | 1 | TSK-007 | Grain statement | Not Started | 0%
TSK-009 | REQ-002 | 1 - Warehouse Modeling | Modeling | Create and execute tests - Declare FactOrders grain | Define one row per order line, represented by OrderID plus OrderLineNumber. ProductID alone is insufficient if the same product can appear more than once in an order. | Must | 1 | TSK-008 | Create and execute tests: Declare FactOrders grain | Not Started | 0%
TSK-010 | REQ-002 | 1 - Warehouse Modeling | Modeling | Record evidence and decisions - Declare FactOrders grain | Define one row per order line, represented by OrderID plus OrderLineNumber. ProductID alone is insufficient if the same product can appear more than once in an order. | Must | 0.5 | TSK-009 | Record evidence and decisions: Declare FactOrders grain | Not Started | 0%
TSK-011 | REQ-003 | 1 - Warehouse Modeling | Modeling | Analyze and document - Declare FactShipment grain | Define one row per shipment event or shipment record. Document treatment of split shipments and multiple delivery attempts. | Must | 1 | TSK-010 | Analyze and document: Declare FactShipment grain | Not Started | 0%
TSK-012 | REQ-003 | 1 - Warehouse Modeling | Modeling | Design approach - Declare FactShipment grain | Define one row per shipment event or shipment record. Document treatment of split shipments and multiple delivery attempts. | Must | 1 | TSK-011 | Design approach: Declare FactShipment grain | Not Started | 0%
TSK-013 | REQ-003 | 1 - Warehouse Modeling | Modeling | Implement SQL or artifact - Declare FactShipment grain | Define one row per shipment event or shipment record. Document treatment of split shipments and multiple delivery attempts. | Must | 2 | TSK-012 | Shipment grain statement | Not Started | 0%
TSK-014 | REQ-003 | 1 - Warehouse Modeling | Modeling | Create and execute tests - Declare FactShipment grain | Define one row per shipment event or shipment record. Document treatment of split shipments and multiple delivery attempts. | Must | 1 | TSK-013 | Create and execute tests: Declare FactShipment grain | Not Started | 0%
TSK-015 | REQ-003 | 1 - Warehouse Modeling | Modeling | Record evidence and decisions - Declare FactShipment grain | Define one row per shipment event or shipment record. Document treatment of split shipments and multiple delivery attempts. | Must | 0.5 | TSK-014 | Record evidence and decisions: Declare FactShipment grain | Not Started | 0%
TSK-016 | REQ-004 | 1 - Warehouse Modeling | Modeling | Analyze and document - Design star schema | Create FactOrders, FactShipment, DimCustomer, DimProduct, DimDate and DimLocation relationships. | Must | 1 | TSK-015 | Analyze and document: Design star schema | Not Started | 0%
TSK-017 | REQ-004 | 1 - Warehouse Modeling | Modeling | Design approach - Design star schema | Create FactOrders, FactShipment, DimCustomer, DimProduct, DimDate and DimLocation relationships. | Must | 0.5 | TSK-016 | Design approach: Design star schema | Not Started | 0%
TSK-018 | REQ-004 | 1 - Warehouse Modeling | Modeling | Implement SQL or artifact - Design star schema | Create FactOrders, FactShipment, DimCustomer, DimProduct, DimDate and DimLocation relationships. | Must | 1 | TSK-017 | ERD/star schema | Not Started | 0%
TSK-019 | REQ-004 | 1 - Warehouse Modeling | Modeling | Create and execute tests - Design star schema | Create FactOrders, FactShipment, DimCustomer, DimProduct, DimDate and DimLocation relationships. | Must | 1 | TSK-018 | Create and execute tests: Design star schema | Not Started | 0%
TSK-020 | REQ-004 | 1 - Warehouse Modeling | Modeling | Record evidence and decisions - Design star schema | Create FactOrders, FactShipment, DimCustomer, DimProduct, DimDate and DimLocation relationships. | Must | 0.5 | TSK-019 | Record evidence and decisions: Design star schema | Not Started | 0%
TSK-021 | REQ-005 | 1 - Warehouse Modeling | Keys | Analyze and document - Use surrogate keys | Use integer/bigint surrogate keys for warehouse dimensions while retaining source business keys. | Must | 0.5 | TSK-020 | Analyze and document: Use surrogate keys | Not Started | 0%
TSK-022 | REQ-005 | 1 - Warehouse Modeling | Keys | Design approach - Use surrogate keys | Use integer/bigint surrogate keys for warehouse dimensions while retaining source business keys. | Must | 1 | TSK-021 | Design approach: Use surrogate keys | Not Started | 0%
TSK-023 | REQ-005 | 1 - Warehouse Modeling | Keys | Implement SQL or artifact - Use surrogate keys | Use integer/bigint surrogate keys for warehouse dimensions while retaining source business keys. | Must | 2 | TSK-022 | DDL design | Not Started | 0%
TSK-024 | REQ-005 | 1 - Warehouse Modeling | Keys | Create and execute tests - Use surrogate keys | Use integer/bigint surrogate keys for warehouse dimensions while retaining source business keys. | Must | 1 | TSK-023 | Create and execute tests: Use surrogate keys | Not Started | 0%
TSK-025 | REQ-005 | 1 - Warehouse Modeling | Keys | Record evidence and decisions - Use surrogate keys | Use integer/bigint surrogate keys for warehouse dimensions while retaining source business keys. | Must | 0.5 | TSK-024 | Record evidence and decisions: Use surrogate keys | Not Started | 0%
TSK-026 | REQ-006 | 1 - Warehouse Modeling | Keys | Analyze and document - Create unknown members | Insert key 0 or -1 rows for unknown customer, product, date or location where applicable. | Must | 0.5 | TSK-025 | Analyze and document: Create unknown members | Not Started | 0%
TSK-027 | REQ-006 | 1 - Warehouse Modeling | Keys | Design approach - Create unknown members | Insert key 0 or -1 rows for unknown customer, product, date or location where applicable. | Must | 1 | TSK-026 | Design approach: Create unknown members | Not Started | 0%
TSK-028 | REQ-006 | 1 - Warehouse Modeling | Keys | Implement SQL or artifact - Create unknown members | Insert key 0 or -1 rows for unknown customer, product, date or location where applicable. | Must | 2 | TSK-027 | Unknown-member script | Not Started | 0%
TSK-029 | REQ-006 | 1 - Warehouse Modeling | Keys | Create and execute tests - Create unknown members | Insert key 0 or -1 rows for unknown customer, product, date or location where applicable. | Must | 1 | TSK-028 | Create and execute tests: Create unknown members | Not Started | 0%
TSK-030 | REQ-006 | 1 - Warehouse Modeling | Keys | Record evidence and decisions - Create unknown members | Insert key 0 or -1 rows for unknown customer, product, date or location where applicable. | Must | 0.5 | TSK-029 | Record evidence and decisions: Create unknown members | Not Started | 0%
TSK-031 | REQ-007 | 1 - Warehouse Modeling | Data | Analyze and document - Define additive measures | Store Quantity, GrossAmount, DiscountAmount, NetAmount, CostAmount and FreightAllocatedAmount at the declared grain where available. | Should | 1 | TSK-030 | Analyze and document: Define additive measures | Not Started | 0%
TSK-032 | REQ-007 | 1 - Warehouse Modeling | Data | Design approach - Define additive measures | Store Quantity, GrossAmount, DiscountAmount, NetAmount, CostAmount and FreightAllocatedAmount at the declared grain where available. | Should | 0.5 | TSK-031 | Design approach: Define additive measures | Not Started | 0%
TSK-033 | REQ-007 | 1 - Warehouse Modeling | Data | Implement SQL or artifact - Define additive measures | Store Quantity, GrossAmount, DiscountAmount, NetAmount, CostAmount and FreightAllocatedAmount at the declared grain where available. | Should | 1.5 | TSK-032 | Measure catalogue | Not Started | 0%
TSK-034 | REQ-007 | 1 - Warehouse Modeling | Data | Create and execute tests - Define additive measures | Store Quantity, GrossAmount, DiscountAmount, NetAmount, CostAmount and FreightAllocatedAmount at the declared grain where available. | Should | 1 | TSK-033 | Create and execute tests: Define additive measures | Not Started | 0%
TSK-035 | REQ-007 | 1 - Warehouse Modeling | Data | Record evidence and decisions - Define additive measures | Store Quantity, GrossAmount, DiscountAmount, NetAmount, CostAmount and FreightAllocatedAmount at the declared grain where available. | Should | 0.5 | TSK-034 | Record evidence and decisions: Define additive measures | Not Started | 0%
TSK-036 | REQ-008 | 1 - Warehouse Modeling | Audit | Analyze and document - Add audit columns | Include BatchID, SourceSystem, SourceModifiedDate, InsertedDateTime and UpdatedDateTime where applicable. | Must | 0.5 | TSK-035 | Analyze and document: Add audit columns | Not Started | 0%
TSK-037 | REQ-008 | 1 - Warehouse Modeling | Audit | Design approach - Add audit columns | Include BatchID, SourceSystem, SourceModifiedDate, InsertedDateTime and UpdatedDateTime where applicable. | Must | 0.5 | TSK-036 | Design approach: Add audit columns | Not Started | 0%
TSK-038 | REQ-008 | 1 - Warehouse Modeling | Audit | Implement SQL or artifact - Add audit columns | Include BatchID, SourceSystem, SourceModifiedDate, InsertedDateTime and UpdatedDateTime where applicable. | Must | 2 | TSK-037 | Audit-column standard | Not Started | 0%
TSK-039 | REQ-008 | 1 - Warehouse Modeling | Audit | Create and execute tests - Add audit columns | Include BatchID, SourceSystem, SourceModifiedDate, InsertedDateTime and UpdatedDateTime where applicable. | Must | 1 | TSK-038 | Create and execute tests: Add audit columns | Not Started | 0%
TSK-040 | REQ-008 | 1 - Warehouse Modeling | Audit | Record evidence and decisions - Add audit columns | Include BatchID, SourceSystem, SourceModifiedDate, InsertedDateTime and UpdatedDateTime where applicable. | Must | 0.5 | TSK-039 | Record evidence and decisions: Add audit columns | Not Started | 0%
TSK-041 | REQ-009 | 1 - Warehouse Modeling | Modeling | Analyze and document - Role-playing date dimensions | Represent OrderDate, ShipmentDate and DeliveryDate through separate foreign keys to DimDate. | Must | 1 | TSK-040 | Analyze and document: Role-playing date dimensions | Not Started | 0%
TSK-042 | REQ-009 | 1 - Warehouse Modeling | Modeling | Design approach - Role-playing date dimensions | Represent OrderDate, ShipmentDate and DeliveryDate through separate foreign keys to DimDate. | Must | 0.5 | TSK-041 | Design approach: Role-playing date dimensions | Not Started | 0%
TSK-043 | REQ-009 | 1 - Warehouse Modeling | Modeling | Implement SQL or artifact - Role-playing date dimensions | Represent OrderDate, ShipmentDate and DeliveryDate through separate foreign keys to DimDate. | Must | 1 | TSK-042 | Date-key design | Not Started | 0%
TSK-044 | REQ-009 | 1 - Warehouse Modeling | Modeling | Create and execute tests - Role-playing date dimensions | Represent OrderDate, ShipmentDate and DeliveryDate through separate foreign keys to DimDate. | Must | 1 | TSK-043 | Create and execute tests: Role-playing date dimensions | Not Started | 0%
TSK-045 | REQ-009 | 1 - Warehouse Modeling | Modeling | Record evidence and decisions - Role-playing date dimensions | Represent OrderDate, ShipmentDate and DeliveryDate through separate foreign keys to DimDate. | Must | 0.5 | TSK-044 | Record evidence and decisions: Role-playing date dimensions | Not Started | 0%
TSK-046 | REQ-010 | 1 - Warehouse Modeling | Data Quality | Analyze and document - Enforce key integrity | Define PK, unique business-key constraints where practical, and FK strategy. | Should | 0.5 | TSK-045 | Analyze and document: Enforce key integrity | Not Started | 0%
TSK-047 | REQ-010 | 1 - Warehouse Modeling | Data Quality | Design approach - Enforce key integrity | Define PK, unique business-key constraints where practical, and FK strategy. | Should | 1 | TSK-046 | Design approach: Enforce key integrity | Not Started | 0%
TSK-048 | REQ-010 | 1 - Warehouse Modeling | Data Quality | Implement SQL or artifact - Enforce key integrity | Define PK, unique business-key constraints where practical, and FK strategy. | Should | 1 | TSK-047 | Constraint script | Not Started | 0%
TSK-049 | REQ-010 | 1 - Warehouse Modeling | Data Quality | Create and execute tests - Enforce key integrity | Define PK, unique business-key constraints where practical, and FK strategy. | Should | 1 | TSK-048 | Create and execute tests: Enforce key integrity | Not Started | 0%
TSK-050 | REQ-010 | 1 - Warehouse Modeling | Data Quality | Record evidence and decisions - Enforce key integrity | Define PK, unique business-key constraints where practical, and FK strategy. | Should | 0.5 | TSK-049 | Record evidence and decisions: Enforce key integrity | Not Started | 0%
TSK-051 | REQ-011 | 2 - SCD Type 2 | History | Analyze and document - Track customer changes | Track City, Country and CustomerType changes while preserving prior values. | Must | 1 | TSK-050 | Analyze and document: Track customer changes | Not Started | 0%
TSK-052 | REQ-011 | 2 - SCD Type 2 | History | Design approach - Track customer changes | Track City, Country and CustomerType changes while preserving prior values. | Must | 1 | TSK-051 | Design approach: Track customer changes | Not Started | 0%
TSK-053 | REQ-011 | 2 - SCD Type 2 | History | Implement SQL or artifact - Track customer changes | Track City, Country and CustomerType changes while preserving prior values. | Must | 1 | TSK-052 | SCD procedure | Not Started | 0%
TSK-054 | REQ-011 | 2 - SCD Type 2 | History | Create and execute tests - Track customer changes | Track City, Country and CustomerType changes while preserving prior values. | Must | 1 | TSK-053 | Create and execute tests: Track customer changes | Not Started | 0%
TSK-055 | REQ-011 | 2 - SCD Type 2 | History | Record evidence and decisions - Track customer changes | Track City, Country and CustomerType changes while preserving prior values. | Must | 0.5 | TSK-054 | Record evidence and decisions: Track customer changes | Not Started | 0%
TSK-056 | REQ-012 | 2 - SCD Type 2 | History | Analyze and document - Ignore non-changing records | Do not create a new dimension version when tracked values are unchanged. | Must | 1 | TSK-055 | Analyze and document: Ignore non-changing records | Not Started | 0%
TSK-057 | REQ-012 | 2 - SCD Type 2 | History | Design approach - Ignore non-changing records | Do not create a new dimension version when tracked values are unchanged. | Must | 0.5 | TSK-056 | Design approach: Ignore non-changing records | Not Started | 0%
TSK-058 | REQ-012 | 2 - SCD Type 2 | History | Implement SQL or artifact - Ignore non-changing records | Do not create a new dimension version when tracked values are unchanged. | Must | 1.5 | TSK-057 | Idempotency evidence | Not Started | 0%
TSK-059 | REQ-012 | 2 - SCD Type 2 | History | Create and execute tests - Ignore non-changing records | Do not create a new dimension version when tracked values are unchanged. | Must | 1 | TSK-058 | Create and execute tests: Ignore non-changing records | Not Started | 0%
TSK-060 | REQ-012 | 2 - SCD Type 2 | History | Record evidence and decisions - Ignore non-changing records | Do not create a new dimension version when tracked values are unchanged. | Must | 0.5 | TSK-059 | Record evidence and decisions: Ignore non-changing records | Not Started | 0%
TSK-061 | REQ-013 | 2 - SCD Type 2 | History | Analyze and document - Handle new customers | Insert first version with EffectiveFrom, open-ended EffectiveTo and IsCurrent=1. | Must | 1 | TSK-060 | Analyze and document: Handle new customers | Not Started | 0%
TSK-062 | REQ-013 | 2 - SCD Type 2 | History | Design approach - Handle new customers | Insert first version with EffectiveFrom, open-ended EffectiveTo and IsCurrent=1. | Must | 1 | TSK-061 | Design approach: Handle new customers | Not Started | 0%
TSK-063 | REQ-013 | 2 - SCD Type 2 | History | Implement SQL or artifact - Handle new customers | Insert first version with EffectiveFrom, open-ended EffectiveTo and IsCurrent=1. | Must | 2 | TSK-062 | Insert logic | Not Started | 0%
TSK-064 | REQ-013 | 2 - SCD Type 2 | History | Create and execute tests - Handle new customers | Insert first version with EffectiveFrom, open-ended EffectiveTo and IsCurrent=1. | Must | 1 | TSK-063 | Create and execute tests: Handle new customers | Not Started | 0%
TSK-065 | REQ-013 | 2 - SCD Type 2 | History | Record evidence and decisions - Handle new customers | Insert first version with EffectiveFrom, open-ended EffectiveTo and IsCurrent=1. | Must | 0.5 | TSK-064 | Record evidence and decisions: Handle new customers | Not Started | 0%
TSK-066 | REQ-014 | 2 - SCD Type 2 | History | Analyze and document - Close prior version | Expire old row immediately before the new version starts using the selected timestamp convention. | Must | 0.5 | TSK-065 | Analyze and document: Close prior version | Not Started | 0%
TSK-067 | REQ-014 | 2 - SCD Type 2 | History | Design approach - Close prior version | Expire old row immediately before the new version starts using the selected timestamp convention. | Must | 1 | TSK-066 | Design approach: Close prior version | Not Started | 0%
TSK-068 | REQ-014 | 2 - SCD Type 2 | History | Implement SQL or artifact - Close prior version | Expire old row immediately before the new version starts using the selected timestamp convention. | Must | 1 | TSK-067 | Expiry logic | Not Started | 0%
TSK-069 | REQ-014 | 2 - SCD Type 2 | History | Create and execute tests - Close prior version | Expire old row immediately before the new version starts using the selected timestamp convention. | Must | 1 | TSK-068 | Create and execute tests: Close prior version | Not Started | 0%
TSK-070 | REQ-014 | 2 - SCD Type 2 | History | Record evidence and decisions - Close prior version | Expire old row immediately before the new version starts using the selected timestamp convention. | Must | 0.5 | TSK-069 | Record evidence and decisions: Close prior version | Not Started | 0%
TSK-071 | REQ-015 | 2 - SCD Type 2 | History | Analyze and document - Maintain current-row uniqueness | Ensure no CustomerID has more than one IsCurrent=1 row. | Must | 0.5 | TSK-070 | Analyze and document: Maintain current-row uniqueness | Not Started | 0%
TSK-072 | REQ-015 | 2 - SCD Type 2 | History | Design approach - Maintain current-row uniqueness | Ensure no CustomerID has more than one IsCurrent=1 row. | Must | 1 | TSK-071 | Design approach: Maintain current-row uniqueness | Not Started | 0%
TSK-073 | REQ-015 | 2 - SCD Type 2 | History | Implement SQL or artifact - Maintain current-row uniqueness | Ensure no CustomerID has more than one IsCurrent=1 row. | Must | 1 | TSK-072 | Uniqueness test | Not Started | 0%
TSK-074 | REQ-015 | 2 - SCD Type 2 | History | Create and execute tests - Maintain current-row uniqueness | Ensure no CustomerID has more than one IsCurrent=1 row. | Must | 1 | TSK-073 | Create and execute tests: Maintain current-row uniqueness | Not Started | 0%
TSK-075 | REQ-015 | 2 - SCD Type 2 | History | Record evidence and decisions - Maintain current-row uniqueness | Ensure no CustomerID has more than one IsCurrent=1 row. | Must | 0.5 | TSK-074 | Record evidence and decisions: Maintain current-row uniqueness | Not Started | 0%
TSK-076 | REQ-016 | 2 - SCD Type 2 | History | Analyze and document - Null-safe comparison | Treat null-to-value, value-to-null and value-to-different-value as changes. | Must | 1 | TSK-075 | Analyze and document: Null-safe comparison | Not Started | 0%
TSK-077 | REQ-016 | 2 - SCD Type 2 | History | Design approach - Null-safe comparison | Treat null-to-value, value-to-null and value-to-different-value as changes. | Must | 1 | TSK-076 | Design approach: Null-safe comparison | Not Started | 0%
TSK-078 | REQ-016 | 2 - SCD Type 2 | History | Implement SQL or artifact - Null-safe comparison | Treat null-to-value, value-to-null and value-to-different-value as changes. | Must | 1.5 | TSK-077 | Comparison logic | Not Started | 0%
TSK-079 | REQ-016 | 2 - SCD Type 2 | History | Create and execute tests - Null-safe comparison | Treat null-to-value, value-to-null and value-to-different-value as changes. | Must | 1 | TSK-078 | Create and execute tests: Null-safe comparison | Not Started | 0%
TSK-080 | REQ-016 | 2 - SCD Type 2 | History | Record evidence and decisions - Null-safe comparison | Treat null-to-value, value-to-null and value-to-different-value as changes. | Must | 0.5 | TSK-079 | Record evidence and decisions: Null-safe comparison | Not Started | 0%
TSK-081 | REQ-017 | 2 - SCD Type 2 | Late Data | Analyze and document - Define late-arriving customer handling | Document what happens when a fact arrives before its customer dimension record. | Should | 0.5 | TSK-080 | Analyze and document: Define late-arriving customer handling | Not Started | 0%
TSK-082 | REQ-017 | 2 - SCD Type 2 | Late Data | Design approach - Define late-arriving customer handling | Document what happens when a fact arrives before its customer dimension record. | Should | 1 | TSK-081 | Design approach: Define late-arriving customer handling | Not Started | 0%
TSK-083 | REQ-017 | 2 - SCD Type 2 | Late Data | Implement SQL or artifact - Define late-arriving customer handling | Document what happens when a fact arrives before its customer dimension record. | Should | 1.5 | TSK-082 | Late-arriving runbook | Not Started | 0%
TSK-084 | REQ-017 | 2 - SCD Type 2 | Late Data | Create and execute tests - Define late-arriving customer handling | Document what happens when a fact arrives before its customer dimension record. | Should | 1 | TSK-083 | Create and execute tests: Define late-arriving customer handling | Not Started | 0%
TSK-085 | REQ-017 | 2 - SCD Type 2 | Late Data | Record evidence and decisions - Define late-arriving customer handling | Document what happens when a fact arrives before its customer dimension record. | Should | 0.5 | TSK-084 | Record evidence and decisions: Define late-arriving customer handling | Not Started | 0%
TSK-086 | REQ-018 | 2 - SCD Type 2 | Audit | Analyze and document - Capture change metadata | Store source modified timestamp and load batch identifier for every version. | Must | 1 | TSK-085 | Analyze and document: Capture change metadata | Not Started | 0%
TSK-087 | REQ-018 | 2 - SCD Type 2 | Audit | Design approach - Capture change metadata | Store source modified timestamp and load batch identifier for every version. | Must | 1 | TSK-086 | Design approach: Capture change metadata | Not Started | 0%
TSK-088 | REQ-018 | 2 - SCD Type 2 | Audit | Implement SQL or artifact - Capture change metadata | Store source modified timestamp and load batch identifier for every version. | Must | 2 | TSK-087 | Audit query | Not Started | 0%
TSK-089 | REQ-018 | 2 - SCD Type 2 | Audit | Create and execute tests - Capture change metadata | Store source modified timestamp and load batch identifier for every version. | Must | 1 | TSK-088 | Create and execute tests: Capture change metadata | Not Started | 0%
TSK-090 | REQ-018 | 2 - SCD Type 2 | Audit | Record evidence and decisions - Capture change metadata | Store source modified timestamp and load batch identifier for every version. | Must | 0.5 | TSK-089 | Record evidence and decisions: Capture change metadata | Not Started | 0%
TSK-091 | REQ-019 | 3 - Revenue Analytics | Metric | Analyze and document - Define revenue | Document whether revenue means gross, net, invoiced, recognized, local-currency or reporting-currency revenue. | Must | 1 | TSK-090 | Analyze and document: Define revenue | Not Started | 0%
TSK-092 | REQ-019 | 3 - Revenue Analytics | Metric | Design approach - Define revenue | Document whether revenue means gross, net, invoiced, recognized, local-currency or reporting-currency revenue. | Must | 1 | TSK-091 | Design approach: Define revenue | Not Started | 0%
TSK-093 | REQ-019 | 3 - Revenue Analytics | Metric | Implement SQL or artifact - Define revenue | Document whether revenue means gross, net, invoiced, recognized, local-currency or reporting-currency revenue. | Must | 1 | TSK-092 | Metric definition | Not Started | 0%
TSK-094 | REQ-019 | 3 - Revenue Analytics | Metric | Create and execute tests - Define revenue | Document whether revenue means gross, net, invoiced, recognized, local-currency or reporting-currency revenue. | Must | 1 | TSK-093 | Create and execute tests: Define revenue | Not Started | 0%
TSK-095 | REQ-019 | 3 - Revenue Analytics | Metric | Record evidence and decisions - Define revenue | Document whether revenue means gross, net, invoiced, recognized, local-currency or reporting-currency revenue. | Must | 0.5 | TSK-094 | Record evidence and decisions: Define revenue | Not Started | 0%
TSK-096 | REQ-020 | 3 - Revenue Analytics | Analytics | Analyze and document - Monthly customer revenue | Aggregate revenue by customer and calendar month. | Must | 0.5 | TSK-095 | Analyze and document: Monthly customer revenue | Not Started | 0%
TSK-097 | REQ-020 | 3 - Revenue Analytics | Analytics | Design approach - Monthly customer revenue | Aggregate revenue by customer and calendar month. | Must | 0.5 | TSK-096 | Design approach: Monthly customer revenue | Not Started | 0%
TSK-098 | REQ-020 | 3 - Revenue Analytics | Analytics | Implement SQL or artifact - Monthly customer revenue | Aggregate revenue by customer and calendar month. | Must | 1.5 | TSK-097 | Revenue view | Not Started | 0%
TSK-099 | REQ-020 | 3 - Revenue Analytics | Analytics | Create and execute tests - Monthly customer revenue | Aggregate revenue by customer and calendar month. | Must | 1 | TSK-098 | Create and execute tests: Monthly customer revenue | Not Started | 0%
TSK-100 | REQ-020 | 3 - Revenue Analytics | Analytics | Record evidence and decisions - Monthly customer revenue | Aggregate revenue by customer and calendar month. | Must | 0.5 | TSK-099 | Record evidence and decisions: Monthly customer revenue | Not Started | 0%
TSK-101 | REQ-021 | 3 - Revenue Analytics | Analytics | Analyze and document - Previous month comparison | Use LAG to retrieve prior calendar-month revenue for each customer. | Must | 1 | TSK-100 | Analyze and document: Previous month comparison | Not Started | 0%
TSK-102 | REQ-021 | 3 - Revenue Analytics | Analytics | Design approach - Previous month comparison | Use LAG to retrieve prior calendar-month revenue for each customer. | Must | 1 | TSK-101 | Design approach: Previous month comparison | Not Started | 0%
TSK-103 | REQ-021 | 3 - Revenue Analytics | Analytics | Implement SQL or artifact - Previous month comparison | Use LAG to retrieve prior calendar-month revenue for each customer. | Must | 2 | TSK-102 | Growth query | Not Started | 0%
TSK-104 | REQ-021 | 3 - Revenue Analytics | Analytics | Create and execute tests - Previous month comparison | Use LAG to retrieve prior calendar-month revenue for each customer. | Must | 1 | TSK-103 | Create and execute tests: Previous month comparison | Not Started | 0%
TSK-105 | REQ-021 | 3 - Revenue Analytics | Analytics | Record evidence and decisions - Previous month comparison | Use LAG to retrieve prior calendar-month revenue for each customer. | Must | 0.5 | TSK-104 | Record evidence and decisions: Previous month comparison | Not Started | 0%
TSK-106 | REQ-022 | 3 - Revenue Analytics | Analytics | Analyze and document - Growth percentage | Calculate growth with divide-by-zero and absent-prior-month handling. | Must | 1 | TSK-105 | Analyze and document: Growth percentage | Not Started | 0%
TSK-107 | REQ-022 | 3 - Revenue Analytics | Analytics | Design approach - Growth percentage | Calculate growth with divide-by-zero and absent-prior-month handling. | Must | 0.5 | TSK-106 | Design approach: Growth percentage | Not Started | 0%
TSK-108 | REQ-022 | 3 - Revenue Analytics | Analytics | Implement SQL or artifact - Growth percentage | Calculate growth with divide-by-zero and absent-prior-month handling. | Must | 1 | TSK-107 | Growth calculation | Not Started | 0%
TSK-109 | REQ-022 | 3 - Revenue Analytics | Analytics | Create and execute tests - Growth percentage | Calculate growth with divide-by-zero and absent-prior-month handling. | Must | 1 | TSK-108 | Create and execute tests: Growth percentage | Not Started | 0%
TSK-110 | REQ-022 | 3 - Revenue Analytics | Analytics | Record evidence and decisions - Growth percentage | Calculate growth with divide-by-zero and absent-prior-month handling. | Must | 0.5 | TSK-109 | Record evidence and decisions: Growth percentage | Not Started | 0%
TSK-111 | REQ-023 | 3 - Revenue Analytics | Analytics | Analyze and document - Zero-activity month handling | Choose whether missing months are absent or generated with a date scaffold. | Should | 1 | TSK-110 | Analyze and document: Zero-activity month handling | Not Started | 0%
TSK-112 | REQ-023 | 3 - Revenue Analytics | Analytics | Design approach - Zero-activity month handling | Choose whether missing months are absent or generated with a date scaffold. | Should | 1 | TSK-111 | Design approach: Zero-activity month handling | Not Started | 0%
TSK-113 | REQ-023 | 3 - Revenue Analytics | Analytics | Implement SQL or artifact - Zero-activity month handling | Choose whether missing months are absent or generated with a date scaffold. | Should | 1 | TSK-112 | Calendar scaffold logic | Not Started | 0%
TSK-114 | REQ-023 | 3 - Revenue Analytics | Analytics | Create and execute tests - Zero-activity month handling | Choose whether missing months are absent or generated with a date scaffold. | Should | 1 | TSK-113 | Create and execute tests: Zero-activity month handling | Not Started | 0%
TSK-115 | REQ-023 | 3 - Revenue Analytics | Analytics | Record evidence and decisions - Zero-activity month handling | Choose whether missing months are absent or generated with a date scaffold. | Should | 0.5 | TSK-114 | Record evidence and decisions: Zero-activity month handling | Not Started | 0%
TSK-116 | REQ-024 | 3 - Revenue Analytics | Analytics | Analyze and document - Revenue trend | Produce month, quarter and year trend outputs. | Should | 1 | TSK-115 | Analyze and document: Revenue trend | Not Started | 0%
TSK-117 | REQ-024 | 3 - Revenue Analytics | Analytics | Design approach - Revenue trend | Produce month, quarter and year trend outputs. | Should | 1 | TSK-116 | Design approach: Revenue trend | Not Started | 0%
TSK-118 | REQ-024 | 3 - Revenue Analytics | Analytics | Implement SQL or artifact - Revenue trend | Produce month, quarter and year trend outputs. | Should | 1 | TSK-117 | Trend view | Not Started | 0%
TSK-119 | REQ-024 | 3 - Revenue Analytics | Analytics | Create and execute tests - Revenue trend | Produce month, quarter and year trend outputs. | Should | 1 | TSK-118 | Create and execute tests: Revenue trend | Not Started | 0%
TSK-120 | REQ-024 | 3 - Revenue Analytics | Analytics | Record evidence and decisions - Revenue trend | Produce month, quarter and year trend outputs. | Should | 0.5 | TSK-119 | Record evidence and decisions: Revenue trend | Not Started | 0%
TSK-121 | REQ-025 | 3 - Revenue Analytics | Currency | Analyze and document - Reporting currency rule | If multiple currencies exist, define exchange-rate date and conversion logic rather than summing currencies directly. | Must | 1 | TSK-120 | Analyze and document: Reporting currency rule | Not Started | 0%
TSK-122 | REQ-025 | 3 - Revenue Analytics | Currency | Design approach - Reporting currency rule | If multiple currencies exist, define exchange-rate date and conversion logic rather than summing currencies directly. | Must | 1 | TSK-121 | Design approach: Reporting currency rule | Not Started | 0%
TSK-123 | REQ-025 | 3 - Revenue Analytics | Currency | Implement SQL or artifact - Reporting currency rule | If multiple currencies exist, define exchange-rate date and conversion logic rather than summing currencies directly. | Must | 1.5 | TSK-122 | Currency design note | Not Started | 0%
TSK-124 | REQ-025 | 3 - Revenue Analytics | Currency | Create and execute tests - Reporting currency rule | If multiple currencies exist, define exchange-rate date and conversion logic rather than summing currencies directly. | Must | 1 | TSK-123 | Create and execute tests: Reporting currency rule | Not Started | 0%
TSK-125 | REQ-025 | 3 - Revenue Analytics | Currency | Record evidence and decisions - Reporting currency rule | If multiple currencies exist, define exchange-rate date and conversion logic rather than summing currencies directly. | Must | 0.5 | TSK-124 | Record evidence and decisions: Reporting currency rule | Not Started | 0%
TSK-126 | REQ-026 | 4 - Deduplication | Quality | Analyze and document - Identify duplicate order events | Profile duplicate frequency by OrderID and OrderLineNumber. | Must | 0.5 | TSK-125 | Analyze and document: Identify duplicate order events | Not Started | 0%
TSK-127 | REQ-026 | 4 - Deduplication | Quality | Design approach - Identify duplicate order events | Profile duplicate frequency by OrderID and OrderLineNumber. | Must | 0.5 | TSK-126 | Design approach: Identify duplicate order events | Not Started | 0%
TSK-128 | REQ-026 | 4 - Deduplication | Quality | Implement SQL or artifact - Identify duplicate order events | Profile duplicate frequency by OrderID and OrderLineNumber. | Must | 2 | TSK-127 | Profiling query | Not Started | 0%
TSK-129 | REQ-026 | 4 - Deduplication | Quality | Create and execute tests - Identify duplicate order events | Profile duplicate frequency by OrderID and OrderLineNumber. | Must | 1 | TSK-128 | Create and execute tests: Identify duplicate order events | Not Started | 0%
TSK-130 | REQ-026 | 4 - Deduplication | Quality | Record evidence and decisions - Identify duplicate order events | Profile duplicate frequency by OrderID and OrderLineNumber. | Must | 0.5 | TSK-129 | Record evidence and decisions: Identify duplicate order events | Not Started | 0%
TSK-131 | REQ-027 | 4 - Deduplication | Quality | Analyze and document - Define survivor rule | Keep the record with greatest SourceModifiedDate, then IngestionDateTime, then deterministic tie-breaker. | Must | 1 | TSK-130 | Analyze and document: Define survivor rule | Not Started | 0%
TSK-132 | REQ-027 | 4 - Deduplication | Quality | Design approach - Define survivor rule | Keep the record with greatest SourceModifiedDate, then IngestionDateTime, then deterministic tie-breaker. | Must | 1 | TSK-131 | Design approach: Define survivor rule | Not Started | 0%
TSK-133 | REQ-027 | 4 - Deduplication | Quality | Implement SQL or artifact - Define survivor rule | Keep the record with greatest SourceModifiedDate, then IngestionDateTime, then deterministic tie-breaker. | Must | 2 | TSK-132 | Survivorship rule | Not Started | 0%
TSK-134 | REQ-027 | 4 - Deduplication | Quality | Create and execute tests - Define survivor rule | Keep the record with greatest SourceModifiedDate, then IngestionDateTime, then deterministic tie-breaker. | Must | 1 | TSK-133 | Create and execute tests: Define survivor rule | Not Started | 0%
TSK-135 | REQ-027 | 4 - Deduplication | Quality | Record evidence and decisions - Define survivor rule | Keep the record with greatest SourceModifiedDate, then IngestionDateTime, then deterministic tie-breaker. | Must | 0.5 | TSK-134 | Record evidence and decisions: Define survivor rule | Not Started | 0%
TSK-136 | REQ-028 | 4 - Deduplication | Quality | Analyze and document - Implement ROW_NUMBER | Use partitioned ROW_NUMBER to select the survivor. | Must | 1 | TSK-135 | Analyze and document: Implement ROW_NUMBER | Not Started | 0%
TSK-137 | REQ-028 | 4 - Deduplication | Quality | Design approach - Implement ROW_NUMBER | Use partitioned ROW_NUMBER to select the survivor. | Must | 1 | TSK-136 | Design approach: Implement ROW_NUMBER | Not Started | 0%
TSK-138 | REQ-028 | 4 - Deduplication | Quality | Implement SQL or artifact - Implement ROW_NUMBER | Use partitioned ROW_NUMBER to select the survivor. | Must | 1 | TSK-137 | Dedup view/procedure | Not Started | 0%
TSK-139 | REQ-028 | 4 - Deduplication | Quality | Create and execute tests - Implement ROW_NUMBER | Use partitioned ROW_NUMBER to select the survivor. | Must | 1 | TSK-138 | Create and execute tests: Implement ROW_NUMBER | Not Started | 0%
TSK-140 | REQ-028 | 4 - Deduplication | Quality | Record evidence and decisions - Implement ROW_NUMBER | Use partitioned ROW_NUMBER to select the survivor. | Must | 0.5 | TSK-139 | Record evidence and decisions: Implement ROW_NUMBER | Not Started | 0%
TSK-141 | REQ-029 | 4 - Deduplication | Quality | Analyze and document - Quarantine rejected rows | Persist discarded duplicates with rejection reason and batch details. | Should | 1 | TSK-140 | Analyze and document: Quarantine rejected rows | Not Started | 0%
TSK-142 | REQ-029 | 4 - Deduplication | Quality | Design approach - Quarantine rejected rows | Persist discarded duplicates with rejection reason and batch details. | Should | 0.5 | TSK-141 | Design approach: Quarantine rejected rows | Not Started | 0%
TSK-143 | REQ-029 | 4 - Deduplication | Quality | Implement SQL or artifact - Quarantine rejected rows | Persist discarded duplicates with rejection reason and batch details. | Should | 1 | TSK-142 | Reject table | Not Started | 0%
TSK-144 | REQ-029 | 4 - Deduplication | Quality | Create and execute tests - Quarantine rejected rows | Persist discarded duplicates with rejection reason and batch details. | Should | 1 | TSK-143 | Create and execute tests: Quarantine rejected rows | Not Started | 0%
TSK-145 | REQ-029 | 4 - Deduplication | Quality | Record evidence and decisions - Quarantine rejected rows | Persist discarded duplicates with rejection reason and batch details. | Should | 0.5 | TSK-144 | Record evidence and decisions: Quarantine rejected rows | Not Started | 0%
TSK-146 | REQ-030 | 4 - Deduplication | Quality | Analyze and document - Ensure idempotency | Rerunning the same batch must not create additional target rows. | Must | 1 | TSK-145 | Analyze and document: Ensure idempotency | Not Started | 0%
TSK-147 | REQ-030 | 4 - Deduplication | Quality | Design approach - Ensure idempotency | Rerunning the same batch must not create additional target rows. | Must | 0.5 | TSK-146 | Design approach: Ensure idempotency | Not Started | 0%
TSK-148 | REQ-030 | 4 - Deduplication | Quality | Implement SQL or artifact - Ensure idempotency | Rerunning the same batch must not create additional target rows. | Must | 2 | TSK-147 | Rerun evidence | Not Started | 0%
TSK-149 | REQ-030 | 4 - Deduplication | Quality | Create and execute tests - Ensure idempotency | Rerunning the same batch must not create additional target rows. | Must | 1 | TSK-148 | Create and execute tests: Ensure idempotency | Not Started | 0%
TSK-150 | REQ-030 | 4 - Deduplication | Quality | Record evidence and decisions - Ensure idempotency | Rerunning the same batch must not create additional target rows. | Must | 0.5 | TSK-149 | Record evidence and decisions: Ensure idempotency | Not Started | 0%
TSK-151 | REQ-031 | 4 - Deduplication | Quality | Analyze and document - Handle exact ties | Use a deterministic final tie-breaker when timestamps are equal. | Must | 0.5 | TSK-150 | Analyze and document: Handle exact ties | Not Started | 0%
TSK-152 | REQ-031 | 4 - Deduplication | Quality | Design approach - Handle exact ties | Use a deterministic final tie-breaker when timestamps are equal. | Must | 1 | TSK-151 | Design approach: Handle exact ties | Not Started | 0%
TSK-153 | REQ-031 | 4 - Deduplication | Quality | Implement SQL or artifact - Handle exact ties | Use a deterministic final tie-breaker when timestamps are equal. | Must | 1.5 | TSK-152 | Tie-break test | Not Started | 0%
TSK-154 | REQ-031 | 4 - Deduplication | Quality | Create and execute tests - Handle exact ties | Use a deterministic final tie-breaker when timestamps are equal. | Must | 1 | TSK-153 | Create and execute tests: Handle exact ties | Not Started | 0%
TSK-155 | REQ-031 | 4 - Deduplication | Quality | Record evidence and decisions - Handle exact ties | Use a deterministic final tie-breaker when timestamps are equal. | Must | 0.5 | TSK-154 | Record evidence and decisions: Handle exact ties | Not Started | 0%
TSK-156 | REQ-032 | 5 - Delivery Delay | Metric | Analyze and document - Define delivery duration | Calculate delivery days from ShipmentDate to DeliveryDate using an agreed calendar-day or business-day rule. | Must | 1 | TSK-155 | Analyze and document: Define delivery duration | Not Started | 0%
TSK-157 | REQ-032 | 5 - Delivery Delay | Metric | Design approach - Define delivery duration | Calculate delivery days from ShipmentDate to DeliveryDate using an agreed calendar-day or business-day rule. | Must | 1 | TSK-156 | Design approach: Define delivery duration | Not Started | 0%
TSK-158 | REQ-032 | 5 - Delivery Delay | Metric | Implement SQL or artifact - Define delivery duration | Calculate delivery days from ShipmentDate to DeliveryDate using an agreed calendar-day or business-day rule. | Must | 2 | TSK-157 | Delay definition | Not Started | 0%
TSK-159 | REQ-032 | 5 - Delivery Delay | Metric | Create and execute tests - Define delivery duration | Calculate delivery days from ShipmentDate to DeliveryDate using an agreed calendar-day or business-day rule. | Must | 1 | TSK-158 | Create and execute tests: Define delivery duration | Not Started | 0%
TSK-160 | REQ-032 | 5 - Delivery Delay | Metric | Record evidence and decisions - Define delivery duration | Calculate delivery days from ShipmentDate to DeliveryDate using an agreed calendar-day or business-day rule. | Must | 0.5 | TSK-159 | Record evidence and decisions: Define delivery duration | Not Started | 0%
TSK-161 | REQ-033 | 5 - Delivery Delay | Metric | Analyze and document - Identify late delivery | Flag delivery duration greater than 7 days as late. | Must | 1 | TSK-160 | Analyze and document: Identify late delivery | Not Started | 0%
TSK-162 | REQ-033 | 5 - Delivery Delay | Metric | Design approach - Identify late delivery | Flag delivery duration greater than 7 days as late. | Must | 0.5 | TSK-161 | Design approach: Identify late delivery | Not Started | 0%
TSK-163 | REQ-033 | 5 - Delivery Delay | Metric | Implement SQL or artifact - Identify late delivery | Flag delivery duration greater than 7 days as late. | Must | 2 | TSK-162 | Late flag | Not Started | 0%
TSK-164 | REQ-033 | 5 - Delivery Delay | Metric | Create and execute tests - Identify late delivery | Flag delivery duration greater than 7 days as late. | Must | 1 | TSK-163 | Create and execute tests: Identify late delivery | Not Started | 0%
TSK-165 | REQ-033 | 5 - Delivery Delay | Metric | Record evidence and decisions - Identify late delivery | Flag delivery duration greater than 7 days as late. | Must | 0.5 | TSK-164 | Record evidence and decisions: Identify late delivery | Not Started | 0%
TSK-166 | REQ-034 | 5 - Delivery Delay | Analytics | Analyze and document - Create non-overlapping buckets | Use 0-3, 4-7, 8-15 and 16+ days, avoiding overlap in the original 15+ wording. | Must | 1 | TSK-165 | Analyze and document: Create non-overlapping buckets | Not Started | 0%
TSK-167 | REQ-034 | 5 - Delivery Delay | Analytics | Design approach - Create non-overlapping buckets | Use 0-3, 4-7, 8-15 and 16+ days, avoiding overlap in the original 15+ wording. | Must | 1 | TSK-166 | Design approach: Create non-overlapping buckets | Not Started | 0%
TSK-168 | REQ-034 | 5 - Delivery Delay | Analytics | Implement SQL or artifact - Create non-overlapping buckets | Use 0-3, 4-7, 8-15 and 16+ days, avoiding overlap in the original 15+ wording. | Must | 1 | TSK-167 | Bucket expression | Not Started | 0%
TSK-169 | REQ-034 | 5 - Delivery Delay | Analytics | Create and execute tests - Create non-overlapping buckets | Use 0-3, 4-7, 8-15 and 16+ days, avoiding overlap in the original 15+ wording. | Must | 1 | TSK-168 | Create and execute tests: Create non-overlapping buckets | Not Started | 0%
TSK-170 | REQ-034 | 5 - Delivery Delay | Analytics | Record evidence and decisions - Create non-overlapping buckets | Use 0-3, 4-7, 8-15 and 16+ days, avoiding overlap in the original 15+ wording. | Must | 0.5 | TSK-169 | Record evidence and decisions: Create non-overlapping buckets | Not Started | 0%
TSK-171 | REQ-035 | 5 - Delivery Delay | Quality | Analyze and document - Handle undelivered shipments | Classify null DeliveryDate separately as In Transit or Undelivered. | Must | 0.5 | TSK-170 | Analyze and document: Handle undelivered shipments | Not Started | 0%
TSK-172 | REQ-035 | 5 - Delivery Delay | Quality | Design approach - Handle undelivered shipments | Classify null DeliveryDate separately as In Transit or Undelivered. | Must | 1 | TSK-171 | Design approach: Handle undelivered shipments | Not Started | 0%
TSK-173 | REQ-035 | 5 - Delivery Delay | Quality | Implement SQL or artifact - Handle undelivered shipments | Classify null DeliveryDate separately as In Transit or Undelivered. | Must | 1 | TSK-172 | Null-handling logic | Not Started | 0%
TSK-174 | REQ-035 | 5 - Delivery Delay | Quality | Create and execute tests - Handle undelivered shipments | Classify null DeliveryDate separately as In Transit or Undelivered. | Must | 1 | TSK-173 | Create and execute tests: Handle undelivered shipments | Not Started | 0%
TSK-175 | REQ-035 | 5 - Delivery Delay | Quality | Record evidence and decisions - Handle undelivered shipments | Classify null DeliveryDate separately as In Transit or Undelivered. | Must | 0.5 | TSK-174 | Record evidence and decisions: Handle undelivered shipments | Not Started | 0%
TSK-176 | REQ-036 | 5 - Delivery Delay | Quality | Analyze and document - Handle invalid chronology | Reject or flag DeliveryDate earlier than ShipmentDate. | Must | 1 | TSK-175 | Analyze and document: Handle invalid chronology | Not Started | 0%
TSK-177 | REQ-036 | 5 - Delivery Delay | Quality | Design approach - Handle invalid chronology | Reject or flag DeliveryDate earlier than ShipmentDate. | Must | 1 | TSK-176 | Design approach: Handle invalid chronology | Not Started | 0%
TSK-178 | REQ-036 | 5 - Delivery Delay | Quality | Implement SQL or artifact - Handle invalid chronology | Reject or flag DeliveryDate earlier than ShipmentDate. | Must | 1 | TSK-177 | DQ rule | Not Started | 0%
TSK-179 | REQ-036 | 5 - Delivery Delay | Quality | Create and execute tests - Handle invalid chronology | Reject or flag DeliveryDate earlier than ShipmentDate. | Must | 1 | TSK-178 | Create and execute tests: Handle invalid chronology | Not Started | 0%
TSK-180 | REQ-036 | 5 - Delivery Delay | Quality | Record evidence and decisions - Handle invalid chronology | Reject or flag DeliveryDate earlier than ShipmentDate. | Must | 0.5 | TSK-179 | Record evidence and decisions: Handle invalid chronology | Not Started | 0%
TSK-181 | REQ-037 | 5 - Delivery Delay | Analytics | Analyze and document - Delay KPI output | Report delayed shipment count, percentage, average days and bucket distribution. | Should | 1 | TSK-180 | Analyze and document: Delay KPI output | Not Started | 0%
TSK-182 | REQ-037 | 5 - Delivery Delay | Analytics | Design approach - Delay KPI output | Report delayed shipment count, percentage, average days and bucket distribution. | Should | 1 | TSK-181 | Design approach: Delay KPI output | Not Started | 0%
TSK-183 | REQ-037 | 5 - Delivery Delay | Analytics | Implement SQL or artifact - Delay KPI output | Report delayed shipment count, percentage, average days and bucket distribution. | Should | 2 | TSK-182 | Delay view | Not Started | 0%
TSK-184 | REQ-037 | 5 - Delivery Delay | Analytics | Create and execute tests - Delay KPI output | Report delayed shipment count, percentage, average days and bucket distribution. | Should | 1 | TSK-183 | Create and execute tests: Delay KPI output | Not Started | 0%
TSK-185 | REQ-037 | 5 - Delivery Delay | Analytics | Record evidence and decisions - Delay KPI output | Report delayed shipment count, percentage, average days and bucket distribution. | Should | 0.5 | TSK-184 | Record evidence and decisions: Delay KPI output | Not Started | 0%
TSK-186 | REQ-038 | 6 - Top Customers | Analytics | Analyze and document - Rank within country | Rank customers by revenue separately within each country. | Must | 0.5 | TSK-185 | Analyze and document: Rank within country | Not Started | 0%
TSK-187 | REQ-038 | 6 - Top Customers | Analytics | Design approach - Rank within country | Rank customers by revenue separately within each country. | Must | 0.5 | TSK-186 | Design approach: Rank within country | Not Started | 0%
TSK-188 | REQ-038 | 6 - Top Customers | Analytics | Implement SQL or artifact - Rank within country | Rank customers by revenue separately within each country. | Must | 1.5 | TSK-187 | Ranking query | Not Started | 0%
TSK-189 | REQ-038 | 6 - Top Customers | Analytics | Create and execute tests - Rank within country | Rank customers by revenue separately within each country. | Must | 1 | TSK-188 | Create and execute tests: Rank within country | Not Started | 0%
TSK-190 | REQ-038 | 6 - Top Customers | Analytics | Record evidence and decisions - Rank within country | Rank customers by revenue separately within each country. | Must | 0.5 | TSK-189 | Record evidence and decisions: Rank within country | Not Started | 0%
TSK-191 | REQ-039 | 6 - Top Customers | Analytics | Analyze and document - Top 10 per country | Return customers whose rank is 10 or lower. | Must | 1 | TSK-190 | Analyze and document: Top 10 per country | Not Started | 0%
TSK-192 | REQ-039 | 6 - Top Customers | Analytics | Design approach - Top 10 per country | Return customers whose rank is 10 or lower. | Must | 0.5 | TSK-191 | Design approach: Top 10 per country | Not Started | 0%
TSK-193 | REQ-039 | 6 - Top Customers | Analytics | Implement SQL or artifact - Top 10 per country | Return customers whose rank is 10 or lower. | Must | 2 | TSK-192 | Top-customer view | Not Started | 0%
TSK-194 | REQ-039 | 6 - Top Customers | Analytics | Create and execute tests - Top 10 per country | Return customers whose rank is 10 or lower. | Must | 1 | TSK-193 | Create and execute tests: Top 10 per country | Not Started | 0%
TSK-195 | REQ-039 | 6 - Top Customers | Analytics | Record evidence and decisions - Top 10 per country | Return customers whose rank is 10 or lower. | Must | 0.5 | TSK-194 | Record evidence and decisions: Top 10 per country | Not Started | 0%
TSK-196 | REQ-040 | 6 - Top Customers | Analytics | Analyze and document - Define tie behavior | Select RANK or DENSE_RANK and document whether ties can return more than 10 rows. | Must | 0.5 | TSK-195 | Analyze and document: Define tie behavior | Not Started | 0%
TSK-197 | REQ-040 | 6 - Top Customers | Analytics | Design approach - Define tie behavior | Select RANK or DENSE_RANK and document whether ties can return more than 10 rows. | Must | 0.5 | TSK-196 | Design approach: Define tie behavior | Not Started | 0%
TSK-198 | REQ-040 | 6 - Top Customers | Analytics | Implement SQL or artifact - Define tie behavior | Select RANK or DENSE_RANK and document whether ties can return more than 10 rows. | Must | 1.5 | TSK-197 | Tie decision | Not Started | 0%
TSK-199 | REQ-040 | 6 - Top Customers | Analytics | Create and execute tests - Define tie behavior | Select RANK or DENSE_RANK and document whether ties can return more than 10 rows. | Must | 1 | TSK-198 | Create and execute tests: Define tie behavior | Not Started | 0%
TSK-200 | REQ-040 | 6 - Top Customers | Analytics | Record evidence and decisions - Define tie behavior | Select RANK or DENSE_RANK and document whether ties can return more than 10 rows. | Must | 0.5 | TSK-199 | Record evidence and decisions: Define tie behavior | Not Started | 0%
TSK-201 | REQ-041 | 6 - Top Customers | History | Analyze and document - Use transaction-time geography | Attribute the sale to the customer/location version valid on the order date. | Should | 0.5 | TSK-200 | Analyze and document: Use transaction-time geography | Not Started | 0%
TSK-202 | REQ-041 | 6 - Top Customers | History | Design approach - Use transaction-time geography | Attribute the sale to the customer/location version valid on the order date. | Should | 0.5 | TSK-201 | Design approach: Use transaction-time geography | Not Started | 0%
TSK-203 | REQ-041 | 6 - Top Customers | History | Implement SQL or artifact - Use transaction-time geography | Attribute the sale to the customer/location version valid on the order date. | Should | 2 | TSK-202 | Temporal join | Not Started | 0%
TSK-204 | REQ-041 | 6 - Top Customers | History | Create and execute tests - Use transaction-time geography | Attribute the sale to the customer/location version valid on the order date. | Should | 1 | TSK-203 | Create and execute tests: Use transaction-time geography | Not Started | 0%
TSK-205 | REQ-041 | 6 - Top Customers | History | Record evidence and decisions - Use transaction-time geography | Attribute the sale to the customer/location version valid on the order date. | Should | 0.5 | TSK-204 | Record evidence and decisions: Use transaction-time geography | Not Started | 0%
TSK-206 | REQ-042 | 6 - Top Customers | Metric | Analyze and document - Parameterize period | Allow ranking for a selected date range. | Should | 1 | TSK-205 | Analyze and document: Parameterize period | Not Started | 0%
TSK-207 | REQ-042 | 6 - Top Customers | Metric | Design approach - Parameterize period | Allow ranking for a selected date range. | Should | 1 | TSK-206 | Design approach: Parameterize period | Not Started | 0%
TSK-208 | REQ-042 | 6 - Top Customers | Metric | Implement SQL or artifact - Parameterize period | Allow ranking for a selected date range. | Should | 1 | TSK-207 | Parameterized procedure/view | Not Started | 0%
TSK-209 | REQ-042 | 6 - Top Customers | Metric | Create and execute tests - Parameterize period | Allow ranking for a selected date range. | Should | 1 | TSK-208 | Create and execute tests: Parameterize period | Not Started | 0%
TSK-210 | REQ-042 | 6 - Top Customers | Metric | Record evidence and decisions - Parameterize period | Allow ranking for a selected date range. | Should | 0.5 | TSK-209 | Record evidence and decisions: Parameterize period | Not Started | 0%
TSK-211 | REQ-043 | 7 - Incremental Load | Control | Analyze and document - Create watermark table | Store PipelineName, SourceObject, LastSuccessfulWatermark, LastBatchID, Status and update timestamp. | Must | 0.5 | TSK-210 | Analyze and document: Create watermark table | Not Started | 0%
TSK-212 | REQ-043 | 7 - Incremental Load | Control | Design approach - Create watermark table | Store PipelineName, SourceObject, LastSuccessfulWatermark, LastBatchID, Status and update timestamp. | Must | 1 | TSK-211 | Design approach: Create watermark table | Not Started | 0%
TSK-213 | REQ-043 | 7 - Incremental Load | Control | Implement SQL or artifact - Create watermark table | Store PipelineName, SourceObject, LastSuccessfulWatermark, LastBatchID, Status and update timestamp. | Must | 1.5 | TSK-212 | Watermark table | Not Started | 0%
TSK-214 | REQ-043 | 7 - Incremental Load | Control | Create and execute tests - Create watermark table | Store PipelineName, SourceObject, LastSuccessfulWatermark, LastBatchID, Status and update timestamp. | Must | 1 | TSK-213 | Create and execute tests: Create watermark table | Not Started | 0%
TSK-215 | REQ-043 | 7 - Incremental Load | Control | Record evidence and decisions - Create watermark table | Store PipelineName, SourceObject, LastSuccessfulWatermark, LastBatchID, Status and update timestamp. | Must | 0.5 | TSK-214 | Record evidence and decisions: Create watermark table | Not Started | 0%
TSK-216 | REQ-044 | 7 - Incremental Load | Extraction | Analyze and document - Read bounded source window | Capture high watermark at run start and extract greater than previous watermark and less than or equal to high watermark. | Must | 1 | TSK-215 | Analyze and document: Read bounded source window | Not Started | 0%
TSK-217 | REQ-044 | 7 - Incremental Load | Extraction | Design approach - Read bounded source window | Capture high watermark at run start and extract greater than previous watermark and less than or equal to high watermark. | Must | 1 | TSK-216 | Design approach: Read bounded source window | Not Started | 0%
TSK-218 | REQ-044 | 7 - Incremental Load | Extraction | Implement SQL or artifact - Read bounded source window | Capture high watermark at run start and extract greater than previous watermark and less than or equal to high watermark. | Must | 2 | TSK-217 | Extraction query | Not Started | 0%
TSK-219 | REQ-044 | 7 - Incremental Load | Extraction | Create and execute tests - Read bounded source window | Capture high watermark at run start and extract greater than previous watermark and less than or equal to high watermark. | Must | 1 | TSK-218 | Create and execute tests: Read bounded source window | Not Started | 0%
TSK-220 | REQ-044 | 7 - Incremental Load | Extraction | Record evidence and decisions - Read bounded source window | Capture high watermark at run start and extract greater than previous watermark and less than or equal to high watermark. | Must | 0.5 | TSK-219 | Record evidence and decisions: Read bounded source window | Not Started | 0%
TSK-221 | REQ-045 | 7 - Incremental Load | Control | Analyze and document - Advance only on success | Update the successful watermark only after target transaction and validations succeed. | Must | 1 | TSK-220 | Analyze and document: Advance only on success | Not Started | 0%
TSK-222 | REQ-045 | 7 - Incremental Load | Control | Design approach - Advance only on success | Update the successful watermark only after target transaction and validations succeed. | Must | 1 | TSK-221 | Design approach: Advance only on success | Not Started | 0%
TSK-223 | REQ-045 | 7 - Incremental Load | Control | Implement SQL or artifact - Advance only on success | Update the successful watermark only after target transaction and validations succeed. | Must | 2 | TSK-222 | Commit logic | Not Started | 0%
TSK-224 | REQ-045 | 7 - Incremental Load | Control | Create and execute tests - Advance only on success | Update the successful watermark only after target transaction and validations succeed. | Must | 1 | TSK-223 | Create and execute tests: Advance only on success | Not Started | 0%
TSK-225 | REQ-045 | 7 - Incremental Load | Control | Record evidence and decisions - Advance only on success | Update the successful watermark only after target transaction and validations succeed. | Must | 0.5 | TSK-224 | Record evidence and decisions: Advance only on success | Not Started | 0%
TSK-226 | REQ-046 | 7 - Incremental Load | Recovery | Analyze and document - Support restart | Reuse or safely regenerate batch state after failure without duplication. | Must | 1 | TSK-225 | Analyze and document: Support restart | Not Started | 0%
TSK-227 | REQ-046 | 7 - Incremental Load | Recovery | Design approach - Support restart | Reuse or safely regenerate batch state after failure without duplication. | Must | 1 | TSK-226 | Design approach: Support restart | Not Started | 0%
TSK-228 | REQ-046 | 7 - Incremental Load | Recovery | Implement SQL or artifact - Support restart | Reuse or safely regenerate batch state after failure without duplication. | Must | 2 | TSK-227 | Restart procedure | Not Started | 0%
TSK-229 | REQ-046 | 7 - Incremental Load | Recovery | Create and execute tests - Support restart | Reuse or safely regenerate batch state after failure without duplication. | Must | 1 | TSK-228 | Create and execute tests: Support restart | Not Started | 0%
TSK-230 | REQ-046 | 7 - Incremental Load | Recovery | Record evidence and decisions - Support restart | Reuse or safely regenerate batch state after failure without duplication. | Must | 0.5 | TSK-229 | Record evidence and decisions: Support restart | Not Started | 0%
TSK-231 | REQ-047 | 7 - Incremental Load | Quality | Analyze and document - Persist batch metrics | Record extracted, inserted, updated, rejected and target counts. | Must | 1 | TSK-230 | Analyze and document: Persist batch metrics | Not Started | 0%
TSK-232 | REQ-047 | 7 - Incremental Load | Quality | Design approach - Persist batch metrics | Record extracted, inserted, updated, rejected and target counts. | Must | 1 | TSK-231 | Design approach: Persist batch metrics | Not Started | 0%
TSK-233 | REQ-047 | 7 - Incremental Load | Quality | Implement SQL or artifact - Persist batch metrics | Record extracted, inserted, updated, rejected and target counts. | Must | 1.5 | TSK-232 | Batch audit table | Not Started | 0%
TSK-234 | REQ-047 | 7 - Incremental Load | Quality | Create and execute tests - Persist batch metrics | Record extracted, inserted, updated, rejected and target counts. | Must | 1 | TSK-233 | Create and execute tests: Persist batch metrics | Not Started | 0%
TSK-235 | REQ-047 | 7 - Incremental Load | Quality | Record evidence and decisions - Persist batch metrics | Record extracted, inserted, updated, rejected and target counts. | Must | 0.5 | TSK-234 | Record evidence and decisions: Persist batch metrics | Not Started | 0%
TSK-236 | REQ-048 | 7 - Incremental Load | Deletion | Analyze and document - Define source-delete strategy | Choose soft delete, tombstone, CDC or periodic reconciliation. | Should | 0.5 | TSK-235 | Analyze and document: Define source-delete strategy | Not Started | 0%
TSK-237 | REQ-048 | 7 - Incremental Load | Deletion | Design approach - Define source-delete strategy | Choose soft delete, tombstone, CDC or periodic reconciliation. | Should | 0.5 | TSK-236 | Design approach: Define source-delete strategy | Not Started | 0%
TSK-238 | REQ-048 | 7 - Incremental Load | Deletion | Implement SQL or artifact - Define source-delete strategy | Choose soft delete, tombstone, CDC or periodic reconciliation. | Should | 1.5 | TSK-237 | Delete strategy | Not Started | 0%
TSK-239 | REQ-048 | 7 - Incremental Load | Deletion | Create and execute tests - Define source-delete strategy | Choose soft delete, tombstone, CDC or periodic reconciliation. | Should | 1 | TSK-238 | Create and execute tests: Define source-delete strategy | Not Started | 0%
TSK-240 | REQ-048 | 7 - Incremental Load | Deletion | Record evidence and decisions - Define source-delete strategy | Choose soft delete, tombstone, CDC or periodic reconciliation. | Should | 0.5 | TSK-239 | Record evidence and decisions: Define source-delete strategy | Not Started | 0%
TSK-241 | REQ-049 | 7 - Incremental Load | Late Data | Analyze and document - Apply lookback window | Optionally reread a configurable historical period to catch late updates, while preserving idempotency. | Should | 1 | TSK-240 | Analyze and document: Apply lookback window | Not Started | 0%
TSK-242 | REQ-049 | 7 - Incremental Load | Late Data | Design approach - Apply lookback window | Optionally reread a configurable historical period to catch late updates, while preserving idempotency. | Should | 0.5 | TSK-241 | Design approach: Apply lookback window | Not Started | 0%
TSK-243 | REQ-049 | 7 - Incremental Load | Late Data | Implement SQL or artifact - Apply lookback window | Optionally reread a configurable historical period to catch late updates, while preserving idempotency. | Should | 2 | TSK-242 | Lookback logic | Not Started | 0%
TSK-244 | REQ-049 | 7 - Incremental Load | Late Data | Create and execute tests - Apply lookback window | Optionally reread a configurable historical period to catch late updates, while preserving idempotency. | Should | 1 | TSK-243 | Create and execute tests: Apply lookback window | Not Started | 0%
TSK-245 | REQ-049 | 7 - Incremental Load | Late Data | Record evidence and decisions - Apply lookback window | Optionally reread a configurable historical period to catch late updates, while preserving idempotency. | Should | 0.5 | TSK-244 | Record evidence and decisions: Apply lookback window | Not Started | 0%
TSK-246 | REQ-050 | 7 - Incremental Load | Concurrency | Analyze and document - Prevent overlapping runs | Use an application lock or run-status check so the same pipeline cannot overlap unsafely. | Should | 0.5 | TSK-245 | Analyze and document: Prevent overlapping runs | Not Started | 0%
TSK-247 | REQ-050 | 7 - Incremental Load | Concurrency | Design approach - Prevent overlapping runs | Use an application lock or run-status check so the same pipeline cannot overlap unsafely. | Should | 1 | TSK-246 | Design approach: Prevent overlapping runs | Not Started | 0%
TSK-248 | REQ-050 | 7 - Incremental Load | Concurrency | Implement SQL or artifact - Prevent overlapping runs | Use an application lock or run-status check so the same pipeline cannot overlap unsafely. | Should | 2 | TSK-247 | Concurrency control | Not Started | 0%
TSK-249 | REQ-050 | 7 - Incremental Load | Concurrency | Create and execute tests - Prevent overlapping runs | Use an application lock or run-status check so the same pipeline cannot overlap unsafely. | Should | 1 | TSK-248 | Create and execute tests: Prevent overlapping runs | Not Started | 0%
TSK-250 | REQ-050 | 7 - Incremental Load | Concurrency | Record evidence and decisions - Prevent overlapping runs | Use an application lock or run-status check so the same pipeline cannot overlap unsafely. | Should | 0.5 | TSK-249 | Record evidence and decisions: Prevent overlapping runs | Not Started | 0%
TSK-251 | REQ-051 | 7 - Incremental Load | Operations | Analyze and document - Create operational logging | Capture start/end time, status, error message and executed procedure. | Must | 0.5 | TSK-250 | Analyze and document: Create operational logging | Not Started | 0%
TSK-252 | REQ-051 | 7 - Incremental Load | Operations | Design approach - Create operational logging | Capture start/end time, status, error message and executed procedure. | Must | 0.5 | TSK-251 | Design approach: Create operational logging | Not Started | 0%
TSK-253 | REQ-051 | 7 - Incremental Load | Operations | Implement SQL or artifact - Create operational logging | Capture start/end time, status, error message and executed procedure. | Must | 1.5 | TSK-252 | Operational log | Not Started | 0%
TSK-254 | REQ-051 | 7 - Incremental Load | Operations | Create and execute tests - Create operational logging | Capture start/end time, status, error message and executed procedure. | Must | 1 | TSK-253 | Create and execute tests: Create operational logging | Not Started | 0%
TSK-255 | REQ-051 | 7 - Incremental Load | Operations | Record evidence and decisions - Create operational logging | Capture start/end time, status, error message and executed procedure. | Must | 0.5 | TSK-254 | Record evidence and decisions: Create operational logging | Not Started | 0%
TSK-256 | REQ-052 | 8 - Performance Tuning | Baseline | Analyze and document - Capture baseline | Record elapsed time, CPU, logical reads, row count and execution plan for target queries. | Must | 0.5 | TSK-255 | Analyze and document: Capture baseline | Not Started | 0%
TSK-257 | REQ-052 | 8 - Performance Tuning | Baseline | Design approach - Capture baseline | Record elapsed time, CPU, logical reads, row count and execution plan for target queries. | Must | 1 | TSK-256 | Design approach: Capture baseline | Not Started | 0%
TSK-258 | REQ-052 | 8 - Performance Tuning | Baseline | Implement SQL or artifact - Capture baseline | Record elapsed time, CPU, logical reads, row count and execution plan for target queries. | Must | 2 | TSK-257 | Baseline report | Not Started | 0%
TSK-259 | REQ-052 | 8 - Performance Tuning | Baseline | Create and execute tests - Capture baseline | Record elapsed time, CPU, logical reads, row count and execution plan for target queries. | Must | 1 | TSK-258 | Create and execute tests: Capture baseline | Not Started | 0%
TSK-260 | REQ-052 | 8 - Performance Tuning | Baseline | Record evidence and decisions - Capture baseline | Record elapsed time, CPU, logical reads, row count and execution plan for target queries. | Must | 0.5 | TSK-259 | Record evidence and decisions: Capture baseline | Not Started | 0%
TSK-261 | REQ-053 | 8 - Performance Tuning | Indexing | Analyze and document - Design clustered strategy | Choose a clustered key based on access pattern, uniqueness, width and load behavior. | Must | 1 | TSK-260 | Analyze and document: Design clustered strategy | Not Started | 0%
TSK-262 | REQ-053 | 8 - Performance Tuning | Indexing | Design approach - Design clustered strategy | Choose a clustered key based on access pattern, uniqueness, width and load behavior. | Must | 0.5 | TSK-261 | Design approach: Design clustered strategy | Not Started | 0%
TSK-263 | REQ-053 | 8 - Performance Tuning | Indexing | Implement SQL or artifact - Design clustered strategy | Choose a clustered key based on access pattern, uniqueness, width and load behavior. | Must | 2 | TSK-262 | Index decision | Not Started | 0%
TSK-264 | REQ-053 | 8 - Performance Tuning | Indexing | Create and execute tests - Design clustered strategy | Choose a clustered key based on access pattern, uniqueness, width and load behavior. | Must | 1 | TSK-263 | Create and execute tests: Design clustered strategy | Not Started | 0%
TSK-265 | REQ-053 | 8 - Performance Tuning | Indexing | Record evidence and decisions - Design clustered strategy | Choose a clustered key based on access pattern, uniqueness, width and load behavior. | Must | 0.5 | TSK-264 | Record evidence and decisions: Design clustered strategy | Not Started | 0%
TSK-266 | REQ-054 | 8 - Performance Tuning | Indexing | Analyze and document - Design covering indexes | Create selective nonclustered indexes with INCLUDE columns for critical filters and joins. | Must | 1 | TSK-265 | Analyze and document: Design covering indexes | Not Started | 0%
TSK-267 | REQ-054 | 8 - Performance Tuning | Indexing | Design approach - Design covering indexes | Create selective nonclustered indexes with INCLUDE columns for critical filters and joins. | Must | 0.5 | TSK-266 | Design approach: Design covering indexes | Not Started | 0%
TSK-268 | REQ-054 | 8 - Performance Tuning | Indexing | Implement SQL or artifact - Design covering indexes | Create selective nonclustered indexes with INCLUDE columns for critical filters and joins. | Must | 1.5 | TSK-267 | Index scripts | Not Started | 0%
TSK-269 | REQ-054 | 8 - Performance Tuning | Indexing | Create and execute tests - Design covering indexes | Create selective nonclustered indexes with INCLUDE columns for critical filters and joins. | Must | 1 | TSK-268 | Create and execute tests: Design covering indexes | Not Started | 0%
TSK-270 | REQ-054 | 8 - Performance Tuning | Indexing | Record evidence and decisions - Design covering indexes | Create selective nonclustered indexes with INCLUDE columns for critical filters and joins. | Must | 0.5 | TSK-269 | Record evidence and decisions: Design covering indexes | Not Started | 0%
TSK-271 | REQ-055 | 8 - Performance Tuning | Partitioning | Analyze and document - Evaluate date partitioning | Partition very large facts by a date key only when pruning, maintenance and lifecycle benefits justify complexity. | Should | 0.5 | TSK-270 | Analyze and document: Evaluate date partitioning | Not Started | 0%
TSK-272 | REQ-055 | 8 - Performance Tuning | Partitioning | Design approach - Evaluate date partitioning | Partition very large facts by a date key only when pruning, maintenance and lifecycle benefits justify complexity. | Should | 0.5 | TSK-271 | Design approach: Evaluate date partitioning | Not Started | 0%
TSK-273 | REQ-055 | 8 - Performance Tuning | Partitioning | Implement SQL or artifact - Evaluate date partitioning | Partition very large facts by a date key only when pruning, maintenance and lifecycle benefits justify complexity. | Should | 2 | TSK-272 | Partition evidence | Not Started | 0%
TSK-274 | REQ-055 | 8 - Performance Tuning | Partitioning | Create and execute tests - Evaluate date partitioning | Partition very large facts by a date key only when pruning, maintenance and lifecycle benefits justify complexity. | Should | 1 | TSK-273 | Create and execute tests: Evaluate date partitioning | Not Started | 0%
TSK-275 | REQ-055 | 8 - Performance Tuning | Partitioning | Record evidence and decisions - Evaluate date partitioning | Partition very large facts by a date key only when pruning, maintenance and lifecycle benefits justify complexity. | Should | 0.5 | TSK-274 | Record evidence and decisions: Evaluate date partitioning | Not Started | 0%
TSK-276 | REQ-056 | 8 - Performance Tuning | SQL | Analyze and document - Remove non-sargable predicates | Avoid functions on filtered columns and implicit datatype conversions. | Must | 1 | TSK-275 | Analyze and document: Remove non-sargable predicates | Not Started | 0%
TSK-277 | REQ-056 | 8 - Performance Tuning | SQL | Design approach - Remove non-sargable predicates | Avoid functions on filtered columns and implicit datatype conversions. | Must | 1 | TSK-276 | Design approach: Remove non-sargable predicates | Not Started | 0%
TSK-278 | REQ-056 | 8 - Performance Tuning | SQL | Implement SQL or artifact - Remove non-sargable predicates | Avoid functions on filtered columns and implicit datatype conversions. | Must | 1.5 | TSK-277 | Query rewrite | Not Started | 0%
TSK-279 | REQ-056 | 8 - Performance Tuning | SQL | Create and execute tests - Remove non-sargable predicates | Avoid functions on filtered columns and implicit datatype conversions. | Must | 1 | TSK-278 | Create and execute tests: Remove non-sargable predicates | Not Started | 0%
TSK-280 | REQ-056 | 8 - Performance Tuning | SQL | Record evidence and decisions - Remove non-sargable predicates | Avoid functions on filtered columns and implicit datatype conversions. | Must | 0.5 | TSK-279 | Record evidence and decisions: Remove non-sargable predicates | Not Started | 0%
TSK-281 | REQ-057 | 8 - Performance Tuning | Statistics | Analyze and document - Maintain statistics | Define statistics update approach after significant loads. | Should | 1 | TSK-280 | Analyze and document: Maintain statistics | Not Started | 0%
TSK-282 | REQ-057 | 8 - Performance Tuning | Statistics | Design approach - Maintain statistics | Define statistics update approach after significant loads. | Should | 1 | TSK-281 | Design approach: Maintain statistics | Not Started | 0%
TSK-283 | REQ-057 | 8 - Performance Tuning | Statistics | Implement SQL or artifact - Maintain statistics | Define statistics update approach after significant loads. | Should | 2 | TSK-282 | Maintenance script | Not Started | 0%
TSK-284 | REQ-057 | 8 - Performance Tuning | Statistics | Create and execute tests - Maintain statistics | Define statistics update approach after significant loads. | Should | 1 | TSK-283 | Create and execute tests: Maintain statistics | Not Started | 0%
TSK-285 | REQ-057 | 8 - Performance Tuning | Statistics | Record evidence and decisions - Maintain statistics | Define statistics update approach after significant loads. | Should | 0.5 | TSK-284 | Record evidence and decisions: Maintain statistics | Not Started | 0%
TSK-286 | REQ-058 | 8 - Performance Tuning | Aggregation | Analyze and document - Create summary table | Build daily/monthly aggregate for high-frequency dashboard queries where justified. | Should | 1 | TSK-285 | Analyze and document: Create summary table | Not Started | 0%
TSK-287 | REQ-058 | 8 - Performance Tuning | Aggregation | Design approach - Create summary table | Build daily/monthly aggregate for high-frequency dashboard queries where justified. | Should | 1 | TSK-286 | Design approach: Create summary table | Not Started | 0%
TSK-288 | REQ-058 | 8 - Performance Tuning | Aggregation | Implement SQL or artifact - Create summary table | Build daily/monthly aggregate for high-frequency dashboard queries where justified. | Should | 1.5 | TSK-287 | Aggregate table | Not Started | 0%
TSK-289 | REQ-058 | 8 - Performance Tuning | Aggregation | Create and execute tests - Create summary table | Build daily/monthly aggregate for high-frequency dashboard queries where justified. | Should | 1 | TSK-288 | Create and execute tests: Create summary table | Not Started | 0%
TSK-290 | REQ-058 | 8 - Performance Tuning | Aggregation | Record evidence and decisions - Create summary table | Build daily/monthly aggregate for high-frequency dashboard queries where justified. | Should | 0.5 | TSK-289 | Record evidence and decisions: Create summary table | Not Started | 0%
TSK-291 | REQ-059 | 8 - Performance Tuning | Analysis | Analyze and document - Detect skew and parameter issues | Investigate skew, spills, memory grants and parameter-sensitive plans. | Should | 0.5 | TSK-290 | Analyze and document: Detect skew and parameter issues | Not Started | 0%
TSK-292 | REQ-059 | 8 - Performance Tuning | Analysis | Design approach - Detect skew and parameter issues | Investigate skew, spills, memory grants and parameter-sensitive plans. | Should | 0.5 | TSK-291 | Design approach: Detect skew and parameter issues | Not Started | 0%
TSK-293 | REQ-059 | 8 - Performance Tuning | Analysis | Implement SQL or artifact - Detect skew and parameter issues | Investigate skew, spills, memory grants and parameter-sensitive plans. | Should | 2 | TSK-292 | Tuning notes | Not Started | 0%
TSK-294 | REQ-059 | 8 - Performance Tuning | Analysis | Create and execute tests - Detect skew and parameter issues | Investigate skew, spills, memory grants and parameter-sensitive plans. | Should | 1 | TSK-293 | Create and execute tests: Detect skew and parameter issues | Not Started | 0%
TSK-295 | REQ-059 | 8 - Performance Tuning | Analysis | Record evidence and decisions - Detect skew and parameter issues | Investigate skew, spills, memory grants and parameter-sensitive plans. | Should | 0.5 | TSK-294 | Record evidence and decisions: Detect skew and parameter issues | Not Started | 0%
TSK-296 | REQ-060 | 8 - Performance Tuning | Regression | Analyze and document - Compare before and after | Document improvement without changing row-level results. | Must | 1 | TSK-295 | Analyze and document: Compare before and after | Not Started | 0%
TSK-297 | REQ-060 | 8 - Performance Tuning | Regression | Design approach - Compare before and after | Document improvement without changing row-level results. | Must | 0.5 | TSK-296 | Design approach: Compare before and after | Not Started | 0%
TSK-298 | REQ-060 | 8 - Performance Tuning | Regression | Implement SQL or artifact - Compare before and after | Document improvement without changing row-level results. | Must | 1.5 | TSK-297 | Performance report | Not Started | 0%
TSK-299 | REQ-060 | 8 - Performance Tuning | Regression | Create and execute tests - Compare before and after | Document improvement without changing row-level results. | Must | 1 | TSK-298 | Create and execute tests: Compare before and after | Not Started | 0%
TSK-300 | REQ-060 | 8 - Performance Tuning | Regression | Record evidence and decisions - Compare before and after | Document improvement without changing row-level results. | Must | 0.5 | TSK-299 | Record evidence and decisions: Compare before and after | Not Started | 0%
TSK-301 | REQ-061 | 9 - Reconciliation & RCA | Reconciliation | Analyze and document - Build source-to-target control totals | Compare row count, quantity, gross, adjustments and net revenue by business date and batch. | Must | 0.5 | TSK-300 | Analyze and document: Build source-to-target control totals | Not Started | 0%
TSK-302 | REQ-061 | 9 - Reconciliation & RCA | Reconciliation | Design approach - Build source-to-target control totals | Compare row count, quantity, gross, adjustments and net revenue by business date and batch. | Must | 1 | TSK-301 | Design approach: Build source-to-target control totals | Not Started | 0%
TSK-303 | REQ-061 | 9 - Reconciliation & RCA | Reconciliation | Implement SQL or artifact - Build source-to-target control totals | Compare row count, quantity, gross, adjustments and net revenue by business date and batch. | Must | 2 | TSK-302 | Reconciliation report | Not Started | 0%
TSK-304 | REQ-061 | 9 - Reconciliation & RCA | Reconciliation | Create and execute tests - Build source-to-target control totals | Compare row count, quantity, gross, adjustments and net revenue by business date and batch. | Must | 1 | TSK-303 | Create and execute tests: Build source-to-target control totals | Not Started | 0%
TSK-305 | REQ-061 | 9 - Reconciliation & RCA | Reconciliation | Record evidence and decisions - Build source-to-target control totals | Compare row count, quantity, gross, adjustments and net revenue by business date and batch. | Must | 0.5 | TSK-304 | Record evidence and decisions: Build source-to-target control totals | Not Started | 0%
TSK-306 | REQ-062 | 9 - Reconciliation & RCA | RCA | Analyze and document - Investigate revenue restatement | Assess late data, duplicate removal, SCD joins, failed batches, currency rates, deletes and filter changes. | Must | 1 | TSK-305 | Analyze and document: Investigate revenue restatement | Not Started | 0%
TSK-307 | REQ-062 | 9 - Reconciliation & RCA | RCA | Design approach - Investigate revenue restatement | Assess late data, duplicate removal, SCD joins, failed batches, currency rates, deletes and filter changes. | Must | 1 | TSK-306 | Design approach: Investigate revenue restatement | Not Started | 0%
TSK-308 | REQ-062 | 9 - Reconciliation & RCA | RCA | Implement SQL or artifact - Investigate revenue restatement | Assess late data, duplicate removal, SCD joins, failed batches, currency rates, deletes and filter changes. | Must | 1 | TSK-307 | RCA worksheet | Not Started | 0%
TSK-309 | REQ-062 | 9 - Reconciliation & RCA | RCA | Create and execute tests - Investigate revenue restatement | Assess late data, duplicate removal, SCD joins, failed batches, currency rates, deletes and filter changes. | Must | 1 | TSK-308 | Create and execute tests: Investigate revenue restatement | Not Started | 0%
TSK-310 | REQ-062 | 9 - Reconciliation & RCA | RCA | Record evidence and decisions - Investigate revenue restatement | Assess late data, duplicate removal, SCD joins, failed batches, currency rates, deletes and filter changes. | Must | 0.5 | TSK-309 | Record evidence and decisions: Investigate revenue restatement | Not Started | 0%
TSK-311 | REQ-063 | 9 - Reconciliation & RCA | Reconciliation | Analyze and document - Classify variances | Categorize timing, logic, reference-data, source-correction and processing variances. | Should | 0.5 | TSK-310 | Analyze and document: Classify variances | Not Started | 0%
TSK-312 | REQ-063 | 9 - Reconciliation & RCA | Reconciliation | Design approach - Classify variances | Categorize timing, logic, reference-data, source-correction and processing variances. | Should | 1 | TSK-311 | Design approach: Classify variances | Not Started | 0%
TSK-313 | REQ-063 | 9 - Reconciliation & RCA | Reconciliation | Implement SQL or artifact - Classify variances | Categorize timing, logic, reference-data, source-correction and processing variances. | Should | 1.5 | TSK-312 | Variance table | Not Started | 0%
TSK-314 | REQ-063 | 9 - Reconciliation & RCA | Reconciliation | Create and execute tests - Classify variances | Categorize timing, logic, reference-data, source-correction and processing variances. | Should | 1 | TSK-313 | Create and execute tests: Classify variances | Not Started | 0%
TSK-315 | REQ-063 | 9 - Reconciliation & RCA | Reconciliation | Record evidence and decisions - Classify variances | Categorize timing, logic, reference-data, source-correction and processing variances. | Should | 0.5 | TSK-314 | Record evidence and decisions: Classify variances | Not Started | 0%
TSK-316 | REQ-064 | 9 - Reconciliation & RCA | Audit | Analyze and document - Create lineage evidence | Trace dashboard total to aggregate, fact, batch and source keys. | Must | 1 | TSK-315 | Analyze and document: Create lineage evidence | Not Started | 0%
TSK-317 | REQ-064 | 9 - Reconciliation & RCA | Audit | Design approach - Create lineage evidence | Trace dashboard total to aggregate, fact, batch and source keys. | Must | 0.5 | TSK-316 | Design approach: Create lineage evidence | Not Started | 0%
TSK-318 | REQ-064 | 9 - Reconciliation & RCA | Audit | Implement SQL or artifact - Create lineage evidence | Trace dashboard total to aggregate, fact, batch and source keys. | Must | 1 | TSK-317 | Lineage query | Not Started | 0%
TSK-319 | REQ-064 | 9 - Reconciliation & RCA | Audit | Create and execute tests - Create lineage evidence | Trace dashboard total to aggregate, fact, batch and source keys. | Must | 1 | TSK-318 | Create and execute tests: Create lineage evidence | Not Started | 0%
TSK-320 | REQ-064 | 9 - Reconciliation & RCA | Audit | Record evidence and decisions - Create lineage evidence | Trace dashboard total to aggregate, fact, batch and source keys. | Must | 0.5 | TSK-319 | Record evidence and decisions: Create lineage evidence | Not Started | 0%
TSK-321 | REQ-065 | 9 - Reconciliation & RCA | Quality | Analyze and document - Set reconciliation thresholds | Define zero tolerance for counts where appropriate and approved tolerances for currency rounding. | Must | 1 | TSK-320 | Analyze and document: Set reconciliation thresholds | Not Started | 0%
TSK-322 | REQ-065 | 9 - Reconciliation & RCA | Quality | Design approach - Set reconciliation thresholds | Define zero tolerance for counts where appropriate and approved tolerances for currency rounding. | Must | 1 | TSK-321 | Design approach: Set reconciliation thresholds | Not Started | 0%
TSK-323 | REQ-065 | 9 - Reconciliation & RCA | Quality | Implement SQL or artifact - Set reconciliation thresholds | Define zero tolerance for counts where appropriate and approved tolerances for currency rounding. | Must | 1.5 | TSK-322 | Threshold rules | Not Started | 0%
TSK-324 | REQ-065 | 9 - Reconciliation & RCA | Quality | Create and execute tests - Set reconciliation thresholds | Define zero tolerance for counts where appropriate and approved tolerances for currency rounding. | Must | 1 | TSK-323 | Create and execute tests: Set reconciliation thresholds | Not Started | 0%
TSK-325 | REQ-065 | 9 - Reconciliation & RCA | Quality | Record evidence and decisions - Set reconciliation thresholds | Define zero tolerance for counts where appropriate and approved tolerances for currency rounding. | Must | 0.5 | TSK-324 | Record evidence and decisions: Set reconciliation thresholds | Not Started | 0%
TSK-326 | REQ-066 | 9 - Reconciliation & RCA | Operations | Analyze and document - Create support runbook | Document symptoms, diagnostic SQL, common causes, recovery and escalation evidence. | Should | 1 | TSK-325 | Analyze and document: Create support runbook | Not Started | 0%
TSK-327 | REQ-066 | 9 - Reconciliation & RCA | Operations | Design approach - Create support runbook | Document symptoms, diagnostic SQL, common causes, recovery and escalation evidence. | Should | 1 | TSK-326 | Design approach: Create support runbook | Not Started | 0%
TSK-328 | REQ-066 | 9 - Reconciliation & RCA | Operations | Implement SQL or artifact - Create support runbook | Document symptoms, diagnostic SQL, common causes, recovery and escalation evidence. | Should | 2 | TSK-327 | Support runbook | Not Started | 0%
TSK-329 | REQ-066 | 9 - Reconciliation & RCA | Operations | Create and execute tests - Create support runbook | Document symptoms, diagnostic SQL, common causes, recovery and escalation evidence. | Should | 1 | TSK-328 | Create and execute tests: Create support runbook | Not Started | 0%
TSK-330 | REQ-066 | 9 - Reconciliation & RCA | Operations | Record evidence and decisions - Create support runbook | Document symptoms, diagnostic SQL, common causes, recovery and escalation evidence. | Should | 0.5 | TSK-329 | Record evidence and decisions: Create support runbook | Not Started | 0%
TSK-331 | REQ-067 | 10 - Packaging & Portfolio | Delivery | Analyze and document - Organize source control | Store DDL, DML, procedures, views, tests and documentation in a clear repository structure. | Must | 1 | TSK-330 | Analyze and document: Organize source control | Not Started | 0%
TSK-332 | REQ-067 | 10 - Packaging & Portfolio | Delivery | Design approach - Organize source control | Store DDL, DML, procedures, views, tests and documentation in a clear repository structure. | Must | 0.5 | TSK-331 | Design approach: Organize source control | Not Started | 0%
TSK-333 | REQ-067 | 10 - Packaging & Portfolio | Delivery | Implement SQL or artifact - Organize source control | Store DDL, DML, procedures, views, tests and documentation in a clear repository structure. | Must | 1 | TSK-332 | Repository | Not Started | 0%
TSK-334 | REQ-067 | 10 - Packaging & Portfolio | Delivery | Create and execute tests - Organize source control | Store DDL, DML, procedures, views, tests and documentation in a clear repository structure. | Must | 1 | TSK-333 | Create and execute tests: Organize source control | Not Started | 0%
TSK-335 | REQ-067 | 10 - Packaging & Portfolio | Delivery | Record evidence and decisions - Organize source control | Store DDL, DML, procedures, views, tests and documentation in a clear repository structure. | Must | 0.5 | TSK-334 | Record evidence and decisions: Organize source control | Not Started | 0%
TSK-336 | REQ-068 | 10 - Packaging & Portfolio | Delivery | Analyze and document - Create deployment order | Provide numbered scripts or automated deployment with dependency order. | Must | 0.5 | TSK-335 | Analyze and document: Create deployment order | Not Started | 0%
TSK-337 | REQ-068 | 10 - Packaging & Portfolio | Delivery | Design approach - Create deployment order | Provide numbered scripts or automated deployment with dependency order. | Must | 1 | TSK-336 | Design approach: Create deployment order | Not Started | 0%
TSK-338 | REQ-068 | 10 - Packaging & Portfolio | Delivery | Implement SQL or artifact - Create deployment order | Provide numbered scripts or automated deployment with dependency order. | Must | 2 | TSK-337 | Deployment guide | Not Started | 0%
TSK-339 | REQ-068 | 10 - Packaging & Portfolio | Delivery | Create and execute tests - Create deployment order | Provide numbered scripts or automated deployment with dependency order. | Must | 1 | TSK-338 | Create and execute tests: Create deployment order | Not Started | 0%
TSK-340 | REQ-068 | 10 - Packaging & Portfolio | Delivery | Record evidence and decisions - Create deployment order | Provide numbered scripts or automated deployment with dependency order. | Must | 0.5 | TSK-339 | Record evidence and decisions: Create deployment order | Not Started | 0%
TSK-341 | REQ-069 | 10 - Packaging & Portfolio | Documentation | Analyze and document - Create architecture document | Include assumptions, diagram, grain, keys, loading patterns and security considerations. | Must | 1 | TSK-340 | Analyze and document: Create architecture document | Not Started | 0%
TSK-342 | REQ-069 | 10 - Packaging & Portfolio | Documentation | Design approach - Create architecture document | Include assumptions, diagram, grain, keys, loading patterns and security considerations. | Must | 1 | TSK-341 | Design approach: Create architecture document | Not Started | 0%
TSK-343 | REQ-069 | 10 - Packaging & Portfolio | Documentation | Implement SQL or artifact - Create architecture document | Include assumptions, diagram, grain, keys, loading patterns and security considerations. | Must | 1 | TSK-342 | Architecture document | Not Started | 0%
TSK-344 | REQ-069 | 10 - Packaging & Portfolio | Documentation | Create and execute tests - Create architecture document | Include assumptions, diagram, grain, keys, loading patterns and security considerations. | Must | 1 | TSK-343 | Create and execute tests: Create architecture document | Not Started | 0%
TSK-345 | REQ-069 | 10 - Packaging & Portfolio | Documentation | Record evidence and decisions - Create architecture document | Include assumptions, diagram, grain, keys, loading patterns and security considerations. | Must | 0.5 | TSK-344 | Record evidence and decisions: Create architecture document | Not Started | 0%
TSK-346 | REQ-070 | 10 - Packaging & Portfolio | Evidence | Analyze and document - Capture test evidence | Record expected, actual, status and evidence query/file for all tests. | Must | 1 | TSK-345 | Analyze and document: Capture test evidence | Not Started | 0%
TSK-347 | REQ-070 | 10 - Packaging & Portfolio | Evidence | Design approach - Capture test evidence | Record expected, actual, status and evidence query/file for all tests. | Must | 1 | TSK-346 | Design approach: Capture test evidence | Not Started | 0%
TSK-348 | REQ-070 | 10 - Packaging & Portfolio | Evidence | Implement SQL or artifact - Capture test evidence | Record expected, actual, status and evidence query/file for all tests. | Must | 2 | TSK-347 | Test report | Not Started | 0%
TSK-349 | REQ-070 | 10 - Packaging & Portfolio | Evidence | Create and execute tests - Capture test evidence | Record expected, actual, status and evidence query/file for all tests. | Must | 1 | TSK-348 | Create and execute tests: Capture test evidence | Not Started | 0%
TSK-350 | REQ-070 | 10 - Packaging & Portfolio | Evidence | Record evidence and decisions - Capture test evidence | Record expected, actual, status and evidence query/file for all tests. | Must | 0.5 | TSK-349 | Record evidence and decisions: Capture test evidence | Not Started | 0%
TSK-351 | REQ-071 | 10 - Packaging & Portfolio | Evidence | Analyze and document - Capture performance evidence | Store baseline and optimized plans/metrics. | Should | 1 | TSK-350 | Analyze and document: Capture performance evidence | Not Started | 0%
TSK-352 | REQ-071 | 10 - Packaging & Portfolio | Evidence | Design approach - Capture performance evidence | Store baseline and optimized plans/metrics. | Should | 0.5 | TSK-351 | Design approach: Capture performance evidence | Not Started | 0%
TSK-353 | REQ-071 | 10 - Packaging & Portfolio | Evidence | Implement SQL or artifact - Capture performance evidence | Store baseline and optimized plans/metrics. | Should | 1 | TSK-352 | Tuning report | Not Started | 0%
TSK-354 | REQ-071 | 10 - Packaging & Portfolio | Evidence | Create and execute tests - Capture performance evidence | Store baseline and optimized plans/metrics. | Should | 1 | TSK-353 | Create and execute tests: Capture performance evidence | Not Started | 0%
TSK-355 | REQ-071 | 10 - Packaging & Portfolio | Evidence | Record evidence and decisions - Capture performance evidence | Store baseline and optimized plans/metrics. | Should | 0.5 | TSK-354 | Record evidence and decisions: Capture performance evidence | Not Started | 0%
TSK-356 | REQ-072 | 10 - Packaging & Portfolio | Portfolio | Analyze and document - Prepare honest resume wording | State that this is a self-directed portfolio project and quantify only measured results from your environment. | Must | 0.5 | TSK-355 | Analyze and document: Prepare honest resume wording | Not Started | 0%
TSK-357 | REQ-072 | 10 - Packaging & Portfolio | Portfolio | Design approach - Prepare honest resume wording | State that this is a self-directed portfolio project and quantify only measured results from your environment. | Must | 1 | TSK-356 | Design approach: Prepare honest resume wording | Not Started | 0%
TSK-358 | REQ-072 | 10 - Packaging & Portfolio | Portfolio | Implement SQL or artifact - Prepare honest resume wording | State that this is a self-directed portfolio project and quantify only measured results from your environment. | Must | 1 | TSK-357 | Resume bullets | Not Started | 0%
TSK-359 | REQ-072 | 10 - Packaging & Portfolio | Portfolio | Create and execute tests - Prepare honest resume wording | State that this is a self-directed portfolio project and quantify only measured results from your environment. | Must | 1 | TSK-358 | Create and execute tests: Prepare honest resume wording | Not Started | 0%
TSK-360 | REQ-072 | 10 - Packaging & Portfolio | Portfolio | Record evidence and decisions - Prepare honest resume wording | State that this is a self-directed portfolio project and quantify only measured results from your environment. | Must | 0.5 | TSK-359 | Record evidence and decisions: Prepare honest resume wording | Not Started | 0%
TSK-361 | REQ-073 | 10 - Packaging & Portfolio | Interview | Analyze and document - Prepare design defense | Explain trade-offs, failure recovery, data quality, performance, and alternative approaches. | Must | 1 | TSK-360 | Analyze and document: Prepare design defense | Not Started | 0%
TSK-362 | REQ-073 | 10 - Packaging & Portfolio | Interview | Design approach - Prepare design defense | Explain trade-offs, failure recovery, data quality, performance, and alternative approaches. | Must | 0.5 | TSK-361 | Design approach: Prepare design defense | Not Started | 0%
TSK-363 | REQ-073 | 10 - Packaging & Portfolio | Interview | Implement SQL or artifact - Prepare design defense | Explain trade-offs, failure recovery, data quality, performance, and alternative approaches. | Must | 2 | TSK-362 | Interview notes | Not Started | 0%
TSK-364 | REQ-073 | 10 - Packaging & Portfolio | Interview | Create and execute tests - Prepare design defense | Explain trade-offs, failure recovery, data quality, performance, and alternative approaches. | Must | 1 | TSK-363 | Create and execute tests: Prepare design defense | Not Started | 0%
TSK-365 | REQ-073 | 10 - Packaging & Portfolio | Interview | Record evidence and decisions - Prepare design defense | Explain trade-offs, failure recovery, data quality, performance, and alternative approaches. | Must | 0.5 | TSK-364 | Record evidence and decisions: Prepare design defense | Not Started | 0%

## Daily Plan
Daily Study Plan: 2 to 3 Hours per Working Day
Day # | Planned Date | Daily Capacity | Task ID | Phase | Small Task | Allocated Hours | Task Status | Task Completion % | Daily Planned Total | Notes
1 | 2026-09-01 | 3 | TSK-001 | 1 - Warehouse Modeling | Analyze and document - Confirm analytical scope | 1 | Not Started | 0% | 3
1 | 2026-09-01 | 3 | TSK-002 | 1 - Warehouse Modeling | Design approach - Confirm analytical scope | 0.5 | Not Started | 0% | 3
1 | 2026-09-01 | 3 | TSK-003 | 1 - Warehouse Modeling | Implement SQL or artifact - Confirm analytical scope | 1 | Not Started | 0% | 3
1 | 2026-09-01 | 3 | TSK-004 | 1 - Warehouse Modeling | Create and execute tests - Confirm analytical scope | 0.5 | Not Started | 0% | 3
2 | 2026-09-02 | 2 | TSK-004 | 1 - Warehouse Modeling | Create and execute tests - Confirm analytical scope | 0.5 | Not Started | 0% | 2
2 | 2026-09-02 | 2 | TSK-005 | 1 - Warehouse Modeling | Record evidence and decisions - Confirm analytical scope | 0.5 | Not Started | 0% | 2
2 | 2026-09-02 | 2 | TSK-006 | 1 - Warehouse Modeling | Analyze and document - Declare FactOrders grain | 0.5 | Not Started | 0% | 2
2 | 2026-09-02 | 2 | TSK-007 | 1 - Warehouse Modeling | Design approach - Declare FactOrders grain | 0.5 | Not Started | 0% | 2
3 | 2026-09-03 | 2.5 | TSK-008 | 1 - Warehouse Modeling | Implement SQL or artifact - Declare FactOrders grain | 1 | Not Started | 0% | 2.5
3 | 2026-09-03 | 2.5 | TSK-009 | 1 - Warehouse Modeling | Create and execute tests - Declare FactOrders grain | 1 | Not Started | 0% | 2.5
3 | 2026-09-03 | 2.5 | TSK-010 | 1 - Warehouse Modeling | Record evidence and decisions - Declare FactOrders grain | 0.5 | Not Started | 0% | 2.5
4 | 2026-09-04 | 3 | TSK-011 | 1 - Warehouse Modeling | Analyze and document - Declare FactShipment grain | 1 | Not Started | 0% | 3
4 | 2026-09-04 | 3 | TSK-012 | 1 - Warehouse Modeling | Design approach - Declare FactShipment grain | 1 | Not Started | 0% | 3
4 | 2026-09-04 | 3 | TSK-013 | 1 - Warehouse Modeling | Implement SQL or artifact - Declare FactShipment grain | 1 | Not Started | 0% | 3
5 | 2026-09-07 | 3 | TSK-013 | 1 - Warehouse Modeling | Implement SQL or artifact - Declare FactShipment grain | 1 | Not Started | 0% | 3
5 | 2026-09-07 | 3 | TSK-014 | 1 - Warehouse Modeling | Create and execute tests - Declare FactShipment grain | 1 | Not Started | 0% | 3
5 | 2026-09-07 | 3 | TSK-015 | 1 - Warehouse Modeling | Record evidence and decisions - Declare FactShipment grain | 0.5 | Not Started | 0% | 3
5 | 2026-09-07 | 3 | TSK-016 | 1 - Warehouse Modeling | Analyze and document - Design star schema | 0.5 | Not Started | 0% | 3
6 | 2026-09-08 | 3 | TSK-016 | 1 - Warehouse Modeling | Analyze and document - Design star schema | 0.5 | Not Started | 0% | 3
6 | 2026-09-08 | 3 | TSK-017 | 1 - Warehouse Modeling | Design approach - Design star schema | 0.5 | Not Started | 0% | 3
6 | 2026-09-08 | 3 | TSK-018 | 1 - Warehouse Modeling | Implement SQL or artifact - Design star schema | 1 | Not Started | 0% | 3
6 | 2026-09-08 | 3 | TSK-019 | 1 - Warehouse Modeling | Create and execute tests - Design star schema | 1 | Not Started | 0% | 3
7 | 2026-09-09 | 3 | TSK-020 | 1 - Warehouse Modeling | Record evidence and decisions - Design star schema | 0.5 | Not Started | 0% | 3
7 | 2026-09-09 | 3 | TSK-021 | 1 - Warehouse Modeling | Analyze and document - Use surrogate keys | 0.5 | Not Started | 0% | 3
7 | 2026-09-09 | 3 | TSK-022 | 1 - Warehouse Modeling | Design approach - Use surrogate keys | 1 | Not Started | 0% | 3
7 | 2026-09-09 | 3 | TSK-023 | 1 - Warehouse Modeling | Implement SQL or artifact - Use surrogate keys | 1 | Not Started | 0% | 3
8 | 2026-09-10 | 2.5 | TSK-023 | 1 - Warehouse Modeling | Implement SQL or artifact - Use surrogate keys | 1 | Not Started | 0% | 2.5
8 | 2026-09-10 | 2.5 | TSK-024 | 1 - Warehouse Modeling | Create and execute tests - Use surrogate keys | 1 | Not Started | 0% | 2.5
8 | 2026-09-10 | 2.5 | TSK-025 | 1 - Warehouse Modeling | Record evidence and decisions - Use surrogate keys | 0.5 | Not Started | 0% | 2.5
9 | 2026-09-11 | 2.5 | TSK-026 | 1 - Warehouse Modeling | Analyze and document - Create unknown members | 0.5 | Not Started | 0% | 2.5
9 | 2026-09-11 | 2.5 | TSK-027 | 1 - Warehouse Modeling | Design approach - Create unknown members | 1 | Not Started | 0% | 2.5
9 | 2026-09-11 | 2.5 | TSK-028 | 1 - Warehouse Modeling | Implement SQL or artifact - Create unknown members | 1 | Not Started | 0% | 2.5
10 | 2026-09-14 | 2 | TSK-028 | 1 - Warehouse Modeling | Implement SQL or artifact - Create unknown members | 1 | Not Started | 0% | 2
10 | 2026-09-14 | 2 | TSK-029 | 1 - Warehouse Modeling | Create and execute tests - Create unknown members | 1 | Not Started | 0% | 2
11 | 2026-09-15 | 3 | TSK-030 | 1 - Warehouse Modeling | Record evidence and decisions - Create unknown members | 0.5 | Not Started | 0% | 3
11 | 2026-09-15 | 3 | TSK-031 | 1 - Warehouse Modeling | Analyze and document - Define additive measures | 1 | Not Started | 0% | 3
11 | 2026-09-15 | 3 | TSK-032 | 1 - Warehouse Modeling | Design approach - Define additive measures | 0.5 | Not Started | 0% | 3
11 | 2026-09-15 | 3 | TSK-033 | 1 - Warehouse Modeling | Implement SQL or artifact - Define additive measures | 1 | Not Started | 0% | 3
12 | 2026-09-16 | 3 | TSK-033 | 1 - Warehouse Modeling | Implement SQL or artifact - Define additive measures | 0.5 | Not Started | 0% | 3
12 | 2026-09-16 | 3 | TSK-034 | 1 - Warehouse Modeling | Create and execute tests - Define additive measures | 1 | Not Started | 0% | 3
12 | 2026-09-16 | 3 | TSK-035 | 1 - Warehouse Modeling | Record evidence and decisions - Define additive measures | 0.5 | Not Started | 0% | 3
12 | 2026-09-16 | 3 | TSK-036 | 1 - Warehouse Modeling | Analyze and document - Add audit columns | 0.5 | Not Started | 0% | 3
12 | 2026-09-16 | 3 | TSK-037 | 1 - Warehouse Modeling | Design approach - Add audit columns | 0.5 | Not Started | 0% | 3
13 | 2026-09-17 | 2.5 | TSK-038 | 1 - Warehouse Modeling | Implement SQL or artifact - Add audit columns | 2 | Not Started | 0% | 2.5
13 | 2026-09-17 | 2.5 | TSK-039 | 1 - Warehouse Modeling | Create and execute tests - Add audit columns | 0.5 | Not Started | 0% | 2.5
14 | 2026-09-18 | 2 | TSK-039 | 1 - Warehouse Modeling | Create and execute tests - Add audit columns | 0.5 | Not Started | 0% | 2
14 | 2026-09-18 | 2 | TSK-040 | 1 - Warehouse Modeling | Record evidence and decisions - Add audit columns | 0.5 | Not Started | 0% | 2
14 | 2026-09-18 | 2 | TSK-041 | 1 - Warehouse Modeling | Analyze and document - Role-playing date dimensions | 1 | Not Started | 0% | 2
15 | 2026-09-21 | 2.5 | TSK-042 | 1 - Warehouse Modeling | Design approach - Role-playing date dimensions | 0.5 | Not Started | 0% | 2.5
15 | 2026-09-21 | 2.5 | TSK-043 | 1 - Warehouse Modeling | Implement SQL or artifact - Role-playing date dimensions | 1 | Not Started | 0% | 2.5
15 | 2026-09-21 | 2.5 | TSK-044 | 1 - Warehouse Modeling | Create and execute tests - Role-playing date dimensions | 1 | Not Started | 0% | 2.5
16 | 2026-09-22 | 2.5 | TSK-045 | 1 - Warehouse Modeling | Record evidence and decisions - Role-playing date dimensions | 0.5 | Not Started | 0% | 2.5
16 | 2026-09-22 | 2.5 | TSK-046 | 1 - Warehouse Modeling | Analyze and document - Enforce key integrity | 0.5 | Not Started | 0% | 2.5
16 | 2026-09-22 | 2.5 | TSK-047 | 1 - Warehouse Modeling | Design approach - Enforce key integrity | 1 | Not Started | 0% | 2.5
16 | 2026-09-22 | 2.5 | TSK-048 | 1 - Warehouse Modeling | Implement SQL or artifact - Enforce key integrity | 0.5 | Not Started | 0% | 2.5
17 | 2026-09-23 | 2 | TSK-048 | 1 - Warehouse Modeling | Implement SQL or artifact - Enforce key integrity | 0.5 | Not Started | 0% | 2
17 | 2026-09-23 | 2 | TSK-049 | 1 - Warehouse Modeling | Create and execute tests - Enforce key integrity | 1 | Not Started | 0% | 2
17 | 2026-09-23 | 2 | TSK-050 | 1 - Warehouse Modeling | Record evidence and decisions - Enforce key integrity | 0.5 | Not Started | 0% | 2
18 | 2026-09-24 | 3 | TSK-051 | 2 - SCD Type 2 | Analyze and document - Track customer changes | 1 | Not Started | 0% | 3
18 | 2026-09-24 | 3 | TSK-052 | 2 - SCD Type 2 | Design approach - Track customer changes | 1 | Not Started | 0% | 3
18 | 2026-09-24 | 3 | TSK-053 | 2 - SCD Type 2 | Implement SQL or artifact - Track customer changes | 1 | Not Started | 0% | 3
19 | 2026-09-25 | 3 | TSK-054 | 2 - SCD Type 2 | Create and execute tests - Track customer changes | 1 | Not Started | 0% | 3
19 | 2026-09-25 | 3 | TSK-055 | 2 - SCD Type 2 | Record evidence and decisions - Track customer changes | 0.5 | Not Started | 0% | 3
19 | 2026-09-25 | 3 | TSK-056 | 2 - SCD Type 2 | Analyze and document - Ignore non-changing records | 1 | Not Started | 0% | 3
19 | 2026-09-25 | 3 | TSK-057 | 2 - SCD Type 2 | Design approach - Ignore non-changing records | 0.5 | Not Started | 0% | 3
20 | 2026-09-28 | 2.5 | TSK-058 | 2 - SCD Type 2 | Implement SQL or artifact - Ignore non-changing records | 1.5 | Not Started | 0% | 2.5
20 | 2026-09-28 | 2.5 | TSK-059 | 2 - SCD Type 2 | Create and execute tests - Ignore non-changing records | 1 | Not Started | 0% | 2.5
21 | 2026-09-29 | 2.5 | TSK-060 | 2 - SCD Type 2 | Record evidence and decisions - Ignore non-changing records | 0.5 | Not Started | 0% | 2.5
21 | 2026-09-29 | 2.5 | TSK-061 | 2 - SCD Type 2 | Analyze and document - Handle new customers | 1 | Not Started | 0% | 2.5
21 | 2026-09-29 | 2.5 | TSK-062 | 2 - SCD Type 2 | Design approach - Handle new customers | 1 | Not Started | 0% | 2.5
22 | 2026-09-30 | 2.5 | TSK-063 | 2 - SCD Type 2 | Implement SQL or artifact - Handle new customers | 2 | Not Started | 0% | 2.5
22 | 2026-09-30 | 2.5 | TSK-064 | 2 - SCD Type 2 | Create and execute tests - Handle new customers | 0.5 | Not Started | 0% | 2.5
23 | 2026-10-01 | 2 | TSK-064 | 2 - SCD Type 2 | Create and execute tests - Handle new customers | 0.5 | Not Started | 0% | 2
23 | 2026-10-01 | 2 | TSK-065 | 2 - SCD Type 2 | Record evidence and decisions - Handle new customers | 0.5 | Not Started | 0% | 2
23 | 2026-10-01 | 2 | TSK-066 | 2 - SCD Type 2 | Analyze and document - Close prior version | 0.5 | Not Started | 0% | 2
23 | 2026-10-01 | 2 | TSK-067 | 2 - SCD Type 2 | Design approach - Close prior version | 0.5 | Not Started | 0% | 2
24 | 2026-10-02 | 2 | TSK-067 | 2 - SCD Type 2 | Design approach - Close prior version | 0.5 | Not Started | 0% | 2
24 | 2026-10-02 | 2 | TSK-068 | 2 - SCD Type 2 | Implement SQL or artifact - Close prior version | 1 | Not Started | 0% | 2
24 | 2026-10-02 | 2 | TSK-069 | 2 - SCD Type 2 | Create and execute tests - Close prior version | 0.5 | Not Started | 0% | 2
25 | 2026-10-05 | 2.5 | TSK-069 | 2 - SCD Type 2 | Create and execute tests - Close prior version | 0.5 | Not Started | 0% | 2.5
25 | 2026-10-05 | 2.5 | TSK-070 | 2 - SCD Type 2 | Record evidence and decisions - Close prior version | 0.5 | Not Started | 0% | 2.5
25 | 2026-10-05 | 2.5 | TSK-071 | 2 - SCD Type 2 | Analyze and document - Maintain current-row uniqueness | 0.5 | Not Started | 0% | 2.5
25 | 2026-10-05 | 2.5 | TSK-072 | 2 - SCD Type 2 | Design approach - Maintain current-row uniqueness | 1 | Not Started | 0% | 2.5
26 | 2026-10-06 | 3 | TSK-073 | 2 - SCD Type 2 | Implement SQL or artifact - Maintain current-row uniqueness | 1 | Not Started | 0% | 3
26 | 2026-10-06 | 3 | TSK-074 | 2 - SCD Type 2 | Create and execute tests - Maintain current-row uniqueness | 1 | Not Started | 0% | 3
26 | 2026-10-06 | 3 | TSK-075 | 2 - SCD Type 2 | Record evidence and decisions - Maintain current-row uniqueness | 0.5 | Not Started | 0% | 3
26 | 2026-10-06 | 3 | TSK-076 | 2 - SCD Type 2 | Analyze and document - Null-safe comparison | 0.5 | Not Started | 0% | 3
27 | 2026-10-07 | 3 | TSK-076 | 2 - SCD Type 2 | Analyze and document - Null-safe comparison | 0.5 | Not Started | 0% | 3
27 | 2026-10-07 | 3 | TSK-077 | 2 - SCD Type 2 | Design approach - Null-safe comparison | 1 | Not Started | 0% | 3
27 | 2026-10-07 | 3 | TSK-078 | 2 - SCD Type 2 | Implement SQL or artifact - Null-safe comparison | 1.5 | Not Started | 0% | 3
28 | 2026-10-08 | 2 | TSK-079 | 2 - SCD Type 2 | Create and execute tests - Null-safe comparison | 1 | Not Started | 0% | 2
28 | 2026-10-08 | 2 | TSK-080 | 2 - SCD Type 2 | Record evidence and decisions - Null-safe comparison | 0.5 | Not Started | 0% | 2
28 | 2026-10-08 | 2 | TSK-081 | 2 - SCD Type 2 | Analyze and document - Define late-arriving customer handling | 0.5 | Not Started | 0% | 2
29 | 2026-10-09 | 2 | TSK-082 | 2 - SCD Type 2 | Design approach - Define late-arriving customer handling | 1 | Not Started | 0% | 2
29 | 2026-10-09 | 2 | TSK-083 | 2 - SCD Type 2 | Implement SQL or artifact - Define late-arriving customer handling | 1 | Not Started | 0% | 2
30 | 2026-10-12 | 3 | TSK-083 | 2 - SCD Type 2 | Implement SQL or artifact - Define late-arriving customer handling | 0.5 | Not Started | 0% | 3
30 | 2026-10-12 | 3 | TSK-084 | 2 - SCD Type 2 | Create and execute tests - Define late-arriving customer handling | 1 | Not Started | 0% | 3
30 | 2026-10-12 | 3 | TSK-085 | 2 - SCD Type 2 | Record evidence and decisions - Define late-arriving customer handling | 0.5 | Not Started | 0% | 3
30 | 2026-10-12 | 3 | TSK-086 | 2 - SCD Type 2 | Analyze and document - Capture change metadata | 1 | Not Started | 0% | 3
31 | 2026-10-13 | 2 | TSK-087 | 2 - SCD Type 2 | Design approach - Capture change metadata | 1 | Not Started | 0% | 2
31 | 2026-10-13 | 2 | TSK-088 | 2 - SCD Type 2 | Implement SQL or artifact - Capture change metadata | 1 | Not Started | 0% | 2
32 | 2026-10-14 | 3 | TSK-088 | 2 - SCD Type 2 | Implement SQL or artifact - Capture change metadata | 1 | Not Started | 0% | 3
32 | 2026-10-14 | 3 | TSK-089 | 2 - SCD Type 2 | Create and execute tests - Capture change metadata | 1 | Not Started | 0% | 3
32 | 2026-10-14 | 3 | TSK-090 | 2 - SCD Type 2 | Record evidence and decisions - Capture change metadata | 0.5 | Not Started | 0% | 3
32 | 2026-10-14 | 3 | TSK-091 | 3 - Revenue Analytics | Analyze and document - Define revenue | 0.5 | Not Started | 0% | 3
33 | 2026-10-15 | 2.5 | TSK-091 | 3 - Revenue Analytics | Analyze and document - Define revenue | 0.5 | Not Started | 0% | 2.5
33 | 2026-10-15 | 2.5 | TSK-092 | 3 - Revenue Analytics | Design approach - Define revenue | 1 | Not Started | 0% | 2.5
33 | 2026-10-15 | 2.5 | TSK-093 | 3 - Revenue Analytics | Implement SQL or artifact - Define revenue | 1 | Not Started | 0% | 2.5
34 | 2026-10-16 | 2 | TSK-094 | 3 - Revenue Analytics | Create and execute tests - Define revenue | 1 | Not Started | 0% | 2
34 | 2026-10-16 | 2 | TSK-095 | 3 - Revenue Analytics | Record evidence and decisions - Define revenue | 0.5 | Not Started | 0% | 2
34 | 2026-10-16 | 2 | TSK-096 | 3 - Revenue Analytics | Analyze and document - Monthly customer revenue | 0.5 | Not Started | 0% | 2
35 | 2026-10-19 | 2.5 | TSK-097 | 3 - Revenue Analytics | Design approach - Monthly customer revenue | 0.5 | Not Started | 0% | 2.5
35 | 2026-10-19 | 2.5 | TSK-098 | 3 - Revenue Analytics | Implement SQL or artifact - Monthly customer revenue | 1.5 | Not Started | 0% | 2.5
35 | 2026-10-19 | 2.5 | TSK-099 | 3 - Revenue Analytics | Create and execute tests - Monthly customer revenue | 0.5 | Not Started | 0% | 2.5
36 | 2026-10-20 | 2 | TSK-099 | 3 - Revenue Analytics | Create and execute tests - Monthly customer revenue | 0.5 | Not Started | 0% | 2
36 | 2026-10-20 | 2 | TSK-100 | 3 - Revenue Analytics | Record evidence and decisions - Monthly customer revenue | 0.5 | Not Started | 0% | 2
36 | 2026-10-20 | 2 | TSK-101 | 3 - Revenue Analytics | Analyze and document - Previous month comparison | 1 | Not Started | 0% | 2
37 | 2026-10-21 | 2 | TSK-102 | 3 - Revenue Analytics | Design approach - Previous month comparison | 1 | Not Started | 0% | 2
37 | 2026-10-21 | 2 | TSK-103 | 3 - Revenue Analytics | Implement SQL or artifact - Previous month comparison | 1 | Not Started | 0% | 2
38 | 2026-10-22 | 2.5 | TSK-103 | 3 - Revenue Analytics | Implement SQL or artifact - Previous month comparison | 1 | Not Started | 0% | 2.5
38 | 2026-10-22 | 2.5 | TSK-104 | 3 - Revenue Analytics | Create and execute tests - Previous month comparison | 1 | Not Started | 0% | 2.5
38 | 2026-10-22 | 2.5 | TSK-105 | 3 - Revenue Analytics | Record evidence and decisions - Previous month comparison | 0.5 | Not Started | 0% | 2.5
39 | 2026-10-23 | 2.5 | TSK-106 | 3 - Revenue Analytics | Analyze and document - Growth percentage | 1 | Not Started | 0% | 2.5
39 | 2026-10-23 | 2.5 | TSK-107 | 3 - Revenue Analytics | Design approach - Growth percentage | 0.5 | Not Started | 0% | 2.5
39 | 2026-10-23 | 2.5 | TSK-108 | 3 - Revenue Analytics | Implement SQL or artifact - Growth percentage | 1 | Not Started | 0% | 2.5
40 | 2026-10-26 | 2 | TSK-109 | 3 - Revenue Analytics | Create and execute tests - Growth percentage | 1 | Not Started | 0% | 2
40 | 2026-10-26 | 2 | TSK-110 | 3 - Revenue Analytics | Record evidence and decisions - Growth percentage | 0.5 | Not Started | 0% | 2
40 | 2026-10-26 | 2 | TSK-111 | 3 - Revenue Analytics | Analyze and document - Zero-activity month handling | 0.5 | Not Started | 0% | 2
41 | 2026-10-27 | 2.5 | TSK-111 | 3 - Revenue Analytics | Analyze and document - Zero-activity month handling | 0.5 | Not Started | 0% | 2.5
41 | 2026-10-27 | 2.5 | TSK-112 | 3 - Revenue Analytics | Design approach - Zero-activity month handling | 1 | Not Started | 0% | 2.5
41 | 2026-10-27 | 2.5 | TSK-113 | 3 - Revenue Analytics | Implement SQL or artifact - Zero-activity month handling | 1 | Not Started | 0% | 2.5
42 | 2026-10-28 | 3 | TSK-114 | 3 - Revenue Analytics | Create and execute tests - Zero-activity month handling | 1 | Not Started | 0% | 3
42 | 2026-10-28 | 3 | TSK-115 | 3 - Revenue Analytics | Record evidence and decisions - Zero-activity month handling | 0.5 | Not Started | 0% | 3
42 | 2026-10-28 | 3 | TSK-116 | 3 - Revenue Analytics | Analyze and document - Revenue trend | 1 | Not Started | 0% | 3
42 | 2026-10-28 | 3 | TSK-117 | 3 - Revenue Analytics | Design approach - Revenue trend | 0.5 | Not Started | 0% | 3
43 | 2026-10-29 | 3 | TSK-117 | 3 - Revenue Analytics | Design approach - Revenue trend | 0.5 | Not Started | 0% | 3
43 | 2026-10-29 | 3 | TSK-118 | 3 - Revenue Analytics | Implement SQL or artifact - Revenue trend | 1 | Not Started | 0% | 3
43 | 2026-10-29 | 3 | TSK-119 | 3 - Revenue Analytics | Create and execute tests - Revenue trend | 1 | Not Started | 0% | 3
43 | 2026-10-29 | 3 | TSK-120 | 3 - Revenue Analytics | Record evidence and decisions - Revenue trend | 0.5 | Not Started | 0% | 3
44 | 2026-10-30 | 2.5 | TSK-121 | 3 - Revenue Analytics | Analyze and document - Reporting currency rule | 1 | Not Started | 0% | 2.5
44 | 2026-10-30 | 2.5 | TSK-122 | 3 - Revenue Analytics | Design approach - Reporting currency rule | 1 | Not Started | 0% | 2.5
44 | 2026-10-30 | 2.5 | TSK-123 | 3 - Revenue Analytics | Implement SQL or artifact - Reporting currency rule | 0.5 | Not Started | 0% | 2.5
45 | 2026-11-02 | 3 | TSK-123 | 3 - Revenue Analytics | Implement SQL or artifact - Reporting currency rule | 1 | Not Started | 0% | 3
45 | 2026-11-02 | 3 | TSK-124 | 3 - Revenue Analytics | Create and execute tests - Reporting currency rule | 1 | Not Started | 0% | 3
45 | 2026-11-02 | 3 | TSK-125 | 3 - Revenue Analytics | Record evidence and decisions - Reporting currency rule | 0.5 | Not Started | 0% | 3
45 | 2026-11-02 | 3 | TSK-126 | 4 - Deduplication | Analyze and document - Identify duplicate order events | 0.5 | Not Started | 0% | 3
46 | 2026-11-03 | 3 | TSK-127 | 4 - Deduplication | Design approach - Identify duplicate order events | 0.5 | Not Started | 0% | 3
46 | 2026-11-03 | 3 | TSK-128 | 4 - Deduplication | Implement SQL or artifact - Identify duplicate order events | 2 | Not Started | 0% | 3
46 | 2026-11-03 | 3 | TSK-129 | 4 - Deduplication | Create and execute tests - Identify duplicate order events | 0.5 | Not Started | 0% | 3
47 | 2026-11-04 | 3 | TSK-129 | 4 - Deduplication | Create and execute tests - Identify duplicate order events | 0.5 | Not Started | 0% | 3
47 | 2026-11-04 | 3 | TSK-130 | 4 - Deduplication | Record evidence and decisions - Identify duplicate order events | 0.5 | Not Started | 0% | 3
47 | 2026-11-04 | 3 | TSK-131 | 4 - Deduplication | Analyze and document - Define survivor rule | 1 | Not Started | 0% | 3
47 | 2026-11-04 | 3 | TSK-132 | 4 - Deduplication | Design approach - Define survivor rule | 1 | Not Started | 0% | 3
48 | 2026-11-05 | 2 | TSK-133 | 4 - Deduplication | Implement SQL or artifact - Define survivor rule | 2 | Not Started | 0% | 2
49 | 2026-11-06 | 3 | TSK-134 | 4 - Deduplication | Create and execute tests - Define survivor rule | 1 | Not Started | 0% | 3
49 | 2026-11-06 | 3 | TSK-135 | 4 - Deduplication | Record evidence and decisions - Define survivor rule | 0.5 | Not Started | 0% | 3
49 | 2026-11-06 | 3 | TSK-136 | 4 - Deduplication | Analyze and document - Implement ROW_NUMBER | 1 | Not Started | 0% | 3
49 | 2026-11-06 | 3 | TSK-137 | 4 - Deduplication | Design approach - Implement ROW_NUMBER | 0.5 | Not Started | 0% | 3
50 | 2026-11-09 | 3 | TSK-137 | 4 - Deduplication | Design approach - Implement ROW_NUMBER | 0.5 | Not Started | 0% | 3
50 | 2026-11-09 | 3 | TSK-138 | 4 - Deduplication | Implement SQL or artifact - Implement ROW_NUMBER | 1 | Not Started | 0% | 3
50 | 2026-11-09 | 3 | TSK-139 | 4 - Deduplication | Create and execute tests - Implement ROW_NUMBER | 1 | Not Started | 0% | 3
50 | 2026-11-09 | 3 | TSK-140 | 4 - Deduplication | Record evidence and decisions - Implement ROW_NUMBER | 0.5 | Not Started | 0% | 3
51 | 2026-11-10 | 2.5 | TSK-141 | 4 - Deduplication | Analyze and document - Quarantine rejected rows | 1 | Not Started | 0% | 2.5
51 | 2026-11-10 | 2.5 | TSK-142 | 4 - Deduplication | Design approach - Quarantine rejected rows | 0.5 | Not Started | 0% | 2.5
51 | 2026-11-10 | 2.5 | TSK-143 | 4 - Deduplication | Implement SQL or artifact - Quarantine rejected rows | 1 | Not Started | 0% | 2.5
52 | 2026-11-11 | 3 | TSK-144 | 4 - Deduplication | Create and execute tests - Quarantine rejected rows | 1 | Not Started | 0% | 3
52 | 2026-11-11 | 3 | TSK-145 | 4 - Deduplication | Record evidence and decisions - Quarantine rejected rows | 0.5 | Not Started | 0% | 3
52 | 2026-11-11 | 3 | TSK-146 | 4 - Deduplication | Analyze and document - Ensure idempotency | 1 | Not Started | 0% | 3
52 | 2026-11-11 | 3 | TSK-147 | 4 - Deduplication | Design approach - Ensure idempotency | 0.5 | Not Started | 0% | 3
53 | 2026-11-12 | 2 | TSK-148 | 4 - Deduplication | Implement SQL or artifact - Ensure idempotency | 2 | Not Started | 0% | 2
54 | 2026-11-13 | 2 | TSK-149 | 4 - Deduplication | Create and execute tests - Ensure idempotency | 1 | Not Started | 0% | 2
54 | 2026-11-13 | 2 | TSK-150 | 4 - Deduplication | Record evidence and decisions - Ensure idempotency | 0.5 | Not Started | 0% | 2
54 | 2026-11-13 | 2 | TSK-151 | 4 - Deduplication | Analyze and document - Handle exact ties | 0.5 | Not Started | 0% | 2
55 | 2026-11-16 | 2.5 | TSK-152 | 4 - Deduplication | Design approach - Handle exact ties | 1 | Not Started | 0% | 2.5
55 | 2026-11-16 | 2.5 | TSK-153 | 4 - Deduplication | Implement SQL or artifact - Handle exact ties | 1.5 | Not Started | 0% | 2.5
56 | 2026-11-17 | 2 | TSK-154 | 4 - Deduplication | Create and execute tests - Handle exact ties | 1 | Not Started | 0% | 2
56 | 2026-11-17 | 2 | TSK-155 | 4 - Deduplication | Record evidence and decisions - Handle exact ties | 0.5 | Not Started | 0% | 2
56 | 2026-11-17 | 2 | TSK-156 | 5 - Delivery Delay | Analyze and document - Define delivery duration | 0.5 | Not Started | 0% | 2
57 | 2026-11-18 | 2 | TSK-156 | 5 - Delivery Delay | Analyze and document - Define delivery duration | 0.5 | Not Started | 0% | 2
57 | 2026-11-18 | 2 | TSK-157 | 5 - Delivery Delay | Design approach - Define delivery duration | 1 | Not Started | 0% | 2
57 | 2026-11-18 | 2 | TSK-158 | 5 - Delivery Delay | Implement SQL or artifact - Define delivery duration | 0.5 | Not Started | 0% | 2
58 | 2026-11-19 | 3 | TSK-158 | 5 - Delivery Delay | Implement SQL or artifact - Define delivery duration | 1.5 | Not Started | 0% | 3
58 | 2026-11-19 | 3 | TSK-159 | 5 - Delivery Delay | Create and execute tests - Define delivery duration | 1 | Not Started | 0% | 3
58 | 2026-11-19 | 3 | TSK-160 | 5 - Delivery Delay | Record evidence and decisions - Define delivery duration | 0.5 | Not Started | 0% | 3
59 | 2026-11-20 | 3 | TSK-161 | 5 - Delivery Delay | Analyze and document - Identify late delivery | 1 | Not Started | 0% | 3
59 | 2026-11-20 | 3 | TSK-162 | 5 - Delivery Delay | Design approach - Identify late delivery | 0.5 | Not Started | 0% | 3
59 | 2026-11-20 | 3 | TSK-163 | 5 - Delivery Delay | Implement SQL or artifact - Identify late delivery | 1.5 | Not Started | 0% | 3
60 | 2026-11-23 | 2 | TSK-163 | 5 - Delivery Delay | Implement SQL or artifact - Identify late delivery | 0.5 | Not Started | 0% | 2
60 | 2026-11-23 | 2 | TSK-164 | 5 - Delivery Delay | Create and execute tests - Identify late delivery | 1 | Not Started | 0% | 2
60 | 2026-11-23 | 2 | TSK-165 | 5 - Delivery Delay | Record evidence and decisions - Identify late delivery | 0.5 | Not Started | 0% | 2
61 | 2026-11-24 | 2.5 | TSK-166 | 5 - Delivery Delay | Analyze and document - Create non-overlapping buckets | 1 | Not Started | 0% | 2.5
61 | 2026-11-24 | 2.5 | TSK-167 | 5 - Delivery Delay | Design approach - Create non-overlapping buckets | 1 | Not Started | 0% | 2.5
61 | 2026-11-24 | 2.5 | TSK-168 | 5 - Delivery Delay | Implement SQL or artifact - Create non-overlapping buckets | 0.5 | Not Started | 0% | 2.5
62 | 2026-11-25 | 2.5 | TSK-168 | 5 - Delivery Delay | Implement SQL or artifact - Create non-overlapping buckets | 0.5 | Not Started | 0% | 2.5
62 | 2026-11-25 | 2.5 | TSK-169 | 5 - Delivery Delay | Create and execute tests - Create non-overlapping buckets | 1 | Not Started | 0% | 2.5
62 | 2026-11-25 | 2.5 | TSK-170 | 5 - Delivery Delay | Record evidence and decisions - Create non-overlapping buckets | 0.5 | Not Started | 0% | 2.5
62 | 2026-11-25 | 2.5 | TSK-171 | 5 - Delivery Delay | Analyze and document - Handle undelivered shipments | 0.5 | Not Started | 0% | 2.5
63 | 2026-11-26 | 3 | TSK-172 | 5 - Delivery Delay | Design approach - Handle undelivered shipments | 1 | Not Started | 0% | 3
63 | 2026-11-26 | 3 | TSK-173 | 5 - Delivery Delay | Implement SQL or artifact - Handle undelivered shipments | 1 | Not Started | 0% | 3
63 | 2026-11-26 | 3 | TSK-174 | 5 - Delivery Delay | Create and execute tests - Handle undelivered shipments | 1 | Not Started | 0% | 3
64 | 2026-11-27 | 2 | TSK-175 | 5 - Delivery Delay | Record evidence and decisions - Handle undelivered shipments | 0.5 | Not Started | 0% | 2
64 | 2026-11-27 | 2 | TSK-176 | 5 - Delivery Delay | Analyze and document - Handle invalid chronology | 1 | Not Started | 0% | 2
64 | 2026-11-27 | 2 | TSK-177 | 5 - Delivery Delay | Design approach - Handle invalid chronology | 0.5 | Not Started | 0% | 2
65 | 2026-11-30 | 3 | TSK-177 | 5 - Delivery Delay | Design approach - Handle invalid chronology | 0.5 | Not Started | 0% | 3
65 | 2026-11-30 | 3 | TSK-178 | 5 - Delivery Delay | Implement SQL or artifact - Handle invalid chronology | 1 | Not Started | 0% | 3
65 | 2026-11-30 | 3 | TSK-179 | 5 - Delivery Delay | Create and execute tests - Handle invalid chronology | 1 | Not Started | 0% | 3
65 | 2026-11-30 | 3 | TSK-180 | 5 - Delivery Delay | Record evidence and decisions - Handle invalid chronology | 0.5 | Not Started | 0% | 3
66 | 2026-12-01 | 2.5 | TSK-181 | 5 - Delivery Delay | Analyze and document - Delay KPI output | 1 | Not Started | 0% | 2.5
66 | 2026-12-01 | 2.5 | TSK-182 | 5 - Delivery Delay | Design approach - Delay KPI output | 1 | Not Started | 0% | 2.5
66 | 2026-12-01 | 2.5 | TSK-183 | 5 - Delivery Delay | Implement SQL or artifact - Delay KPI output | 0.5 | Not Started | 0% | 2.5
67 | 2026-12-02 | 2 | TSK-183 | 5 - Delivery Delay | Implement SQL or artifact - Delay KPI output | 1.5 | Not Started | 0% | 2
67 | 2026-12-02 | 2 | TSK-184 | 5 - Delivery Delay | Create and execute tests - Delay KPI output | 0.5 | Not Started | 0% | 2
68 | 2026-12-03 | 3 | TSK-184 | 5 - Delivery Delay | Create and execute tests - Delay KPI output | 0.5 | Not Started | 0% | 3
68 | 2026-12-03 | 3 | TSK-185 | 5 - Delivery Delay | Record evidence and decisions - Delay KPI output | 0.5 | Not Started | 0% | 3
68 | 2026-12-03 | 3 | TSK-186 | 6 - Top Customers | Analyze and document - Rank within country | 0.5 | Not Started | 0% | 3
68 | 2026-12-03 | 3 | TSK-187 | 6 - Top Customers | Design approach - Rank within country | 0.5 | Not Started | 0% | 3
68 | 2026-12-03 | 3 | TSK-188 | 6 - Top Customers | Implement SQL or artifact - Rank within country | 1 | Not Started | 0% | 3
69 | 2026-12-04 | 3 | TSK-188 | 6 - Top Customers | Implement SQL or artifact - Rank within country | 0.5 | Not Started | 0% | 3
69 | 2026-12-04 | 3 | TSK-189 | 6 - Top Customers | Create and execute tests - Rank within country | 1 | Not Started | 0% | 3
69 | 2026-12-04 | 3 | TSK-190 | 6 - Top Customers | Record evidence and decisions - Rank within country | 0.5 | Not Started | 0% | 3
69 | 2026-12-04 | 3 | TSK-191 | 6 - Top Customers | Analyze and document - Top 10 per country | 1 | Not Started | 0% | 3
70 | 2026-12-07 | 2.5 | TSK-192 | 6 - Top Customers | Design approach - Top 10 per country | 0.5 | Not Started | 0% | 2.5
70 | 2026-12-07 | 2.5 | TSK-193 | 6 - Top Customers | Implement SQL or artifact - Top 10 per country | 2 | Not Started | 0% | 2.5
71 | 2026-12-08 | 3 | TSK-194 | 6 - Top Customers | Create and execute tests - Top 10 per country | 1 | Not Started | 0% | 3
71 | 2026-12-08 | 3 | TSK-195 | 6 - Top Customers | Record evidence and decisions - Top 10 per country | 0.5 | Not Started | 0% | 3
71 | 2026-12-08 | 3 | TSK-196 | 6 - Top Customers | Analyze and document - Define tie behavior | 0.5 | Not Started | 0% | 3
71 | 2026-12-08 | 3 | TSK-197 | 6 - Top Customers | Design approach - Define tie behavior | 0.5 | Not Started | 0% | 3
71 | 2026-12-08 | 3 | TSK-198 | 6 - Top Customers | Implement SQL or artifact - Define tie behavior | 0.5 | Not Started | 0% | 3
72 | 2026-12-09 | 2.5 | TSK-198 | 6 - Top Customers | Implement SQL or artifact - Define tie behavior | 1 | Not Started | 0% | 2.5
72 | 2026-12-09 | 2.5 | TSK-199 | 6 - Top Customers | Create and execute tests - Define tie behavior | 1 | Not Started | 0% | 2.5
72 | 2026-12-09 | 2.5 | TSK-200 | 6 - Top Customers | Record evidence and decisions - Define tie behavior | 0.5 | Not Started | 0% | 2.5
73 | 2026-12-10 | 2.5 | TSK-201 | 6 - Top Customers | Analyze and document - Use transaction-time geography | 0.5 | Not Started | 0% | 2.5
73 | 2026-12-10 | 2.5 | TSK-202 | 6 - Top Customers | Design approach - Use transaction-time geography | 0.5 | Not Started | 0% | 2.5
73 | 2026-12-10 | 2.5 | TSK-203 | 6 - Top Customers | Implement SQL or artifact - Use transaction-time geography | 1.5 | Not Started | 0% | 2.5
74 | 2026-12-11 | 2 | TSK-203 | 6 - Top Customers | Implement SQL or artifact - Use transaction-time geography | 0.5 | Not Started | 0% | 2
74 | 2026-12-11 | 2 | TSK-204 | 6 - Top Customers | Create and execute tests - Use transaction-time geography | 1 | Not Started | 0% | 2
74 | 2026-12-11 | 2 | TSK-205 | 6 - Top Customers | Record evidence and decisions - Use transaction-time geography | 0.5 | Not Started | 0% | 2
75 | 2026-12-14 | 2 | TSK-206 | 6 - Top Customers | Analyze and document - Parameterize period | 1 | Not Started | 0% | 2
75 | 2026-12-14 | 2 | TSK-207 | 6 - Top Customers | Design approach - Parameterize period | 1 | Not Started | 0% | 2
76 | 2026-12-15 | 3 | TSK-208 | 6 - Top Customers | Implement SQL or artifact - Parameterize period | 1 | Not Started | 0% | 3
76 | 2026-12-15 | 3 | TSK-209 | 6 - Top Customers | Create and execute tests - Parameterize period | 1 | Not Started | 0% | 3
76 | 2026-12-15 | 3 | TSK-210 | 6 - Top Customers | Record evidence and decisions - Parameterize period | 0.5 | Not Started | 0% | 3
76 | 2026-12-15 | 3 | TSK-211 | 7 - Incremental Load | Analyze and document - Create watermark table | 0.5 | Not Started | 0% | 3
77 | 2026-12-16 | 2.5 | TSK-212 | 7 - Incremental Load | Design approach - Create watermark table | 1 | Not Started | 0% | 2.5
77 | 2026-12-16 | 2.5 | TSK-213 | 7 - Incremental Load | Implement SQL or artifact - Create watermark table | 1.5 | Not Started | 0% | 2.5
78 | 2026-12-17 | 2.5 | TSK-214 | 7 - Incremental Load | Create and execute tests - Create watermark table | 1 | Not Started | 0% | 2.5
78 | 2026-12-17 | 2.5 | TSK-215 | 7 - Incremental Load | Record evidence and decisions - Create watermark table | 0.5 | Not Started | 0% | 2.5
78 | 2026-12-17 | 2.5 | TSK-216 | 7 - Incremental Load | Analyze and document - Read bounded source window | 1 | Not Started | 0% | 2.5
79 | 2026-12-18 | 2 | TSK-217 | 7 - Incremental Load | Design approach - Read bounded source window | 1 | Not Started | 0% | 2
79 | 2026-12-18 | 2 | TSK-218 | 7 - Incremental Load | Implement SQL or artifact - Read bounded source window | 1 | Not Started | 0% | 2
80 | 2026-12-21 | 2 | TSK-218 | 7 - Incremental Load | Implement SQL or artifact - Read bounded source window | 1 | Not Started | 0% | 2
80 | 2026-12-21 | 2 | TSK-219 | 7 - Incremental Load | Create and execute tests - Read bounded source window | 1 | Not Started | 0% | 2
81 | 2026-12-22 | 2.5 | TSK-220 | 7 - Incremental Load | Record evidence and decisions - Read bounded source window | 0.5 | Not Started | 0% | 2.5
81 | 2026-12-22 | 2.5 | TSK-221 | 7 - Incremental Load | Analyze and document - Advance only on success | 1 | Not Started | 0% | 2.5
81 | 2026-12-22 | 2.5 | TSK-222 | 7 - Incremental Load | Design approach - Advance only on success | 1 | Not Started | 0% | 2.5
82 | 2026-12-23 | 2 | TSK-223 | 7 - Incremental Load | Implement SQL or artifact - Advance only on success | 2 | Not Started | 0% | 2
83 | 2026-12-24 | 3 | TSK-224 | 7 - Incremental Load | Create and execute tests - Advance only on success | 1 | Not Started | 0% | 3
83 | 2026-12-24 | 3 | TSK-225 | 7 - Incremental Load | Record evidence and decisions - Advance only on success | 0.5 | Not Started | 0% | 3
83 | 2026-12-24 | 3 | TSK-226 | 7 - Incremental Load | Analyze and document - Support restart | 1 | Not Started | 0% | 3
83 | 2026-12-24 | 3 | TSK-227 | 7 - Incremental Load | Design approach - Support restart | 0.5 | Not Started | 0% | 3
84 | 2026-12-25 | 2.5 | TSK-227 | 7 - Incremental Load | Design approach - Support restart | 0.5 | Not Started | 0% | 2.5
84 | 2026-12-25 | 2.5 | TSK-228 | 7 - Incremental Load | Implement SQL or artifact - Support restart | 2 | Not Started | 0% | 2.5
85 | 2026-12-28 | 2 | TSK-229 | 7 - Incremental Load | Create and execute tests - Support restart | 1 | Not Started | 0% | 2
85 | 2026-12-28 | 2 | TSK-230 | 7 - Incremental Load | Record evidence and decisions - Support restart | 0.5 | Not Started | 0% | 2
85 | 2026-12-28 | 2 | TSK-231 | 7 - Incremental Load | Analyze and document - Persist batch metrics | 0.5 | Not Started | 0% | 2
86 | 2026-12-29 | 3 | TSK-231 | 7 - Incremental Load | Analyze and document - Persist batch metrics | 0.5 | Not Started | 0% | 3
86 | 2026-12-29 | 3 | TSK-232 | 7 - Incremental Load | Design approach - Persist batch metrics | 1 | Not Started | 0% | 3
86 | 2026-12-29 | 3 | TSK-233 | 7 - Incremental Load | Implement SQL or artifact - Persist batch metrics | 1.5 | Not Started | 0% | 3
87 | 2026-12-30 | 2.5 | TSK-234 | 7 - Incremental Load | Create and execute tests - Persist batch metrics | 1 | Not Started | 0% | 2.5
87 | 2026-12-30 | 2.5 | TSK-235 | 7 - Incremental Load | Record evidence and decisions - Persist batch metrics | 0.5 | Not Started | 0% | 2.5
87 | 2026-12-30 | 2.5 | TSK-236 | 7 - Incremental Load | Analyze and document - Define source-delete strategy | 0.5 | Not Started | 0% | 2.5
87 | 2026-12-30 | 2.5 | TSK-237 | 7 - Incremental Load | Design approach - Define source-delete strategy | 0.5 | Not Started | 0% | 2.5
88 | 2026-12-31 | 3 | TSK-238 | 7 - Incremental Load | Implement SQL or artifact - Define source-delete strategy | 1.5 | Not Started | 0% | 3
88 | 2026-12-31 | 3 | TSK-239 | 7 - Incremental Load | Create and execute tests - Define source-delete strategy | 1 | Not Started | 0% | 3
88 | 2026-12-31 | 3 | TSK-240 | 7 - Incremental Load | Record evidence and decisions - Define source-delete strategy | 0.5 | Not Started | 0% | 3
89 | 2027-01-01 | 3 | TSK-241 | 7 - Incremental Load | Analyze and document - Apply lookback window | 1 | Not Started | 0% | 3
89 | 2027-01-01 | 3 | TSK-242 | 7 - Incremental Load | Design approach - Apply lookback window | 0.5 | Not Started | 0% | 3
89 | 2027-01-01 | 3 | TSK-243 | 7 - Incremental Load | Implement SQL or artifact - Apply lookback window | 1.5 | Not Started | 0% | 3
90 | 2027-01-04 | 2.5 | TSK-243 | 7 - Incremental Load | Implement SQL or artifact - Apply lookback window | 0.5 | Not Started | 0% | 2.5
90 | 2027-01-04 | 2.5 | TSK-244 | 7 - Incremental Load | Create and execute tests - Apply lookback window | 1 | Not Started | 0% | 2.5
90 | 2027-01-04 | 2.5 | TSK-245 | 7 - Incremental Load | Record evidence and decisions - Apply lookback window | 0.5 | Not Started | 0% | 2.5
90 | 2027-01-04 | 2.5 | TSK-246 | 7 - Incremental Load | Analyze and document - Prevent overlapping runs | 0.5 | Not Started | 0% | 2.5
91 | 2027-01-05 | 3 | TSK-247 | 7 - Incremental Load | Design approach - Prevent overlapping runs | 1 | Not Started | 0% | 3
91 | 2027-01-05 | 3 | TSK-248 | 7 - Incremental Load | Implement SQL or artifact - Prevent overlapping runs | 2 | Not Started | 0% | 3
92 | 2027-01-06 | 2 | TSK-249 | 7 - Incremental Load | Create and execute tests - Prevent overlapping runs | 1 | Not Started | 0% | 2
92 | 2027-01-06 | 2 | TSK-250 | 7 - Incremental Load | Record evidence and decisions - Prevent overlapping runs | 0.5 | Not Started | 0% | 2
92 | 2027-01-06 | 2 | TSK-251 | 7 - Incremental Load | Analyze and document - Create operational logging | 0.5 | Not Started | 0% | 2
93 | 2027-01-07 | 2 | TSK-252 | 7 - Incremental Load | Design approach - Create operational logging | 0.5 | Not Started | 0% | 2
93 | 2027-01-07 | 2 | TSK-253 | 7 - Incremental Load | Implement SQL or artifact - Create operational logging | 1.5 | Not Started | 0% | 2
94 | 2027-01-08 | 2 | TSK-254 | 7 - Incremental Load | Create and execute tests - Create operational logging | 1 | Not Started | 0% | 2
94 | 2027-01-08 | 2 | TSK-255 | 7 - Incremental Load | Record evidence and decisions - Create operational logging | 0.5 | Not Started | 0% | 2
94 | 2027-01-08 | 2 | TSK-256 | 8 - Performance Tuning | Analyze and document - Capture baseline | 0.5 | Not Started | 0% | 2
95 | 2027-01-11 | 3 | TSK-257 | 8 - Performance Tuning | Design approach - Capture baseline | 1 | Not Started | 0% | 3
95 | 2027-01-11 | 3 | TSK-258 | 8 - Performance Tuning | Implement SQL or artifact - Capture baseline | 2 | Not Started | 0% | 3
96 | 2027-01-12 | 2 | TSK-259 | 8 - Performance Tuning | Create and execute tests - Capture baseline | 1 | Not Started | 0% | 2
96 | 2027-01-12 | 2 | TSK-260 | 8 - Performance Tuning | Record evidence and decisions - Capture baseline | 0.5 | Not Started | 0% | 2
96 | 2027-01-12 | 2 | TSK-261 | 8 - Performance Tuning | Analyze and document - Design clustered strategy | 0.5 | Not Started | 0% | 2
97 | 2027-01-13 | 3 | TSK-261 | 8 - Performance Tuning | Analyze and document - Design clustered strategy | 0.5 | Not Started | 0% | 3
97 | 2027-01-13 | 3 | TSK-262 | 8 - Performance Tuning | Design approach - Design clustered strategy | 0.5 | Not Started | 0% | 3
97 | 2027-01-13 | 3 | TSK-263 | 8 - Performance Tuning | Implement SQL or artifact - Design clustered strategy | 2 | Not Started | 0% | 3
98 | 2027-01-14 | 2 | TSK-264 | 8 - Performance Tuning | Create and execute tests - Design clustered strategy | 1 | Not Started | 0% | 2
98 | 2027-01-14 | 2 | TSK-265 | 8 - Performance Tuning | Record evidence and decisions - Design clustered strategy | 0.5 | Not Started | 0% | 2
98 | 2027-01-14 | 2 | TSK-266 | 8 - Performance Tuning | Analyze and document - Design covering indexes | 0.5 | Not Started | 0% | 2
99 | 2027-01-15 | 2.5 | TSK-266 | 8 - Performance Tuning | Analyze and document - Design covering indexes | 0.5 | Not Started | 0% | 2.5
99 | 2027-01-15 | 2.5 | TSK-267 | 8 - Performance Tuning | Design approach - Design covering indexes | 0.5 | Not Started | 0% | 2.5
99 | 2027-01-15 | 2.5 | TSK-268 | 8 - Performance Tuning | Implement SQL or artifact - Design covering indexes | 1.5 | Not Started | 0% | 2.5
100 | 2027-01-18 | 3 | TSK-269 | 8 - Performance Tuning | Create and execute tests - Design covering indexes | 1 | Not Started | 0% | 3
100 | 2027-01-18 | 3 | TSK-270 | 8 - Performance Tuning | Record evidence and decisions - Design covering indexes | 0.5 | Not Started | 0% | 3
100 | 2027-01-18 | 3 | TSK-271 | 8 - Performance Tuning | Analyze and document - Evaluate date partitioning | 0.5 | Not Started | 0% | 3
100 | 2027-01-18 | 3 | TSK-272 | 8 - Performance Tuning | Design approach - Evaluate date partitioning | 0.5 | Not Started | 0% | 3
100 | 2027-01-18 | 3 | TSK-273 | 8 - Performance Tuning | Implement SQL or artifact - Evaluate date partitioning | 0.5 | Not Started | 0% | 3
101 | 2027-01-19 | 3 | TSK-273 | 8 - Performance Tuning | Implement SQL or artifact - Evaluate date partitioning | 1.5 | Not Started | 0% | 3
101 | 2027-01-19 | 3 | TSK-274 | 8 - Performance Tuning | Create and execute tests - Evaluate date partitioning | 1 | Not Started | 0% | 3
101 | 2027-01-19 | 3 | TSK-275 | 8 - Performance Tuning | Record evidence and decisions - Evaluate date partitioning | 0.5 | Not Started | 0% | 3
102 | 2027-01-20 | 2 | TSK-276 | 8 - Performance Tuning | Analyze and document - Remove non-sargable predicates | 1 | Not Started | 0% | 2
102 | 2027-01-20 | 2 | TSK-277 | 8 - Performance Tuning | Design approach - Remove non-sargable predicates | 1 | Not Started | 0% | 2
103 | 2027-01-21 | 2.5 | TSK-278 | 8 - Performance Tuning | Implement SQL or artifact - Remove non-sargable predicates | 1.5 | Not Started | 0% | 2.5
103 | 2027-01-21 | 2.5 | TSK-279 | 8 - Performance Tuning | Create and execute tests - Remove non-sargable predicates | 1 | Not Started | 0% | 2.5
104 | 2027-01-22 | 2 | TSK-280 | 8 - Performance Tuning | Record evidence and decisions - Remove non-sargable predicates | 0.5 | Not Started | 0% | 2
104 | 2027-01-22 | 2 | TSK-281 | 8 - Performance Tuning | Analyze and document - Maintain statistics | 1 | Not Started | 0% | 2
104 | 2027-01-22 | 2 | TSK-282 | 8 - Performance Tuning | Design approach - Maintain statistics | 0.5 | Not Started | 0% | 2
105 | 2027-01-25 | 2 | TSK-282 | 8 - Performance Tuning | Design approach - Maintain statistics | 0.5 | Not Started | 0% | 2
105 | 2027-01-25 | 2 | TSK-283 | 8 - Performance Tuning | Implement SQL or artifact - Maintain statistics | 1.5 | Not Started | 0% | 2
106 | 2027-01-26 | 2.5 | TSK-283 | 8 - Performance Tuning | Implement SQL or artifact - Maintain statistics | 0.5 | Not Started | 0% | 2.5
106 | 2027-01-26 | 2.5 | TSK-284 | 8 - Performance Tuning | Create and execute tests - Maintain statistics | 1 | Not Started | 0% | 2.5
106 | 2027-01-26 | 2.5 | TSK-285 | 8 - Performance Tuning | Record evidence and decisions - Maintain statistics | 0.5 | Not Started | 0% | 2.5
106 | 2027-01-26 | 2.5 | TSK-286 | 8 - Performance Tuning | Analyze and document - Create summary table | 0.5 | Not Started | 0% | 2.5
107 | 2027-01-27 | 2.5 | TSK-286 | 8 - Performance Tuning | Analyze and document - Create summary table | 0.5 | Not Started | 0% | 2.5
107 | 2027-01-27 | 2.5 | TSK-287 | 8 - Performance Tuning | Design approach - Create summary table | 1 | Not Started | 0% | 2.5
107 | 2027-01-27 | 2.5 | TSK-288 | 8 - Performance Tuning | Implement SQL or artifact - Create summary table | 1 | Not Started | 0% | 2.5
108 | 2027-01-28 | 2 | TSK-288 | 8 - Performance Tuning | Implement SQL or artifact - Create summary table | 0.5 | Not Started | 0% | 2
108 | 2027-01-28 | 2 | TSK-289 | 8 - Performance Tuning | Create and execute tests - Create summary table | 1 | Not Started | 0% | 2
108 | 2027-01-28 | 2 | TSK-290 | 8 - Performance Tuning | Record evidence and decisions - Create summary table | 0.5 | Not Started | 0% | 2
109 | 2027-01-29 | 2.5 | TSK-291 | 8 - Performance Tuning | Analyze and document - Detect skew and parameter issues | 0.5 | Not Started | 0% | 2.5
109 | 2027-01-29 | 2.5 | TSK-292 | 8 - Performance Tuning | Design approach - Detect skew and parameter issues | 0.5 | Not Started | 0% | 2.5
109 | 2027-01-29 | 2.5 | TSK-293 | 8 - Performance Tuning | Implement SQL or artifact - Detect skew and parameter issues | 1.5 | Not Started | 0% | 2.5
110 | 2027-02-01 | 2 | TSK-293 | 8 - Performance Tuning | Implement SQL or artifact - Detect skew and parameter issues | 0.5 | Not Started | 0% | 2
110 | 2027-02-01 | 2 | TSK-294 | 8 - Performance Tuning | Create and execute tests - Detect skew and parameter issues | 1 | Not Started | 0% | 2
110 | 2027-02-01 | 2 | TSK-295 | 8 - Performance Tuning | Record evidence and decisions - Detect skew and parameter issues | 0.5 | Not Started | 0% | 2
111 | 2027-02-02 | 3 | TSK-296 | 8 - Performance Tuning | Analyze and document - Compare before and after | 1 | Not Started | 0% | 3
111 | 2027-02-02 | 3 | TSK-297 | 8 - Performance Tuning | Design approach - Compare before and after | 0.5 | Not Started | 0% | 3
111 | 2027-02-02 | 3 | TSK-298 | 8 - Performance Tuning | Implement SQL or artifact - Compare before and after | 1.5 | Not Started | 0% | 3
112 | 2027-02-03 | 2 | TSK-299 | 8 - Performance Tuning | Create and execute tests - Compare before and after | 1 | Not Started | 0% | 2
112 | 2027-02-03 | 2 | TSK-300 | 8 - Performance Tuning | Record evidence and decisions - Compare before and after | 0.5 | Not Started | 0% | 2
112 | 2027-02-03 | 2 | TSK-301 | 9 - Reconciliation & RCA | Analyze and document - Build source-to-target control totals | 0.5 | Not Started | 0% | 2
113 | 2027-02-04 | 3 | TSK-302 | 9 - Reconciliation & RCA | Design approach - Build source-to-target control totals | 1 | Not Started | 0% | 3
113 | 2027-02-04 | 3 | TSK-303 | 9 - Reconciliation & RCA | Implement SQL or artifact - Build source-to-target control totals | 2 | Not Started | 0% | 3
114 | 2027-02-05 | 2 | TSK-304 | 9 - Reconciliation & RCA | Create and execute tests - Build source-to-target control totals | 1 | Not Started | 0% | 2
114 | 2027-02-05 | 2 | TSK-305 | 9 - Reconciliation & RCA | Record evidence and decisions - Build source-to-target control totals | 0.5 | Not Started | 0% | 2
114 | 2027-02-05 | 2 | TSK-306 | 9 - Reconciliation & RCA | Analyze and document - Investigate revenue restatement | 0.5 | Not Started | 0% | 2
115 | 2027-02-08 | 2.5 | TSK-306 | 9 - Reconciliation & RCA | Analyze and document - Investigate revenue restatement | 0.5 | Not Started | 0% | 2.5
115 | 2027-02-08 | 2.5 | TSK-307 | 9 - Reconciliation & RCA | Design approach - Investigate revenue restatement | 1 | Not Started | 0% | 2.5
115 | 2027-02-08 | 2.5 | TSK-308 | 9 - Reconciliation & RCA | Implement SQL or artifact - Investigate revenue restatement | 1 | Not Started | 0% | 2.5
116 | 2027-02-09 | 3 | TSK-309 | 9 - Reconciliation & RCA | Create and execute tests - Investigate revenue restatement | 1 | Not Started | 0% | 3
116 | 2027-02-09 | 3 | TSK-310 | 9 - Reconciliation & RCA | Record evidence and decisions - Investigate revenue restatement | 0.5 | Not Started | 0% | 3
116 | 2027-02-09 | 3 | TSK-311 | 9 - Reconciliation & RCA | Analyze and document - Classify variances | 0.5 | Not Started | 0% | 3
116 | 2027-02-09 | 3 | TSK-312 | 9 - Reconciliation & RCA | Design approach - Classify variances | 1 | Not Started | 0% | 3
117 | 2027-02-10 | 2.5 | TSK-313 | 9 - Reconciliation & RCA | Implement SQL or artifact - Classify variances | 1.5 | Not Started | 0% | 2.5
117 | 2027-02-10 | 2.5 | TSK-314 | 9 - Reconciliation & RCA | Create and execute tests - Classify variances | 1 | Not Started | 0% | 2.5
118 | 2027-02-11 | 3 | TSK-315 | 9 - Reconciliation & RCA | Record evidence and decisions - Classify variances | 0.5 | Not Started | 0% | 3
118 | 2027-02-11 | 3 | TSK-316 | 9 - Reconciliation & RCA | Analyze and document - Create lineage evidence | 1 | Not Started | 0% | 3
118 | 2027-02-11 | 3 | TSK-317 | 9 - Reconciliation & RCA | Design approach - Create lineage evidence | 0.5 | Not Started | 0% | 3
118 | 2027-02-11 | 3 | TSK-318 | 9 - Reconciliation & RCA | Implement SQL or artifact - Create lineage evidence | 1 | Not Started | 0% | 3
119 | 2027-02-12 | 3 | TSK-319 | 9 - Reconciliation & RCA | Create and execute tests - Create lineage evidence | 1 | Not Started | 0% | 3
119 | 2027-02-12 | 3 | TSK-320 | 9 - Reconciliation & RCA | Record evidence and decisions - Create lineage evidence | 0.5 | Not Started | 0% | 3
119 | 2027-02-12 | 3 | TSK-321 | 9 - Reconciliation & RCA | Analyze and document - Set reconciliation thresholds | 1 | Not Started | 0% | 3
119 | 2027-02-12 | 3 | TSK-322 | 9 - Reconciliation & RCA | Design approach - Set reconciliation thresholds | 0.5 | Not Started | 0% | 3
120 | 2027-02-15 | 2 | TSK-322 | 9 - Reconciliation & RCA | Design approach - Set reconciliation thresholds | 0.5 | Not Started | 0% | 2
120 | 2027-02-15 | 2 | TSK-323 | 9 - Reconciliation & RCA | Implement SQL or artifact - Set reconciliation thresholds | 1.5 | Not Started | 0% | 2
121 | 2027-02-16 | 2 | TSK-324 | 9 - Reconciliation & RCA | Create and execute tests - Set reconciliation thresholds | 1 | Not Started | 0% | 2
121 | 2027-02-16 | 2 | TSK-325 | 9 - Reconciliation & RCA | Record evidence and decisions - Set reconciliation thresholds | 0.5 | Not Started | 0% | 2
121 | 2027-02-16 | 2 | TSK-326 | 9 - Reconciliation & RCA | Analyze and document - Create support runbook | 0.5 | Not Started | 0% | 2
122 | 2027-02-17 | 2 | TSK-326 | 9 - Reconciliation & RCA | Analyze and document - Create support runbook | 0.5 | Not Started | 0% | 2
122 | 2027-02-17 | 2 | TSK-327 | 9 - Reconciliation & RCA | Design approach - Create support runbook | 1 | Not Started | 0% | 2
122 | 2027-02-17 | 2 | TSK-328 | 9 - Reconciliation & RCA | Implement SQL or artifact - Create support runbook | 0.5 | Not Started | 0% | 2
123 | 2027-02-18 | 2 | TSK-328 | 9 - Reconciliation & RCA | Implement SQL or artifact - Create support runbook | 1.5 | Not Started | 0% | 2
123 | 2027-02-18 | 2 | TSK-329 | 9 - Reconciliation & RCA | Create and execute tests - Create support runbook | 0.5 | Not Started | 0% | 2
124 | 2027-02-19 | 2.5 | TSK-329 | 9 - Reconciliation & RCA | Create and execute tests - Create support runbook | 0.5 | Not Started | 0% | 2.5
124 | 2027-02-19 | 2.5 | TSK-330 | 9 - Reconciliation & RCA | Record evidence and decisions - Create support runbook | 0.5 | Not Started | 0% | 2.5
124 | 2027-02-19 | 2.5 | TSK-331 | 10 - Packaging & Portfolio | Analyze and document - Organize source control | 1 | Not Started | 0% | 2.5
124 | 2027-02-19 | 2.5 | TSK-332 | 10 - Packaging & Portfolio | Design approach - Organize source control | 0.5 | Not Started | 0% | 2.5
125 | 2027-02-22 | 2 | TSK-333 | 10 - Packaging & Portfolio | Implement SQL or artifact - Organize source control | 1 | Not Started | 0% | 2
125 | 2027-02-22 | 2 | TSK-334 | 10 - Packaging & Portfolio | Create and execute tests - Organize source control | 1 | Not Started | 0% | 2
126 | 2027-02-23 | 2 | TSK-335 | 10 - Packaging & Portfolio | Record evidence and decisions - Organize source control | 0.5 | Not Started | 0% | 2
126 | 2027-02-23 | 2 | TSK-336 | 10 - Packaging & Portfolio | Analyze and document - Create deployment order | 0.5 | Not Started | 0% | 2
126 | 2027-02-23 | 2 | TSK-337 | 10 - Packaging & Portfolio | Design approach - Create deployment order | 1 | Not Started | 0% | 2
127 | 2027-02-24 | 3 | TSK-338 | 10 - Packaging & Portfolio | Implement SQL or artifact - Create deployment order | 2 | Not Started | 0% | 3
127 | 2027-02-24 | 3 | TSK-339 | 10 - Packaging & Portfolio | Create and execute tests - Create deployment order | 1 | Not Started | 0% | 3
128 | 2027-02-25 | 2.5 | TSK-340 | 10 - Packaging & Portfolio | Record evidence and decisions - Create deployment order | 0.5 | Not Started | 0% | 2.5
128 | 2027-02-25 | 2.5 | TSK-341 | 10 - Packaging & Portfolio | Analyze and document - Create architecture document | 1 | Not Started | 0% | 2.5
128 | 2027-02-25 | 2.5 | TSK-342 | 10 - Packaging & Portfolio | Design approach - Create architecture document | 1 | Not Started | 0% | 2.5
129 | 2027-02-26 | 2.5 | TSK-343 | 10 - Packaging & Portfolio | Implement SQL or artifact - Create architecture document | 1 | Not Started | 0% | 2.5
129 | 2027-02-26 | 2.5 | TSK-344 | 10 - Packaging & Portfolio | Create and execute tests - Create architecture document | 1 | Not Started | 0% | 2.5
129 | 2027-02-26 | 2.5 | TSK-345 | 10 - Packaging & Portfolio | Record evidence and decisions - Create architecture document | 0.5 | Not Started | 0% | 2.5
130 | 2027-03-01 | 3 | TSK-346 | 10 - Packaging & Portfolio | Analyze and document - Capture test evidence | 1 | Not Started | 0% | 3
130 | 2027-03-01 | 3 | TSK-347 | 10 - Packaging & Portfolio | Design approach - Capture test evidence | 1 | Not Started | 0% | 3
130 | 2027-03-01 | 3 | TSK-348 | 10 - Packaging & Portfolio | Implement SQL or artifact - Capture test evidence | 1 | Not Started | 0% | 3
131 | 2027-03-02 | 3 | TSK-348 | 10 - Packaging & Portfolio | Implement SQL or artifact - Capture test evidence | 1 | Not Started | 0% | 3
131 | 2027-03-02 | 3 | TSK-349 | 10 - Packaging & Portfolio | Create and execute tests - Capture test evidence | 1 | Not Started | 0% | 3
131 | 2027-03-02 | 3 | TSK-350 | 10 - Packaging & Portfolio | Record evidence and decisions - Capture test evidence | 0.5 | Not Started | 0% | 3
131 | 2027-03-02 | 3 | TSK-351 | 10 - Packaging & Portfolio | Analyze and document - Capture performance evidence | 0.5 | Not Started | 0% | 3
132 | 2027-03-03 | 2 | TSK-351 | 10 - Packaging & Portfolio | Analyze and document - Capture performance evidence | 0.5 | Not Started | 0% | 2
132 | 2027-03-03 | 2 | TSK-352 | 10 - Packaging & Portfolio | Design approach - Capture performance evidence | 0.5 | Not Started | 0% | 2
132 | 2027-03-03 | 2 | TSK-353 | 10 - Packaging & Portfolio | Implement SQL or artifact - Capture performance evidence | 1 | Not Started | 0% | 2
133 | 2027-03-04 | 2.5 | TSK-354 | 10 - Packaging & Portfolio | Create and execute tests - Capture performance evidence | 1 | Not Started | 0% | 2.5
133 | 2027-03-04 | 2.5 | TSK-355 | 10 - Packaging & Portfolio | Record evidence and decisions - Capture performance evidence | 0.5 | Not Started | 0% | 2.5
133 | 2027-03-04 | 2.5 | TSK-356 | 10 - Packaging & Portfolio | Analyze and document - Prepare honest resume wording | 0.5 | Not Started | 0% | 2.5
133 | 2027-03-04 | 2.5 | TSK-357 | 10 - Packaging & Portfolio | Design approach - Prepare honest resume wording | 0.5 | Not Started | 0% | 2.5
134 | 2027-03-05 | 2 | TSK-357 | 10 - Packaging & Portfolio | Design approach - Prepare honest resume wording | 0.5 | Not Started | 0% | 2
134 | 2027-03-05 | 2 | TSK-358 | 10 - Packaging & Portfolio | Implement SQL or artifact - Prepare honest resume wording | 1 | Not Started | 0% | 2
134 | 2027-03-05 | 2 | TSK-359 | 10 - Packaging & Portfolio | Create and execute tests - Prepare honest resume wording | 0.5 | Not Started | 0% | 2
135 | 2027-03-08 | 3 | TSK-359 | 10 - Packaging & Portfolio | Create and execute tests - Prepare honest resume wording | 0.5 | Not Started | 0% | 3
135 | 2027-03-08 | 3 | TSK-360 | 10 - Packaging & Portfolio | Record evidence and decisions - Prepare honest resume wording | 0.5 | Not Started | 0% | 3
135 | 2027-03-08 | 3 | TSK-361 | 10 - Packaging & Portfolio | Analyze and document - Prepare design defense | 1 | Not Started | 0% | 3
135 | 2027-03-08 | 3 | TSK-362 | 10 - Packaging & Portfolio | Design approach - Prepare design defense | 0.5 | Not Started | 0% | 3
135 | 2027-03-08 | 3 | TSK-363 | 10 - Packaging & Portfolio | Implement SQL or artifact - Prepare design defense | 0.5 | Not Started | 0% | 3
136 | 2027-03-09 | 2 | TSK-363 | 10 - Packaging & Portfolio | Implement SQL or artifact - Prepare design defense | 1.5 | Not Started | 0% | 2
136 | 2027-03-09 | 2 | TSK-364 | 10 - Packaging & Portfolio | Create and execute tests - Prepare design defense | 0.5 | Not Started | 0% | 2
137 | 2027-03-10 | 2.5 | TSK-364 | 10 - Packaging & Portfolio | Create and execute tests - Prepare design defense | 0.5 | Not Started | 0% | 1
137 | 2027-03-10 | 2.5 | TSK-365 | 10 - Packaging & Portfolio | Record evidence and decisions - Prepare design defense | 0.5 | Not Started | 0% | 1

## Test Cases
Detailed Test Cases and Evidence Tracker
Test Case ID | Phase | Test Area | Scenario | Preconditions / Test Data | Execution Steps | Expected Result | Severity | Status | Actual Result | Evidence Reference | Defect / Notes
TC-001 | 1 - Warehouse Modeling | Business | Confirm analytical scope | Related object for REQ-001 is deployed | Prepare minimum data for Confirm analytical scope; execute relevant SQL; compare actual result with acceptance criteria. | Scope explicitly lists included metrics and excluded scenarios. | Critical | Not Run
TC-002 | 1 - Warehouse Modeling | Modeling | Declare FactOrders grain | Related object for REQ-002 is deployed | Prepare minimum data for Declare FactOrders grain; execute relevant SQL; compare actual result with acceptance criteria. | Grain statement is written before table design and every fact column conforms to it. | Critical | Not Run
TC-003 | 1 - Warehouse Modeling | Modeling | Declare FactShipment grain | Related object for REQ-003 is deployed | Prepare minimum data for Declare FactShipment grain; execute relevant SQL; compare actual result with acceptance criteria. | Grain and business key are unambiguous. | Critical | Not Run
TC-004 | 1 - Warehouse Modeling | Modeling | Design star schema | Related object for REQ-004 is deployed | Prepare minimum data for Design star schema; execute relevant SQL; compare actual result with acceptance criteria. | Diagram shows PK/FK relationships and no unresolved many-to-many relationship. | Critical | Not Run
TC-005 | 1 - Warehouse Modeling | Keys | Use surrogate keys | Related object for REQ-005 is deployed | Prepare minimum data for Use surrogate keys; execute relevant SQL; compare actual result with acceptance criteria. | Facts reference surrogate keys; source keys remain available for traceability. | Critical | Not Run
TC-006 | 1 - Warehouse Modeling | Keys | Create unknown members | Related object for REQ-006 is deployed | Prepare minimum data for Create unknown members; execute relevant SQL; compare actual result with acceptance criteria. | Unmatched source rows load without null dimension foreign keys and are reportable. | Critical | Not Run
TC-007 | 1 - Warehouse Modeling | Data | Define additive measures | Related object for REQ-007 is deployed | Prepare minimum data for Define additive measures; execute relevant SQL; compare actual result with acceptance criteria. | Each measure has a definition and aggregation behavior. | Medium | Not Run
TC-008 | 1 - Warehouse Modeling | Audit | Add audit columns | Related object for REQ-008 is deployed | Prepare minimum data for Add audit columns; execute relevant SQL; compare actual result with acceptance criteria. | Every loaded row can be traced to a batch and source. | Critical | Not Run
TC-009 | 1 - Warehouse Modeling | Modeling | Role-playing date dimensions | Related object for REQ-009 is deployed | Prepare minimum data for Role-playing date dimensions; execute relevant SQL; compare actual result with acceptance criteria. | Date roles are clear and joins return correct calendar attributes. | Critical | Not Run
TC-010 | 1 - Warehouse Modeling | Data Quality | Enforce key integrity | Related object for REQ-010 is deployed | Prepare minimum data for Enforce key integrity; execute relevant SQL; compare actual result with acceptance criteria. | Duplicate dimension business keys and orphan fact keys are detected. | Medium | Not Run
TC-011 | 2 - SCD Type 2 | History | Track customer changes | Related object for REQ-011 is deployed | Prepare minimum data for Track customer changes; execute relevant SQL; compare actual result with acceptance criteria. | A changed tracked attribute expires the old row and creates one new current row. | Critical | Not Run
TC-012 | 2 - SCD Type 2 | History | Ignore non-changing records | Related object for REQ-012 is deployed | Prepare minimum data for Ignore non-changing records; execute relevant SQL; compare actual result with acceptance criteria. | Reprocessing identical source produces no extra versions. | Critical | Not Run
TC-013 | 2 - SCD Type 2 | History | Handle new customers | Related object for REQ-013 is deployed | Prepare minimum data for Handle new customers; execute relevant SQL; compare actual result with acceptance criteria. | New business key has exactly one current row. | Critical | Not Run
TC-014 | 2 - SCD Type 2 | History | Close prior version | Related object for REQ-014 is deployed | Prepare minimum data for Close prior version; execute relevant SQL; compare actual result with acceptance criteria. | No overlap exists in effective date ranges. | Critical | Not Run
TC-015 | 2 - SCD Type 2 | History | Maintain current-row uniqueness | Related object for REQ-015 is deployed | Prepare minimum data for Maintain current-row uniqueness; execute relevant SQL; compare actual result with acceptance criteria. | Uniqueness test returns zero violations. | Critical | Not Run
TC-016 | 2 - SCD Type 2 | History | Null-safe comparison | Related object for REQ-016 is deployed | Prepare minimum data for Null-safe comparison; execute relevant SQL; compare actual result with acceptance criteria. | All null transition tests pass. | Critical | Not Run
TC-017 | 2 - SCD Type 2 | Late Data | Define late-arriving customer handling | Related object for REQ-017 is deployed | Prepare minimum data for Define late-arriving customer handling; execute relevant SQL; compare actual result with acceptance criteria. | Fact initially uses unknown key and has a documented correction process. | Medium | Not Run
TC-018 | 2 - SCD Type 2 | Audit | Capture change metadata | Related object for REQ-018 is deployed | Prepare minimum data for Capture change metadata; execute relevant SQL; compare actual result with acceptance criteria. | Version history is traceable to source and batch. | Critical | Not Run
TC-019 | 3 - Revenue Analytics | Metric | Define revenue | Related object for REQ-019 is deployed | Prepare minimum data for Define revenue; execute relevant SQL; compare actual result with acceptance criteria. | One approved SQL expression defines the metric. | Critical | Not Run
TC-020 | 3 - Revenue Analytics | Analytics | Monthly customer revenue | Related object for REQ-020 is deployed | Prepare minimum data for Monthly customer revenue; execute relevant SQL; compare actual result with acceptance criteria. | Result reconciles to the fact table for the same filters. | Critical | Not Run
TC-021 | 3 - Revenue Analytics | Analytics | Previous month comparison | Related object for REQ-021 is deployed | Prepare minimum data for Previous month comparison; execute relevant SQL; compare actual result with acceptance criteria. | January-to-December boundary works correctly. | Critical | Not Run
TC-022 | 3 - Revenue Analytics | Analytics | Growth percentage | Related object for REQ-022 is deployed | Prepare minimum data for Growth percentage; execute relevant SQL; compare actual result with acceptance criteria. | No divide-by-zero error; documented null/zero rules are applied. | Critical | Not Run
TC-023 | 3 - Revenue Analytics | Analytics | Zero-activity month handling | Related object for REQ-023 is deployed | Prepare minimum data for Zero-activity month handling; execute relevant SQL; compare actual result with acceptance criteria. | Output follows the documented reporting behavior. | Medium | Not Run
TC-024 | 3 - Revenue Analytics | Analytics | Revenue trend | Related object for REQ-024 is deployed | Prepare minimum data for Revenue trend; execute relevant SQL; compare actual result with acceptance criteria. | Totals remain consistent across hierarchy levels. | Medium | Not Run
TC-025 | 3 - Revenue Analytics | Currency | Reporting currency rule | Related object for REQ-025 is deployed | Prepare minimum data for Reporting currency rule; execute relevant SQL; compare actual result with acceptance criteria. | Cross-currency totals only appear after conversion. | Critical | Not Run
TC-026 | 4 - Deduplication | Quality | Identify duplicate order events | Related object for REQ-026 is deployed | Prepare minimum data for Identify duplicate order events; execute relevant SQL; compare actual result with acceptance criteria. | Duplicate counts and affected keys are reported. | Critical | Not Run
TC-027 | 4 - Deduplication | Quality | Define survivor rule | Related object for REQ-027 is deployed | Prepare minimum data for Define survivor rule; execute relevant SQL; compare actual result with acceptance criteria. | Exactly one survivor exists per business key. | Critical | Not Run
TC-028 | 4 - Deduplication | Quality | Implement ROW_NUMBER | Related object for REQ-028 is deployed | Prepare minimum data for Implement ROW_NUMBER; execute relevant SQL; compare actual result with acceptance criteria. | Dedup output has no duplicate natural keys. | Critical | Not Run
TC-029 | 4 - Deduplication | Quality | Quarantine rejected rows | Related object for REQ-029 is deployed | Prepare minimum data for Quarantine rejected rows; execute relevant SQL; compare actual result with acceptance criteria. | Rejected rows can be audited and replayed. | Medium | Not Run
TC-030 | 4 - Deduplication | Quality | Ensure idempotency | Related object for REQ-030 is deployed | Prepare minimum data for Ensure idempotency; execute relevant SQL; compare actual result with acceptance criteria. | Row counts remain unchanged after rerun. | Critical | Not Run
TC-031 | 4 - Deduplication | Quality | Handle exact ties | Related object for REQ-031 is deployed | Prepare minimum data for Handle exact ties; execute relevant SQL; compare actual result with acceptance criteria. | Repeated execution selects the same row. | Critical | Not Run
TC-032 | 5 - Delivery Delay | Metric | Define delivery duration | Related object for REQ-032 is deployed | Prepare minimum data for Define delivery duration; execute relevant SQL; compare actual result with acceptance criteria. | Rule and SQL expression are documented. | Critical | Not Run
TC-033 | 5 - Delivery Delay | Metric | Identify late delivery | Related object for REQ-033 is deployed | Prepare minimum data for Identify late delivery; execute relevant SQL; compare actual result with acceptance criteria. | Boundary checks for day 7 and day 8 pass. | Critical | Not Run
TC-034 | 5 - Delivery Delay | Analytics | Create non-overlapping buckets | Related object for REQ-034 is deployed | Prepare minimum data for Create non-overlapping buckets; execute relevant SQL; compare actual result with acceptance criteria. | Every non-negative duration maps to exactly one bucket. | Critical | Not Run
TC-035 | 5 - Delivery Delay | Quality | Handle undelivered shipments | Related object for REQ-035 is deployed | Prepare minimum data for Handle undelivered shipments; execute relevant SQL; compare actual result with acceptance criteria. | Null date does not appear as zero delay. | Critical | Not Run
TC-036 | 5 - Delivery Delay | Quality | Handle invalid chronology | Related object for REQ-036 is deployed | Prepare minimum data for Handle invalid chronology; execute relevant SQL; compare actual result with acceptance criteria. | Negative duration is visible as a data-quality exception. | Critical | Not Run
TC-037 | 5 - Delivery Delay | Analytics | Delay KPI output | Related object for REQ-037 is deployed | Prepare minimum data for Delay KPI output; execute relevant SQL; compare actual result with acceptance criteria. | KPI denominators are documented and reconcilable. | Medium | Not Run
TC-038 | 6 - Top Customers | Analytics | Rank within country | Related object for REQ-038 is deployed | Prepare minimum data for Rank within country; execute relevant SQL; compare actual result with acceptance criteria. | Each country begins at rank 1. | Critical | Not Run
TC-039 | 6 - Top Customers | Analytics | Top 10 per country | Related object for REQ-039 is deployed | Prepare minimum data for Top 10 per country; execute relevant SQL; compare actual result with acceptance criteria. | No country returns rank above 10. | Critical | Not Run
TC-040 | 6 - Top Customers | Analytics | Define tie behavior | Related object for REQ-040 is deployed | Prepare minimum data for Define tie behavior; execute relevant SQL; compare actual result with acceptance criteria. | Tie test matches documented behavior. | Critical | Not Run
TC-041 | 6 - Top Customers | History | Use transaction-time geography | Related object for REQ-041 is deployed | Prepare minimum data for Use transaction-time geography; execute relevant SQL; compare actual result with acceptance criteria. | Historical country does not change when the customer later moves. | Medium | Not Run
TC-042 | 6 - Top Customers | Metric | Parameterize period | Related object for REQ-042 is deployed | Prepare minimum data for Parameterize period; execute relevant SQL; compare actual result with acceptance criteria. | Date filters are sargable and totals reconcile. | Medium | Not Run
TC-043 | 7 - Incremental Load | Control | Create watermark table | Related object for REQ-043 is deployed | Prepare minimum data for Create watermark table; execute relevant SQL; compare actual result with acceptance criteria. | Each load has a recoverable control state. | Critical | Not Run
TC-044 | 7 - Incremental Load | Extraction | Read bounded source window | Related object for REQ-044 is deployed | Prepare minimum data for Read bounded source window; execute relevant SQL; compare actual result with acceptance criteria. | Concurrent source changes are deferred safely to the next run. | Critical | Not Run
TC-045 | 7 - Incremental Load | Control | Advance only on success | Related object for REQ-045 is deployed | Prepare minimum data for Advance only on success; execute relevant SQL; compare actual result with acceptance criteria. | Failed run leaves previous successful watermark unchanged. | Critical | Not Run
TC-046 | 7 - Incremental Load | Recovery | Support restart | Related object for REQ-046 is deployed | Prepare minimum data for Support restart; execute relevant SQL; compare actual result with acceptance criteria. | Injected failure can be rerun to a correct final state. | Critical | Not Run
TC-047 | 7 - Incremental Load | Quality | Persist batch metrics | Related object for REQ-047 is deployed | Prepare minimum data for Persist batch metrics; execute relevant SQL; compare actual result with acceptance criteria. | Batch-control totals reconcile. | Critical | Not Run
TC-048 | 7 - Incremental Load | Deletion | Define source-delete strategy | Related object for REQ-048 is deployed | Prepare minimum data for Define source-delete strategy; execute relevant SQL; compare actual result with acceptance criteria. | Deleted-source behavior is documented and tested. | Medium | Not Run
TC-049 | 7 - Incremental Load | Late Data | Apply lookback window | Related object for REQ-049 is deployed | Prepare minimum data for Apply lookback window; execute relevant SQL; compare actual result with acceptance criteria. | Late update is captured without duplicates. | Medium | Not Run
TC-050 | 7 - Incremental Load | Concurrency | Prevent overlapping runs | Related object for REQ-050 is deployed | Prepare minimum data for Prevent overlapping runs; execute relevant SQL; compare actual result with acceptance criteria. | Second concurrent run is blocked or exits safely. | Medium | Not Run
TC-051 | 7 - Incremental Load | Operations | Create operational logging | Related object for REQ-051 is deployed | Prepare minimum data for Create operational logging; execute relevant SQL; compare actual result with acceptance criteria. | Failed batch has actionable diagnostics. | Critical | Not Run
TC-052 | 8 - Performance Tuning | Baseline | Capture baseline | Related object for REQ-052 is deployed | Prepare minimum data for Capture baseline; execute relevant SQL; compare actual result with acceptance criteria. | Before metrics and plan are saved. | Critical | Not Run
TC-053 | 8 - Performance Tuning | Indexing | Design clustered strategy | Related object for REQ-053 is deployed | Prepare minimum data for Design clustered strategy; execute relevant SQL; compare actual result with acceptance criteria. | Decision is justified against measured workload. | Critical | Not Run
TC-054 | 8 - Performance Tuning | Indexing | Design covering indexes | Related object for REQ-054 is deployed | Prepare minimum data for Design covering indexes; execute relevant SQL; compare actual result with acceptance criteria. | Plan and measured reads demonstrate benefit. | Critical | Not Run
TC-055 | 8 - Performance Tuning | Partitioning | Evaluate date partitioning | Related object for REQ-055 is deployed | Prepare minimum data for Evaluate date partitioning; execute relevant SQL; compare actual result with acceptance criteria. | Partition elimination is demonstrated for date-filtered query. | Medium | Not Run
TC-056 | 8 - Performance Tuning | SQL | Remove non-sargable predicates | Related object for REQ-056 is deployed | Prepare minimum data for Remove non-sargable predicates; execute relevant SQL; compare actual result with acceptance criteria. | Seek-capable predicate is visible where appropriate. | Critical | Not Run
TC-057 | 8 - Performance Tuning | Statistics | Maintain statistics | Related object for REQ-057 is deployed | Prepare minimum data for Maintain statistics; execute relevant SQL; compare actual result with acceptance criteria. | Estimated and actual row counts improve. | Medium | Not Run
TC-058 | 8 - Performance Tuning | Aggregation | Create summary table | Related object for REQ-058 is deployed | Prepare minimum data for Create summary table; execute relevant SQL; compare actual result with acceptance criteria. | Aggregate reconciles and improves measured performance. | Medium | Not Run
TC-059 | 8 - Performance Tuning | Analysis | Detect skew and parameter issues | Related object for REQ-059 is deployed | Prepare minimum data for Detect skew and parameter issues; execute relevant SQL; compare actual result with acceptance criteria. | Findings are tied to plan evidence. | Medium | Not Run
TC-060 | 8 - Performance Tuning | Regression | Compare before and after | Related object for REQ-060 is deployed | Prepare minimum data for Compare before and after; execute relevant SQL; compare actual result with acceptance criteria. | Output checksum/count matches baseline and metrics are captured. | Critical | Not Run
TC-061 | 9 - Reconciliation & RCA | Reconciliation | Build source-to-target control totals | Related object for REQ-061 is deployed | Prepare minimum data for Build source-to-target control totals; execute relevant SQL; compare actual result with acceptance criteria. | Differences are zero or explained. | Critical | Not Run
TC-062 | 9 - Reconciliation & RCA | RCA | Investigate revenue restatement | Related object for REQ-062 is deployed | Prepare minimum data for Investigate revenue restatement; execute relevant SQL; compare actual result with acceptance criteria. | Evidence identifies or narrows the variance without guessing. | Critical | Not Run
TC-063 | 9 - Reconciliation & RCA | Reconciliation | Classify variances | Related object for REQ-063 is deployed | Prepare minimum data for Classify variances; execute relevant SQL; compare actual result with acceptance criteria. | Every unresolved difference has an owner/status. | Medium | Not Run
TC-064 | 9 - Reconciliation & RCA | Audit | Create lineage evidence | Related object for REQ-064 is deployed | Prepare minimum data for Create lineage evidence; execute relevant SQL; compare actual result with acceptance criteria. | Sample metric can be traced end to end. | Critical | Not Run
TC-065 | 9 - Reconciliation & RCA | Quality | Set reconciliation thresholds | Related object for REQ-065 is deployed | Prepare minimum data for Set reconciliation thresholds; execute relevant SQL; compare actual result with acceptance criteria. | Threshold breaches fail or warn according to rule. | Critical | Not Run
TC-066 | 9 - Reconciliation & RCA | Operations | Create support runbook | Related object for REQ-066 is deployed | Prepare minimum data for Create support runbook; execute relevant SQL; compare actual result with acceptance criteria. | Another engineer can follow the runbook. | Medium | Not Run
TC-067 | 10 - Packaging & Portfolio | Delivery | Organize source control | Related object for REQ-067 is deployed | Prepare minimum data for Organize source control; execute relevant SQL; compare actual result with acceptance criteria. | Fresh checkout contains all required assets. | Critical | Not Run
TC-068 | 10 - Packaging & Portfolio | Delivery | Create deployment order | Related object for REQ-068 is deployed | Prepare minimum data for Create deployment order; execute relevant SQL; compare actual result with acceptance criteria. | Empty database can be deployed successfully. | Critical | Not Run
TC-069 | 10 - Packaging & Portfolio | Documentation | Create architecture document | Related object for REQ-069 is deployed | Prepare minimum data for Create architecture document; execute relevant SQL; compare actual result with acceptance criteria. | Document is consistent with implementation. | Critical | Not Run
TC-070 | 10 - Packaging & Portfolio | Evidence | Capture test evidence | Related object for REQ-070 is deployed | Prepare minimum data for Capture test evidence; execute relevant SQL; compare actual result with acceptance criteria. | All critical tests pass before completion. | Critical | Not Run
TC-071 | 10 - Packaging & Portfolio | Evidence | Capture performance evidence | Related object for REQ-071 is deployed | Prepare minimum data for Capture performance evidence; execute relevant SQL; compare actual result with acceptance criteria. | Claims are supported by measurements. | Medium | Not Run
TC-072 | 10 - Packaging & Portfolio | Portfolio | Prepare honest resume wording | Related object for REQ-072 is deployed | Prepare minimum data for Prepare honest resume wording; execute relevant SQL; compare actual result with acceptance criteria. | Resume wording has no unverified client or production claims. | Critical | Not Run
TC-073 | 10 - Packaging & Portfolio | Interview | Prepare design defense | Related object for REQ-073 is deployed | Prepare minimum data for Prepare design defense; execute relevant SQL; compare actual result with acceptance criteria. | A concise walkthrough and deep-dive answers are prepared. | Critical | Not Run
TC-074 | 1 - Warehouse Modeling | Grain | Same product repeated on two order lines | Order has same ProductID on line 1 and line 2 | Load both source lines | FactOrders contains two rows because grain includes OrderLineNumber. | High | Not Run
TC-075 | 1 - Warehouse Modeling | Unknown Key | Missing customer lookup | Order references absent CustomerID | Run fact load | Fact uses unknown CustomerSK and row is logged for follow-up. | High | Not Run
TC-076 | 2 - SCD Type 2 | History | Multiple sequential changes | Customer moves city and later changes type | Run loads in timestamp order | Three non-overlapping versions exist and only latest is current. | High | Not Run
TC-077 | 2 - SCD Type 2 | Null Handling | Tracked attribute changes from null | Current City is null; source City has value | Run SCD load | Prior row is expired and new row is inserted. | High | Not Run
TC-078 | 3 - Revenue Analytics | Growth | Prior revenue is zero | Customer has zero prior-month revenue | Run growth query | No divide-by-zero error and documented output rule is applied. | High | Not Run
TC-079 | 3 - Revenue Analytics | Calendar | No activity in prior month | Customer has revenue this month but no prior row | Run growth query | Prior value/growth follows the documented missing-month rule. | High | Not Run
TC-080 | 4 - Deduplication | Tie Break | Equal timestamps | Two duplicate rows have equal modified and ingestion timestamps | Run dedup twice | Same deterministic survivor is selected both times. | High | Not Run
TC-081 | 5 - Delivery Delay | Boundary | Exactly 7 days | Shipment and delivery differ by 7 days | Run delay classification | Late flag is false and bucket is 4-7 Days. | High | Not Run
TC-082 | 5 - Delivery Delay | Boundary | Exactly 8 days | Shipment and delivery differ by 8 days | Run delay classification | Late flag is true and bucket is 8-15 Days. | High | Not Run
TC-083 | 5 - Delivery Delay | Boundary | Exactly 15 and 16 days | Create two shipments | Run bucket query | 15 maps to 8-15; 16 maps to 16+. | High | Not Run
TC-084 | 6 - Top Customers | Ties | Revenue tie at rank 10 | Two customers share boundary revenue | Run ranking | Output follows selected RANK or DENSE_RANK policy. | High | Not Run
TC-085 | 7 - Incremental Load | Failure | Failure before watermark update | Inject failure after target staging | Rerun load | Watermark remains old and rerun reaches correct result without duplication. | High | Not Run
TC-086 | 7 - Incremental Load | Boundary | Record equals high watermark | Source row timestamp equals captured high watermark | Run load | Row is included based on greater-than/less-than-or-equal window. | High | Not Run
TC-087 | 8 - Performance Tuning | Correctness | Optimized query output | Baseline output saved | Run optimized query | Counts, totals and sample rows match baseline. | High | Not Run
TC-088 | 9 - Reconciliation & RCA | Rounding | Currency rounding variance | Prepare known rounding differences | Run threshold rule | Difference within tolerance warns/passes per policy; larger difference fails. | High | Not Run

## Data Dictionary
Logical Data Dictionary
Object | Column | Role | Suggested Type | Nullable | Key / Rule | Definition | Example | Notes
DimCustomer | CustomerSK | Surrogate key | BIGINT | No | PK | Warehouse-generated customer version key | 101 | Referenced by facts
DimCustomer | CustomerID | Business key | VARCHAR(50) | No | Indexed | Source customer identifier | C1001 | Retain source key
DimCustomer | CustomerName | Attribute | VARCHAR(200) | No |  | Customer display name | Contoso Logistics
DimCustomer | Country | SCD2 attribute | VARCHAR(100) | Yes |  | Customer country for this version | India | Tracked
DimCustomer | City | SCD2 attribute | VARCHAR(100) | Yes |  | Customer city for this version | Chennai | Tracked
DimCustomer | CustomerType | SCD2 attribute | VARCHAR(50) | Yes |  | Business classification | Enterprise | Tracked
DimCustomer | EffectiveFrom | History | DATETIME2 | No |  | Version start time | 2026-09-01 10:00 | Inclusive
DimCustomer | EffectiveTo | History | DATETIME2 | No |  | Version end time | 9999-12-31 | Convention must be documented
DimCustomer | IsCurrent | History | BIT | No |  | Current version flag | 1 | One current row per CustomerID
DimProduct | ProductSK | Surrogate key | BIGINT | No | PK | Warehouse product key | 201
DimProduct | ProductID | Business key | VARCHAR(50) | No | Unique current key | Source product identifier | P100
DimProduct | ProductName | Attribute | VARCHAR(200) | No |  | Product name | Laptop
DimProduct | Category | Attribute | VARCHAR(100) | Yes |  | Product category | Electronics
DimProduct | CostPrice | Measure-like attribute | DECIMAL(19,4) | Yes |  | Reference cost; transaction cost is preferable for historical margin | 450.00 | Do not rely on current value for historical fact if price changes
DimProduct | SellingPrice | Measure-like attribute | DECIMAL(19,4) | Yes |  | Reference selling price | 500.00 | Store actual amount in fact
DimDate | DateSK | Smart key | INT | No | PK | YYYYMMDD date key | 20260901 | Unknown key handled separately
DimDate | FullDate | Date | DATE | No | Unique | Calendar date | 2026-09-01
DimDate | MonthNumber | Calendar | TINYINT | No |  | Month number | 9
DimDate | MonthName | Calendar | VARCHAR(10) | No |  | Month name | September
DimDate | QuarterNumber | Calendar | TINYINT | No |  | Calendar quarter | 3
DimDate | CalendarYear | Calendar | SMALLINT | No |  | Calendar year | 2026
DimLocation | LocationSK | Surrogate key | BIGINT | No | PK | Warehouse location key | 301
DimLocation | Country | Attribute | VARCHAR(100) | No |  | Country | India
DimLocation | City | Attribute | VARCHAR(100) | Yes |  | City | Chennai
FactOrders | OrderID | Degenerate/business key | VARCHAR(50) | No | Business key component | Source order identifier | O50001
FactOrders | OrderLineNumber | Grain key | INT | No | Business key component | Line inside order | 1 | Required for precise grain
FactOrders | CustomerSK | Foreign key | BIGINT | No | FK | Customer version valid for the order | 101
FactOrders | ProductSK | Foreign key | BIGINT | No | FK | Product dimension key | 201
FactOrders | OrderDateSK | Foreign key | INT | No | FK | Order-date role key | 20260901
FactOrders | LocationSK | Foreign key | BIGINT | No | FK | Transaction/customer location key per design | 301
FactOrders | Quantity | Measure | DECIMAL(18,3) | No | Additive | Ordered quantity | 5
FactOrders | GrossAmount | Measure | DECIMAL(19,4) | No | Additive | Amount before adjustments | 2500.00
FactOrders | NetAmount | Measure | DECIMAL(19,4) | No | Additive | Approved revenue expression result | 2400.00 | Definition required
FactOrders | BatchID | Audit | BIGINT | No |  | Load batch identifier | 9001
FactShipment | ShipmentID | Business key | VARCHAR(50) | No | Business key | Source shipment identifier | S90001
FactShipment | OrderID | Relationship key | VARCHAR(50) | No |  | Related order identifier | O50001 | Bridge/order-line approach needed for split allocation
FactShipment | ShipmentDateSK | Foreign key | INT | Yes | FK | Shipment date role | 20260902
FactShipment | DeliveryDateSK | Foreign key | INT | Yes | FK | Delivery date role | 20260908 | Null when undelivered
FactShipment | FreightCost | Measure | DECIMAL(19,4) | Yes | Additive | Shipment freight cost | 100.00
FactShipment | DeliveryDays | Derived | INT | Yes |  | Duration under agreed calendar rule | 6 | Can be computed or persisted
ETLWatermark | PipelineName | Control key | VARCHAR(200) | No | PK component | Logical pipeline identifier | LoadFactOrders
ETLWatermark | LastSuccessfulWatermark | Control value | DATETIME2 | Yes |  | Last committed source boundary | 2026-09-01 00:00 | Update only on success
ETLBatchAudit | BatchID | Audit key | BIGINT | No | PK | Unique load execution identifier | 9001
ETLBatchAudit | Status | Audit status | VARCHAR(20) | No |  | Started, Completed or Failed | Completed

## Dashboard
Project Completion Dashboard
Overall KPIs
Total Requirements | 73
Total Small Tasks | 365
Planned Hours | 340.5
Actual Hours | 0
Task Completion | 0%
Tests Passed | 0
Tests Failed | 0
Test Pass Rate | 0%
Phase | Planned Hours | Completed Weighted Hours | Completion % | Task Count | Completed Tasks
1 - Warehouse Modeling | 44 | 0 | 0% | 50 | 0
2 - SCD Type 2 | 37.5 | 0 | 0% | 40 | 0
3 - Revenue Analytics | 32 | 0 | 0% | 35 | 0
4 - Deduplication | 28 | 0 | 0% | 30 | 0
5 - Delivery Delay | 29 | 0 | 0% | 30 | 0
6 - Top Customers | 22 | 0 | 0% | 25 | 0
7 - Incremental Load | 44 | 0 | 0% | 45 | 0
8 - Performance Tuning | 43.5 | 0 | 0% | 45 | 0
9 - Reconciliation & RCA | 28.5 | 0 | 0% | 30 | 0
10 - Packaging & Portfolio | 32 | 0 | 0% | 35 | 0
Test Status | Count
Not Run | 88
Passed | 0
Failed | 0
Blocked | 0

## Risks & Decisions
Risks, Assumptions and Design Decisions
ID | Type | Phase | Item | Impact | Mitigation / Decision | Owner | Status | Review Notes
R-001 | Risk | 1 - Warehouse Modeling | Order source lacks OrderLineNumber | Cannot guarantee one row per line when product repeats | Create deterministic line identifier from source; do not assume OrderID + ProductID is always unique. | Mukesh | Open
R-002 | Risk | 3 - Revenue Analytics | Revenue definition is ambiguous | Different reports can show different totals | Create a signed metric definition including discounts, cancellations, tax, currency and recognition date. | Mukesh | Open
R-003 | Risk | 7 - Incremental Load | Timestamp precision or timezone mismatch | Rows may be missed or duplicated | Normalize timezone, use bounded windows and test exact-boundary timestamps. | Mukesh | Open
R-004 | Risk | 8 - Performance Tuning | Synthetic volume too small | Index/partition findings may not represent scale | Generate sufficient distribution and compare plans and logical reads; label results as local benchmark. | Mukesh | Open
R-005 | Risk | 2 - SCD Type 2 | Concurrent updates create two current versions | History becomes invalid | Use transactional logic and current-row uniqueness protection. | Mukesh | Open
A-001 | Assumption | All | Practice data is synthetic | Cannot claim real client volume or production impact | Clearly label project and metrics as self-directed portfolio results. | Mukesh | Accepted
D-001 | Decision | 5 - Delivery Delay | Delay buckets use 16+ final bucket | Avoids overlap between 8-15 and 15+ | Use CASE boundaries: 0-3, 4-7, 8-15, 16+. | Mukesh | Accepted
D-002 | Decision | 1 - Warehouse Modeling | Facts will use surrogate dimension keys | Supports history and source-system independence | Retain source keys as audit/business identifiers. | Mukesh | Accepted

## Resume Notes
Portfolio and Resume Notes
Recommended Project Title | Global Logistics SQL Data Warehouse ¦ Self-Directed Portfolio Project
Use after implementation
• Designed a SQL Server star schema for logistics order and shipment analytics, defining fact grains, surrogate-key dimensions, role-playing dates, audit columns and unknown-member handling.
• Implemented SCD Type 2 customer history with null-safe change detection, non-overlapping effective periods, current-version enforcement and idempotent rerun behavior.
• Built reusable SQL analytics for monthly revenue, prior-period growth, country-level customer ranking and delivery-delay classification using window functions and dimensional joins.
• Developed restartable incremental-load controls using bounded watermarks, batch auditing, reconciliation metrics, reject handling and failure-recovery tests.
• Benchmarked and tuned reporting queries using execution plans, logical reads, sargable predicates, indexing and aggregate-table design; report only the improvements actually measured in your environment.
Do Not Claim
• Do not call it a client project unless it was delivered for a real client.
• Do not claim 500 million production rows unless you actually tested that volume.
• Do not claim a percentage performance improvement until your before/after evidence supports it.
• Do not list a technology that is not present in your implementation repository.
Interview Walkthrough
1. Business problem and metric definitions
2. Fact grain and dimensional model
3. Loading order and SCD Type 2 behavior
4. Incremental loading, idempotency and recovery
5. Data-quality and reconciliation controls
6. Query-plan evidence and tuning trade-offs
7. Limitations and what you would change at production scale